“FACTOR AFFECTING COST OF ROAD CONSTRUCTION IN GHANA”

BY

BOATENG, Enoch

(BSc. Quantity Surveying and Construction Economics)

A thesis submitted to the Department of Construction Technology and Management, Kwame Nkrumah University of Science and Technology, Kumasi in partial fulfilment of the requirement for the award degree of

MASTER OF SCIENCE IN PROJECT MANAGEMENT

NOVEMBER, 2019

# DECLARATION

I hereby declare that, this thesis submission is my own work towards the MSc. Project Management and that to the best of my knowledge, it contains no material previously published by another person nor material which has been accepted for the award of any other degree of the university except where due acknowledgement has been made in the text.

BOATENG, Enoch 	              	.......................................                         …………………………

PG 5043618                                             	Signature                                            Date

Certified by:

Rev. PROF. FRANK. FUGAR                 ………………………….                 …………………………

Supervisor                                                               Signature                                          Date

Certified by:

PROF. BERNARD KOFI BAIDEN          .........................................              ........................................

Head of Department 				      Signature                                        Date

## ABSTRACT

Road construction projects are essential to the social and economic development of Ghana, but one major challenge to road construction projects in Ghana is cost. There are factors that affects the cost of road construction in Ghana. The aim of the study is to find out the factors affecting cost of road construction in Ghana and propose possible solutions to how road construction cost can be reduced. The objectives were to identify, the relative importance of the factors affecting the cost of road construction, the severity of the factors leading to high cost of road construction in Ghana, and the possible measures to minimizing road construction cost in Ghana. Structured questionnaire survey was deployed for this study, whiles purposive sampling technique was used in selecting respondents. Relative importance index and mean score ranking were the tools used in the analysis of this study. The study identified bureaucracy in tendering methods, delay in construction, political interference, price fluctuation, delays in monthly payments, material cost and fraudulent practises and kickbacks as severe causes of road construction cost in Ghana. The study further identified delays in construction, delays in monthly payments, bureaucracy in tendering methods, political interference, poor financial control on site, price fluctuations and variations as the most important factors affecting the cost of road construction in Ghana. The study concluded on the following as the most effective ways of minimizing road construction cost in Ghana as managerial measures in the form of securing adequate source of funds, good project management practices, proper inventory and feasibility studies, efficient time management through proper resource planning, duration estimation and schedule development and control, demonstrate adequate knowledge in road construction, and hire the services of experience and qualified personnel.

Keywords: Factors, Severity, road construction

# TABLE OF CONTENTS

DECLARATION	i

ABSTRACT	ii

TABLE OF CONTENTS	iii

LIST OF TABLES	vi

ACKNOWLEDGEMENTS	vii

DEDICATION	viii

CHAPTER ONE	1

1.0 INTRODUCTION	1

1.1 Background	1

1.2 Problem Statement	2

1.3 Justification	2

1.4 Aim	3

1.5 Objectives	3

1.6 Scope and Limitations	3

1.7 Methodology	3

1.8 Structure of Study	4

CHAPTER TWO	5

2.0 LITERATURE REVIEW	5

2.1 Introduction	5

2.2 The Ghanaian Road Construction industry	5

2.3 The Roles of Principal stakeholders in Road Construction	6

2.3.1 The Client	6

2.3.2 The Consultant	7

2.3.3 The Contractor	7

2.4 Road Construction Cost Issues	7

2.5 Further Review on Road Construction Related Cost Issues	10

2.5.1 Improper planning	10

2.5.2 Sham practices and inducements	10

2.5.3 Design Change	11

2.5.4 Political Meddling	11

2.5.5 Connection between management and labour	12

2.5.6 Contract Administration	12

2.5.7 Lack of coordination between designers and contractors	12

2.5.8 Additional Work	12

2.5.9 Lack of Financial control on site	13

2.5.10Variations	13

2.5.11 Inflation	13

2.5.12 Schedule slippage	13

2.5.13 Contract procedure	14

2.5.14 Lack of project knowledge and Underestimating	14

2.5.15 Transportation cost	15

2.5.16 Time of contract period	15

2.6 Minimizing Road Construction Cost	15

2.6.1 Avoid delay payment	15

2.6.2 Estimating Methods	16

2.6.3 Contract Administration	16

CHAPTER THREE	17

3.0 METHODOLOGY	17

3.1 Introduction	17

3.2 Research Strategy	17

3.3 Research Population and Sampling used in the Study	17

3.4 Sampling design and procedures	18

3.5 Means of Data collection	18

3.6 Management of the data collection	18

3.7 Data exploration	18

CHAPTER FOUR	19

4.0 DATA PRESENTATION, ANALYSES AND DISCUSSION	19

4.1 Personal Information of Respondent	19

4.2 Issues Affecting Cost of Road Construction in Ghana	21

4.3 Severity of the Issues Leading to High Cost of Road Construction in Ghana	26

4.4 Measures to Reduce Road Construction Cost in Ghana	31

CHAPTER FIVE	36

5.0 SUMMARY OF FINDINGS, CONCLUSION AND RECOMMENDATIONS	36

5.1 Summary of Findings	36

5.1.1 Main Issues Affecting Cost of Road Construction in Ghana	36

5.1.2 Severe Cause of the Issues Leading to High Cost of Road Construction in Ghana	36

5.1.3 Measures to Reduce Road Construction Cost in Ghana	37

5.2 Conclusion	37

5.3 Recommendations	38

5.3.1 Ensure Adequate and Regular Source of Funding	39

5.3.2 Good Project Management Practices	39

5.3.3 Proper Inventory and Feasibility Studies	40

5.3.4 Employ Experience and Qualified Personnel	40

5.3.5 Proper Tendering Procedure	40

5.4 Suggested Areas for Further Studies	40

REFERENCES	42

APPENDIX	48

# LIST OF TABLES

Table 2.1 Shows Road Construction connected Cost Issues	9

Table 4.1: Socio-Demographic Data of Respondent	19

Table 4.2: Relative Important Issues Affecting Cost of Road Construction in Ghana	21

Table 4.3: Severity of Issues Leading to High Cost of Road Construction	26

Table 4.4: Measures to Minimizing Road Construction Cost	32

# ACKNOWLEDGEMENTS

My greatest appreciation goes to the Uppermost God for His endless love and compassion conferred on me throughout the period of my study.

I wish to also express my profound gratitude to my supervisor Rev. Professor Frank Fugar for without his enormous assistance, useful comments and dedicated involvement in every step throughout the process, this study would have never been accomplished.

Many thanks also goes to all my lecturers for their academic support and the knowledge imparted in me throughout my study on campus.

Getting through this programme successfully would not have been a reality without the unwavering support of my family especially my Parents Mr.& Mrs Nyarko, my beloved son Benedict Agyapong Boateng, my lovely wife Jennifer K. Boateng and not forgetting my colleagues and friends. I am forever grateful for having you around me and for all the prayers and moral support offered me.

Finally, I say a very big thank you to all the respondents of the Questionnaire Survey for your time and contribution to the success of the survey.

May the Lord God Almighty bless you all.

# DEDICATION

This thesis is dedicated to the Almighty God

# CHAPTER ONE

## INTRODUCTION

# 1.1 Background

Road construction is key to the infrastructural development of the country, (Ankomah et al., 2010) though there is a short fall of roads in the country, governments are committed to improving the situation. Funding for road projects has been a big challenge for the various agencies in charge of road construction in Ghana. Road Construction is pivotal to developing countries and an active process throughout the difference phases of economic growth. This phenomenon is more so emphasized in developing countries such as Ghana which is in its take-off phase of economic development. Road construction at the national level involves a tendering process that leads to awards of contracts to registered individuals or to large construction companies. Due to unstable economic condition in the world especially Ghana, road construction have been neglected for some time now. Governments want to get value for money in all the road projects undertaken.  Road projects related cost are normally the sum total of the following cost parameters: Materials component, Labour component, Equipment’s, Head office and site overheads Cost Plus Profit. There are other components such as fluctuation and contingencies that add up to the cost of road construction. These costs have serious consequences for the stakeholders in the road construction sector. Mbachu and Nkado (2004) To the client (generally the Government and other donor agencies), high cost entails extra costs over originally estimated cost at the start of the project, this may not be what the client intended from the start. On the part of consultants, it means unable to protect the clients interest and could result in damage of their status and end up in tarnishing their image and the confidence vest in them. The contractor on the other hand, it infers loss of business coupled with the loss of profit as a result of penalties paid for non- compliance and high interest charged on bank loans. This can affect their chances of being awarded new contracts, if at fault. To the taxpayer whose taxes pay for most of the cost of road construction means increase in road tolls and levies. On the backdrop of this information, the current study seeks to tease out what essentially contributes to the issues affecting cost of road construction in Ghana. Evaluation of these issues affecting cost of road construction will serve as a means to bring out information on the key areas on cost that may be targeted for improvement.

## 1.2 Problem Statement

As Ghana goes through its economic transition, the number of road contracts is expected to increase on the backdrop of increasing developmental plans. This is evident from recent developments of the National Development Planning Commission (NDPC). The demand for roads is concurrently expected to increase. The problem of high cost of road contracts coupled with inflated prices of road construction is becoming obvious. Road construction projects are being awarded each and every time. The increase in road contract has brought about loss of trust and believe in the government agencies, consultants and contractors in general by the public and successive governments. Previous studies conducted in this area have only identify the relative importance of road construction related issues, Frimpong et al. (2003) this study would go a step further in giving possible strategies in reducing road construction cost.

## 1.3 Justification

Many studies have acknowledged the issues that contribute to the cost of the execution of contracts in Ghana. However, there have been few studies that have focused on the road sector which have been a major cause for concern in Ghana. This study will attempt to identify these issues that affects the cost of road construction and bring out key information that will seek to improve the sector significantly.

## 1.4 Aim

The purpose of the current study was to identify the issues affecting the cost of road construction in Ghana and propose possible strategies to reduce the cost of road construction.

## 1.5 Objectives

The objectives of this research work included:

- To find out the foremost issues affecting cost of road construction in Ghana.

- To find out the most severe causes leading to high cost of road construction in Ghana

- To propose possible strategies to reduce cost of road construction in Ghana

# 1.6 Scope and Limitations

Medium size road contracts funded by Ghana road fund, Ghana COCOBOD and the European Union awarded by all the agencies under the Ministry of roads and highways in the Ashanti region of Ghana is the main focus of this study. The study will be limited geographically to road projects in the Kumasi metropolitan area in Ashanti region of Ghana because Kumasi have a lot of road projects ongoing.

# 1.7 Methodology

The research strategy employed for this study was the quantitative research which was based on pervious study conducted in the study area. Relevant literature was review in the cause of the study.in order to achieve the aims and objectives questionnaire were distributed to collect relevant data for the study. The respondents included Project Managers, Civil Engineers, Quantity Surveyors, supervisors from both the contractors and consultants of road construction sites. Respondents were examined using a five-pointer Likert scale. Purposive sampling technique was used. Analysis of data collected was done using the Relative important index (RII) and the mean score ranking.

# 1.8 Structure of Study

This study has five main chapters. Introduction as Chapter one gave an overall background of the study. Literature review as Chapter two gave a thorough review of relevant past works conduct within the study area. Methodology as Chapter three describes how data would be collected. Chapter four gave us analysis of all the data collected from the survey. We concluded, summarized and recommended the study on Chapter five.

# CHAPTER TWO

# 2.0 LITERATURE REVIEW

# 2.1 Introduction

Past literature that gives a detailed breakdown of the challenges of escalating road construction cost in Ghana would be revised in this section. The chapter also looks at how these challenges can be reduced.

# 2.2 The Ghanaian Road Construction industry

Transportation in Ghana is mainly by road, and it represent an important sector for economic development. This has led to massive infrastructure projects with the aim of improving access to all rural communities and upgrading of all feeder roads. This will improve the life of beneficiary communities and access to those areas and reduce poverty.

Roads contributes immensely to the economic development of the nation since it is the main form of transport for goods and persons. Though there are other forms of transportation, roads are the main form of transport preferred by Ghanaians. Gidisu (2009) further emphasised the importance of road in the country, it connects to all areas of the country including farmlands and it transports foodstuffs form the hinterlands to the market centres. Roads also open up towns and villages to appreciable standards.  However, government finds it difficult maintaining and upgrading some of these road networks due to the lack of proper management of funds channelled into the road sector. Poor maintenance and bad construction practises have left our road networks in very bad and deplorable stage.

In Ghana, funding for road projects are mainly sourced from the Ghana Road fund whiles Donor agencies such as the European union, Ghana COCOABOD and others like the World Bank have been helping in this regard.

Financing most of these road projects have been a major cause for concern for successive governments over the years since government is the main financer for road contracts. (Eyiah and Cook, 2003). Most past governments go in for grants from others countries like Japan, China etc. just to finance most of our road projects.

The Ministry of Road and Highways (MRH) regulates the activities in the road construction industry in Ghana (Vulink, 2004). The Ministry play a range of roles in the Ghanaian road sector. (Ofori, 2012) They play the role of client and are also responsible for the registration and classification of road contractors respectively. Ghanaian road contractors are categorized as A, B, C, S, M, L and grouped into financial classes by the Ministry of Roads and Highways according to the size of individual projects they can bid for, and the maximum value of work they can have at any time.  They are further classified into four (4) financial sub-classifications 1, 2, 3 and 4 based on their asset base, plant and equipment holding, human resource capacity and the financial limits of jobs they can undertake (Agbodjah, 2008).

# 2.3 The Roles of Principal stakeholders in Road Construction

The nature of road construction is such that there a lot of stakeholders who have interest one way or the other just like any other form of construction in Ghana. These Stakeholders play different roles at different times but there are 3 main key stakeholders who matter most in road contracts. These key stakeholders are expatiated below:

# 2.3.1 The Client

Road construction is a huge capital venture therefore few individuals are able to initiate road construction projects. In Ghana government is the sole initiator of all road projects, he finances all road projects in the country. The government acts as client through the ministry of roads and highways. In other instances, the ministry of finance acts as client for the governments in the stance where the funding is sourced from outside. Governments try as much as possible to secure funds for road projects or make budgetary allocation for all road contracts. Economic turmoil makes it difficult for road contracts to be finance easily.

# 2.3.2 The Consultant

Consultants must stay focus to protect the interest of both the client and the contractor just like a referee in a football match, one of the responsibilities of the consultant is Cost considerations. In Ghana there are agencies under the ministries of roads and highway responsible for the design, supervision and award of all government road contracts. These agencies serve as consultants to the ministry, the include Ghana Highway Authority responsible for all the major truck roads and highways, there is also the Department of feeder roads who are responsible for the development of all the rural roads in Ghana. The department of urban roads are responsible for all urban and semi urban roads in the Ghana.

# 2.3.3 The Contractor

The contractor is the executor of the clients wish he is solely responsible for the construction of the project and makes sure the project is delivered within time, quality and budget to the client’s satisfaction. Omole (1986)

# 2.4 Road Construction Cost Issues

Raod construction is a huge capital venture it requires the use of heavy equipment, large volumes of materials and personnel therefore making it full of risks and uncertainties. The major problem that affect and turns to impact negatively on road projects in Ghana is cost. If the client’s financial capacity is not too strong it turns to affects the project. (Chileshe and Berko, 2010) highlighted the opinions of consultants, contractors and clients and concluded that suspension of payment certificates to contractors; changes in design; price increases, and schedule delays are the most significant issues affecting the cost of road contraction in Ghana. They further revelled that poor communication; technical complexity or size of road projects; force majeure; and dispute are not very important.  Project management practices were not all that popular within the Ghanaian road construction sector.  The study also found that risk management and Total Quality Management (TQM) though popular were not being effectively applied.

Road projects in Nigeria always results in cost overrun due to delays in execution this according to Odeyinka and Yusuf, (1997) who surveyed ten projects in Nigeria. Cost and time impact on projects were as a result of contractor’s management capabilities according to a study by Aje et al. (2009). Another study conducted by Hassanein and Afify (2007) revelled that indebtedness and unprofessional practises by contractors affects projects completion and cost. Another challenge found by Dada and Jagboro (2007) in the Road industry in Ghana is political influence and finance which affects the performance of both contractors and consultants.

In Indonesia the problem of inflation, underestimating and schedule slippage were dominant in a study conducted by Kaming, Olomolaiye, Holt, and Harris, (1997) as the main issues affecting cost of road construction.

In a related study by Enshassi, Al-Najjar, and Kumaraswamy (2009) revelled that project completion time were affected by boycott of work and immigration issues; resources issues; shortage of resources in marketplaces; and inability to deliver to the site on time, are four key reasons that affects cost within the Gaza strip.

In Ghana road construction related issues include suspension of payment certificates by agencies, lack of proper contract administration, purchase of material, lack of practical understanding of projects, increase in price of resources were among five significant issues identified by road construction stakeholders, according to Frimpong, et al (2003). Carpenter (1973) concluded that about 2/3 of project cost overrun can be attributed to design errors and omissions.

The unprofessional attitude of project quantity surveyors, coupled with late preparation of payment certificates, lack of claiming knowledge, consultant’s wastefulness and lack of competence by the workers at the agencies etc. were emphasised as the causes of delay and cost overrun in construction by Okumbe and Verster (2008) Civil involvement and contribution; estimate and sponsorship; workforce, purchase of material and understanding of the project were among the six critical risk issues that affects cost observed by Manelele and Muya (2008) in sub Saharan countries. Oladapo (2007); Arain and Pheng (2005) in a study concluded that changes in design and variation affects the cost of road construction.

Table 2.1 Shows Road Construction connected Cost Issues

| Road Construction connected Cost Issues | References |
| --- | --- |
| 1.Absence of construction cost data | Elinwa and Silas (1993) AL– Khaldi (1990) |
| 2.Additional work | Mansfield,Ugwu and Doran (1994) |
| 3.Bureaucy in tendering method | Mansfield,Ugwu and Doran (1994) Elinwa and Silas (1993) |
| 4. Contractor’s league | Omole (1986) |
| 5.Contract administration | Mansfield ,Ugwu and Doran(1994) Ogunlana, Krit and Vithool (1996 ) |
| 6.Contractual techniques | Elinwa and Silas (1993) AL– Khaldi (1990) |
| 7. Cost of resources | Elinwa and Silas (1993) |
| 8.Currency exchange | AL– Khaldi (1990) |
| 9.Differences on site | Aibinu and Jagboro (2002) |
| 10.Time of contract period | Aibinu and Jagboro (2002) |
| 11.Economic permanency | Elinwa and Silas (1993) |
| 12.Fluctuation of prices of materials | Omoreigie and Radford (2005) |
| 13. Sham practices and inducements | Hussain (1999), TELL (2002) |
| 14.Recurrent design changes | Asamoah (2002) |
| 15. Government programmes | Omole (1986) |
| 16. High cost of personnel | Elinwa and Silas (1993) |
| 17. High cost of equipment | Elinwa and Silas (1993) |
| 18. High cost of equipment maintenance | AL– Khaldi (1990) |
| 19.High cost of conveyance | Elinwa and Silas (1993) |
| 20. High interest rates charged by banks | AL– Khaldi (1990) |
| 21.Insufficient labour availability | Elinwa and Silas (1993) AL– Khaldi (1990) |
| 22.Insufficient production of raw materials | Eyo – Ita – Eyo (2001) |
| 23.Improper Planning | Elinwa and Silas (1993) |
| 24. Insurance cost | AL– Khaldi (1990) |
| 25.Workforce nationality | AL– Khaldi (1990) |
| 26.Lack of harmonisation between designers and contractors | AL– Khaldi (1990) |
| 27.Lack of efficiency standard | AL– Khaldi (1990) |
| 28.Level of contenders | AL– Khaldi (1990) |
| 29.Long period between design and tendering Time | Elinwa and Silas (1993) |
| 30. Means of funding bond and disbursements | Frimpong Oluwoye and Crawford (2003) |
| 31.Number of contenders | AL– Khaldi (1990) |
| 32.Work load on Contractors | Elinwa and Silas (1993) |
| 33. Experience of contractor | AL– Khaldi (1990) |
| 34. Political meddling | Omole (1986) |
| 35.lack of financial control on site | Ogunlana, Krit and Vithool (1996) |
| 36. Connection between management and labour | Elinwa and Silas (1993) |
| 37. Social and cultural impacts | AL– Khaldi (1990) |
| 38. Supplier and ethnic impacts | Manavazhi and Adhikari (2002) |
| 39. Supplier influence | Elinwa and Silas 1993) |
| 40. method of estimation | Mansfield ,Ugwu and Doran (1994) |

# 2.5 Further Review on Road Construction Related Cost Issues

# 2.5.1 Improper planning

The nature of road construction is such that it needs proper planning of all activities and proper utilisation of resources. Lack of proper planning and coordination on site turn to generates waste in the system which always cause the cost of activities to escalates. Well-coordinated road works always have goods basis for proper development of budget and work schedule. Planning is key in the use of modern equipment’s and technology of choice. Resources needed for road works must be known before works start. Proper planning and programming is key in the proper use of all resources, this in the long run reduce cost and make the project a success.

# 2.5.2 Sham practices and inducements

Corrupt practices were ranked second by Elinwa and Silas (1993) in a study conducted in the Nigerian road construction industry. This is evident in Ghana because both consultants and contractors engage in the act to complement each other. Sham practices and inducement followed with selfish act on the part of road construction actors was found out by Hussain (1999). Inflated contract price is as a result of contract for sale in the Ghanaian road construction industry. These issues affect the cost of major road contracts in Ghana. A documentary conducted by Joy news recently revealed how contracts are being sole to individuals who knows nothing about road construction this is as a result of greed and selfishness.

# 2.5.3 Design Change

This problem arose from insufficient project planning and management of the design process. This is an example of where road projects would increase up to 20- 30% of its initial cost. Frequent design changes are as a result of lack of proper inventory and indecisiveness on the part of city planners.

# 2.5.4 Political Meddling

Indigenous construction companies constitute majority of the contractors in Ghana. Most of the ministries and departments are made to award contract to party stalwarts at very high prices to offset campaign expenses all on the instruction of governments officials. In other cases, members of parliament would lobby to award contracts to their preferred contractor especially when the projects are in their constituencies.   Now a day most Politian’s have all turn themselves in to road contractors awarding contracts to their companies at inflated prices.  During election years’ contracts are awarded to exceed the budgetary allocation. Consultants are given limited time to prepare estimates and the contracts are awarded to at every high prices sometimes beyond the engineer’s estimate.

# 2.5.5 Connection between management and labour

Management of road project must always work hand in hand with the labour force. The welfare of the workers must be of concern to the management. The whole project team must work as one and in unity to reduce cost. When there is disunity in the team there is always power play which turns to in the cost of the project.

# 2.5.6 Contract Administration

Consultants and contractor must practise good contract administration to ensure contacts stay within time and budget. Proper tendering procedure must be adhered to at all times. Projects must not always be awarded to the lowest bidders who cannot do the work, at times the experience of the contractors and the consultants must be taken into consideration (Mansfield, et al 1994). Minimum qualification should be established for entrepreneurs who wish to enter into road construction, so that company owners would know that not every business man can be a contractor that they must acquire the requires skill to be one, this would help in better contract management. Contractors should be discouraged from submitting low bids so they can pay good wages which would boost productivity and reduce cost Frimpong et al (2003).

# 2.5.7 Lack of coordination between designers and contractors

Contractors must have in house designers who would be able to detect design deficiencies and prompt consultants before construction begins this would reduce waiting time to correct design defects and reduce cost.

# 2.5.8 Additional Work

Detailed description of technical and functional requirements need to be given at the briefing stage by clients and engineers before project starts. Proper inventory needs to be done to reduce the issuance of variations and reduce project cost (Mansfield et al, 1994).

# 2.5.9 Lack of Financial control on site

Project managers and site managers must ensure that financial resources are used effectively, spending on spare parts must be done wisely. Trusted personnel must be put in-charge of very sensitive areas to reduce waste in the system. Redundant personnel must be laid off to ensure scares resources are protected.

# 2.5.10Variations

In a study conducted by (Chileshe and Berko, 2010) variation was rank as one of the most important issues that affects the cost of road construction projects this is as a results of changes in scope and specification as outlined by (Oladapo, 2007). Variations increases project cost which as a result increases contractor’s expenses which results additional interest on bank loans. This affects the project cost.

# 2.5.11 Inflation

One of the most severe cause of project cost increase is inflation thus according to Agyakwa-Baah (2007; 2009), Frimpong et al (2003); Denini, (2009). Inflation is cause by currency instability which in turn affects project cost. Ghana experienced one of its worst fuel price hikes between 2001 and 2007 where prices of fuel roused as high as 280% this was as a result of currency instability. Project fluctuation could go as high as 300% between 2001 and 2007 all this as a result of fuel price increase. Frimpong et al. (2003) observed that inflation is attributed to high demand exceeding supply.

# 2.5.12 Schedule slippage

Schedule slippage and its associated extension of time are identical with cost escalation in road projects.  Most road projects are not able to meet the dead line due to non-payment of monthly invoice to contractors whiles variations and lack of proper project management can be attributed to that fact. (Ogunlana et al, 2002). Most construction companies in Ghana are in the business of making money and have relegated good contract administration to the background. This in turn affect project cost because projects delay beyond reasonable doubt.

# 2.5.13 Contract procedure

The contract document is there to guide all parties to the contract it contains the agreement, contract data and the conditions of contract, it also contains procedure and specification that directs all parties to the contract. Once the contract document is ambiguous and unclear it brings conflict and delays the project which affect cost.

# 2.5.14 Lack of project knowledge and Underestimating

For projects to be successful both the contractor and the consultants must have adequate knowledge about the project. Good project estimate means that there is enough knowledge about the project. This also means that there would be no omission and errors in the estimate. Project estimates which are not well done are normally connected with variation which add extra cost to the project.  Project manager’s and their team do not have enough time to do proper inventory and prepare well though through estimates before projects are awarded this may be due to political pressure. Projects of such nature are often characterise by variations which add extra cost to the project. Well prepare estimates for project may not have funds readily available. By the time funding is secured for the project the estimates may be out of date. Comprehensive estimates are every so often totally vague and in their place are project appraisal estimates which are not reliable used for project.  Alternatively, there the issue of fluctuation on project these are used to adjust the billed rates due to inflation. In order to cater for these fluctuations contingencies are use in the estimates which later they turn out not be accurate and unrealistic.

# 2.5.15 Transportation cost

Increase in fuel prices would increase cost of transportation. Equipment spare parts can increase transportation cost when their prices go up. Haulage cost, running cost and maintenance cost of all equipment would all increase as a result of this.

# 2.5.16 Time of contract period

Some projects take too long to complete especially project whose source of funding is not regular. Most raod projects in Ghana turns to have higher rates because the source of funding is GoG. This affects the cost of the project because if payments were regular contractors would complete the project within time. The longer the project takes to complete the more expensive the project is.

# 2.6 Minimizing Road Construction Cost

Minimizing road construction cost can be done in different ways as enumerated by Fisk (1997).

# 2.6.1 Avoid delay payment

Prompt payment of monthly invoice to contractor would reduce the cost of road construction considerably to both the contractor and the client. Prompt payment means that the client avoids the payment of interest on delay payment which in its self is an increase in cost to the client. Early payment means the extra cost incurred by the contractor due to high interest rates can be avoided. Most road contractors in Ghana use their payment certificate as collateral to secure loans from banks so in the invent of late payment the interest accrued on the principal is more. For projects to avoid increase in cost client must secure regular source of funding before contracts are awarded. Financial institutions must find ways to help contractors so they can have access to credit with minimum interest rate.

# 2.6.2 Estimating Methods

Variations can be reduced or avoided during project execution if proper estimating methods are followed. This can be done if proper inventory is done by consultants. Also project managers and their team should be given enough time to complete estimates before contracts are awarded. Design errors and omissions can equally be eliminated if proper inventory is done by consultants and project complexity are well understood. Feasibility studies should be done before and during contract stage so errors and omissions can be eliminated.

# 2.6.3 Contract Administration

Consultants and clients should try and always comply with contract procedures so that the project does not surfer. Contractors and their key staff should ensure they take up courses in project management so they can effectively manage their projects well.  To reduce pilfering and theft on site Contractors needs to review their wages structure to address the needs of its employees

# CHAPTER THREE

# 3.0 METHODOLOGY

# 3.1 Introduction

This chapter elaborates on, the research procedure presented the research strategy, population of the study, sampling techniques, research instrument, and administration of the research instrument and data analysis plan.

# 3.2 Research Strategy

Research strategy means knowing about the research questions and objectives. (Naoum 2002) There are types of research, these are the quantitative, qualitative and mix of both the quantitative and qualitative research (Baiden 2006). The research approach for this study is the quantitative approach whiles questionnaire were used in gathering data.

# 3.3 Research Population and Sampling used in the Study

According to Naoum (2002), population is the entirety or comprehensiveness of collection of individuals or objects. The population consisted of professionals in road construction industry. A sample is a subsection of the population in question and entails of a collection of data from the specific population Naoum (2002). Sampling is described as the collection of a percentage of the total number of units of interest for the eventual reason of being able to draw overall conclusions about the total number of units Naoum (2002).. The idea of sample arises from the inability of the researchers to test all the characters in a given population. The sample must be representative of the population from which it was drawn and it must have good size to warrant statistical analysis. The main function of the sample is to allow the researchers to conduct the study to individuals from the population so that the results of their study can be mused to derive conclusions that will apply to the entire population. It is much like a give-and-take process, the population gives the sample and it “takes” conclusions from the results obtained from the sample. The target of the study consists of professionals such as clients, consultants and contractors in road construction industry within Kumasi. A list all contractors in good standing and are actively working in the city was obtained from the Ministry of Roads and Highways.

# 3.4 Sampling design and procedures

A total of sixty respondents comprising of project managers, Quantity surveyors, Civil Engineers both from consultants and contractors were randomly selected using purposive random sampling technique as a type of non-probability sampling in order to emphasis on specific characteristics of a population that are of importance in the sample.

# 3.5 Means of Data collection

Two sets of information were recognised as being significant to the effective conduct of this research they are primary data and secondary data. The primary data includes field survey data through structured questionnaire. The secondary data collection entails study work study of relevant literature.

# 3.6 Management of the data collection

The questionnaires were hand distributed to the numerous target groups.

# 3.7 Data exploration

Data collected were coded. This was done to ensure uniformity in the dispensation of the data. The data was examined using Statistical Package for Social Science (SPSS 16) and Microsoft Excel. Relative importance index and mean score ranking were used in the analysis and the result represented in tabular form.

## CHAPTER FOUR

## 4.0 DATA PRESENTATION, ANALYSES AND DISCUSSION

The chapter presents the descriptive and inferential result of the data through tabular method. The chapter further analysed and discussed the result. The thematic areas of the chapter were the personal information of the respondent, the relative importance of the issues affecting the cost of road construction, the severity of the issues leading to high cost of road construction in Ghana, and the possible measures to minimizing road construction cost in Ghana.

## 4.1 Personal Information of Respondent

The personal data of the respondent is discussed in this part of the study. The section emphasized on the distribution of the respondent in terms of their profession, years in practice, highest level of education, their understanding of cost implication on road contracts and their view on the effect of cost implication on road construction in Ghana. The result is presented in Table 4.1.

Table 4.1: Socio-Demographic Data of Respondent

| Variables | Category | Frequency (N=60) | Percent (%) |
| --- | --- | --- | --- |
| Respondent’s Profession |  |  |  |
|  | Quantity Surveyor | 7 | 11.7 |
|  | Civil/Structural Engineer | 8 | 13.3 |
|  | Project/Construction Manager | 17 | 28.3 |
|  | Consultant | 22 | 36.7 |
|  | Others | 6 | 10.0 |
| Years in Practice |  |  |  |
|  | < 5 years | 2 | 3.3 |
|  | 5-10 years | 7 | 11.7 |
|  | 11-15 years | 36 | 60.0 |
|  | 16-20 years | 10 | 16.7 |
|  | > 20 years | 5 | 8.3 |
| Level of education |  |  |  |
|  | MSc | 18 | 30.0 |
|  | BSc | 40 | 66.7 |
|  | HND | 2 | 3.3 |
| Understanding of cost implication on road contracts |  |  |  |
|  | Moderate | 6 | 10.0 |
|  | Very well | 38 | 63.3 |
|  | Extremely well | 16 | 26.7 |
| Agree that cost implication affects road construction cost |  |  |  |
|  | Yes | 58 | 96.7 |
|  | No | 2 | 3.3 |

Source: Field Survey (2019)

Table 4.1 provides information on the distribution of the respondent that shows that 11.7% were quantity surveyors, 13.3% were Civil/Structural Engineers, 28.3% were Project/Construction Manager, 36.7% were consultants and 10.0% also belong to other professional categories. It is therefore evident that the contractors surveyed were about half of the total respondent. The majority (60.0%) of the respondent have been practicing for 11 to 15 years whereas 16.7% have also been practicing for 16 to 20 years. The respondent with less than 10 years of practice were 15% whereas those with more than 20 years of practice were 8.3%. It is evident that surveyed respondent have enormous experience in their field of practice and hence are in good position to provide valid and reliable information. Furthermore, the majority (66.7%) of the respondent have higher level of education of Bachelor of Science (BSc) in various fields of study whereas 30.0% also have higher educational qualification of Master of Science (MSc). The respondent with Higher National Diploma (HND) were only 3.3%.

Table 4.1 shows that the majority (63.3%) of the respondent very well understood cost implication on road contracts whereas 26.7% also very well understood the implication of cost implications. Thus, the knowledge of respondent on cost implications on road construction projects was extremely high. This is not surprising considering the high educational qualification of most of the respondent. Furthermore, the majority (96.7%) of the respondent agreed that cost implication affects road construction cost in Ghana.

## 4.2 Issues Affecting Cost of Road Construction in Ghana

This part of the study identifies the issues affecting cost of road construction in Ghana. This section seeks to examine the relative importance of the issues affecting the cost of road construction using the Relative Importance Index (RII). Sixteen issues or items were examined using a five-pointer likert scale of 1 (Not Important at all) to 5 (Very Important). The mean response value of respondent is also presented in this section. Thus, the mean responses and the RII values are presented in Table 4.2.

Table 4.2: Relative Important Issues Affecting Cost of Road Construction in Ghana

| Issues | Importance Scale |  |  |  |  | Weight | RII | Rank | Mean |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 5 |  |  |  |  |
| Delays in construction | 2 | 2 | 3 | 17 | 36 | 263 | 0.877 | 1st | 4.38 |
| Delays in Monthly Payments | 2 | 2 | 8 | 16 | 32 | 254 | 0.847 | 2nd | 4.23 |
| Bureaucracy in tendering methods | 3 | 2 | 7 | 18 | 30 | 250 | 0.833 | 3rd | 4.17 |
| Political interference | 3 | 3 | 9 | 18 | 27 | 243 | 0.810 | 4th | 4.05 |
| Poor Financial control on site | 4 | 3 | 8 | 19 | 26 | 240 | 0.800 | 5th | 4.00 |
| Price Fluctuations | 5 | 3 | 9 | 18 | 25 | 235 | 0.783 | 6th | 3.92 |
| Variations | 6 | 2 | 8 | 19 | 25 | 235 | 0.783 | 6th | 3.92 |
| Underestimating | 6 | 3 | 9 | 17 | 25 | 232 | 0.773 | 8th | 3.87 |
| Material cost | 7 | 4 | 7 | 17 | 25 | 229 | 0.763 | 9th | 3.82 |
| Fraudulent practises and kickbacks | 7 | 4 | 7 | 18 | 24 | 228 | 0.760 | 10th | 3.80 |
| High interest rate charged by banks | 8 | 4 | 7 | 16 | 25 | 226 | 0.753 | 11th | 3.77 |
| Disputes | 10 | 2 | 6 | 18 | 24 | 224 | 0.747 | 12th | 3.73 |
| Design errors & Omissions | 9 | 4 | 7 | 18 | 22 | 220 | 0.733 | 13th | 3.67 |
| Lack of project Knowledge | 13 | 2 | 3 | 18 | 24 | 218 | 0.727 | 14th | 3.63 |
| Technical Complexity/Project Size | 11 | 3 | 7 | 16 | 23 | 217 | 0.723 | 15th | 3.62 |
| Duration of Contract | 11 | 4 | 7 | 18 | 20 | 212 | 0.707 | 16th | 3.53 |

Scale: [1 – Not important at all, 2 – Not important, 3 – Neutral, 4 – Important, 5 -  Very important]

Source: Field Survey (2019)

Table 4.2 shows that respondent perceived delays in construction as an important issue affecting cost of road construction in Ghana (x=4.38). Thus, the delays in construction was deemed as the highest ranked issue affecting the cost of road construction in Ghana relative to the other issues as indicated by the highest RII value of 0.877. This finding is consistent with the study of Enshassi, Al-Najjar, and Kumaraswamy (2009) in the Gaza Strip that emphasized on construction delays due to strikes, border closures and material-related issues is an important issue affecting construction cost. The respondent also perceived delays in monthly payments as an important issue affecting cost of road construction in Ghana (x=4.23). Thus, delays in monthly payments was ranked the second highest issue affecting the cost of road construction in Ghana relative to the other issues as indicated by the second highest RII value of 0.847. This finding is consistent with the study of Chileshe and Berko (2010) in Ghana that also identified delays in monthly payments to contractors as an important issue affecting road construction cost in Ghana. The respondent also perceived bureaucracy in tendering methods as an important issue affecting cost of road construction in Ghana (x=4.17). Thus, bureaucracy in tendering methods was ranked the third highest issue affecting the cost of road construction in Ghana relative to the other issues as indicated by the third highest RII value of 0.833. This finding is consistent with several previous studies in the literature that emphasized on bureaucracy in tendering method as an important issue affecting road construction cost (e.g., Elinwa & Silas, 1993; Mansfield, Ugwu & Doran, 1994).

Table 4.2 shows that the respondent perceived political interference as an important issue affecting cost of road construction in Ghana (x=4.05). Thus, the level of political interference was deemed as the fourth highest ranked issue affecting the cost of road construction in Ghana relative to the other issues as indicated by the fourth highest RII value of 0.810. The government agencies, in most cases are tele guided by the political heavy weight to award contract to party stalwarts at very high prices to offset campaign expenses. This finding is consistent with several previous studies in the literature that emphasized on political interference as an important issue affecting road construction cost (e.g., Omole, 1986; Dada & Jagboro, 2007). The respondent also perceived poor financial control on site as an important issue affecting cost of road construction in Ghana (x=4.00). Thus, poor financial control on site was ranked the fifth highest issue affecting the cost of road construction in Ghana relative to the other issues as indicated by the fifth highest RII value of 0.800. The respondent also perceived price fluctuations as an important issue affecting cost of road construction in Ghana (x=3.92). Thus, price fluctuation was ranked the sixth highest issue affecting the cost of road construction in Ghana relative to the other issues as indicated by the sixth highest RII value of 0.783. This finding is consistent with several previous studies in the literature that emphasized on price fluctuations or inflation as an important issue affecting road construction cost (e.g., Kaming, et al. 1997; Frimpong et al., 2003; Omoreigie & Radford, 2006; Agyakwa-Baah, 2009; Denini, 2009; Chileshe & Berko, 2010).

Table 4.2 shows that the respondent perceived variations as an important issue affecting cost of road construction in Ghana (x=3.92). Thus, the level of variations was deemed as the sixth highest ranked issue affecting the cost of road construction in Ghana relative to the other issues as indicated by the sixth highest RII value of 0.783. This finding is consistent with several previous studies in the literature that emphasized on variations as an important issue affecting road construction cost (e.g., Mansfield et al., 1994; Arain & Pheng, 2005; Oladapo, 2007; Chileshe & Berko, 2010). The respondent also perceived underestimation as an important issue affecting cost of road construction in Ghana (x=3.87). Thus, budget underestimation was ranked the eighth highest issue affecting the cost of road construction in Ghana relative to the other issues as indicated by the eighth highest RII value of 0.773. This finding is consistent with several previous studies in the literature that emphasized on underestimation as an important issue affecting road construction cost (e.g., Kaming, et al. 1997). The respondent also perceived material cost as an important issue affecting cost of road construction in Ghana (x=3.82). Thus, material cost was ranked the ninth highest issue affecting the cost of road construction in Ghana relative to the other issues as indicated by the ninth highest RII value of 0.783. This finding is consistent with several previous studies in the literature that emphasized on material cost as an important issue affecting road construction cost (e.g., Elinwa & Silas, 1993; Frimpong, et al. 2003; Enshassi, et al. 2009; Ogunlana et al. 2002).

Table 4.2 shows that the respondent perceived fraudulent practises and kickbacks as an important issue affecting cost of road construction in Ghana (x=3.80). Thus, fraudulent practises and kickbacks was deemed as the tenth highest ranked issue affecting the cost of road construction in Ghana relative to the other issues as indicated by the tenth highest RII value of 0.760. This finding is consistent with several previous studies in the literature that emphasized on fraudulent practises and kickbacks as an important issue affecting road construction cost (e.g., Elinwa & Silas, 1993; Hussain, 1999; TELL, 2002). The respondent also perceived the high interest rate charged by banks as an important issue affecting cost of road construction in Ghana (x=3.77). Thus, high interest rate charged by banks was ranked the eleventh highest issue affecting the cost of road construction in Ghana relative to the other issues as indicated by the eleventh highest RII value of 0.753. This finding is consistent with several previous studies in the literature that emphasized on high interest rate charged by banks as an important issue affecting road construction cost (e.g., AL-Khaldi, 1990; TELL, 2002; Oladapo, 2007). The respondent also perceived disputes as an important issue affecting cost of road construction in Ghana (x=3.73). Thus, dispute was ranked the twelfth highest issue affecting the cost of road construction in Ghana relative to the other issues as indicated by the twelfth highest RII value of 0.747. This finding is consistent with several previous studies in the literature that emphasized on disputes as an important issue affecting road construction cost (e.g., Fisk, 1997; Aibinu & Jagboro, 2002; Chileshe & Berko, 2010).

Table 4.2 shows that the respondent perceived design errors and omissions as an important issue affecting cost of road construction in Ghana (x=3.67). Thus, design errors and omissions was deemed as the thirteenth highest ranked issue affecting the cost of road construction in Ghana relative to the other issues as indicated by the thirteenth highest RII value of 0.733. This finding is consistent with several previous studies in the literature that emphasized on design errors and omissions as an important issue affecting road construction cost (e.g., Carpenter, 1973; Chileshe & Berko, 2010). The respondent also perceived lack of project Knowledge as an important issue affecting cost of road construction in Ghana (x=3.63). Thus, lack of project Knowledge was ranked the fourteenth highest issue affecting the cost of road construction in Ghana relative to the other issues as indicated by the fourteenth highest RII value of 0.727. This finding is consistent with several previous studies in the literature that emphasized on lack of project Knowledge as an important issue affecting road construction cost (e.g., Kangari, 1989; Chileshe & Berko, 2010). The respondent also perceived technical complexity or project size as an important issue affecting cost of road construction in Ghana (x=3.62). Thus, technical complexity or project size was ranked the fifteenth highest issue affecting the cost of road construction in Ghana relative to the other issues as indicated by the fifteenth highest RII value of 0.723. This finding is consistent with several previous studies in the literature that emphasized on technical complexity or project size as an important issue affecting road construction cost (e.g., Fisk ,1997; Aibinu & Jagboro, 2002; Chileshe & Berko, 2010). The respondent also perceived duration of contract as an important issue affecting cost of road construction in Ghana (x=3.53). Thus, duration of contract was ranked the fifteenth and least issue affecting the cost of road construction in Ghana relative to the other issues as indicated by the fifteenth highest RII value of 0.707. This finding is consistent with several previous studies in the literature that emphasized on duration of contract as an important issue affecting road construction cost (e.g., Aibinu & Jagboro, 2002; Chileshe & Berko, 2010).

## 4.3 Severity of the Issues Leading to High Cost of Road Construction in Ghana

This part of the study examines the severity of the issues affecting cost of road construction in Ghana. This section seeks to examine the relative importance of the issues in terms of the severity of the influence of the issues on the cost of road construction using the Relative Importance Index (RII). Sixteen issues or items were examined using a five-pointer likert scale of 1 (Not Severe) to 5 (Extremely Severe). The mean response value of respondent is also presented in this section. Thus, the mean responses and the RII values are presented in Table 4.3.

Table 4.3: Severity of Issues Leading to High Cost of Road Construction

| Issues | Severity Scale |  |  |  |  | Weight | RII | Rank | Mean |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 5 |  |  |  |  |
| Bureaucracy in tendering methods | 0 | 0 | 3 | 18 | 39 | 276 | 0.920 | 1st | 4.60 |
| Delays in construction | 0 | 2 | 3 | 18 | 37 | 270 | 0.900 | 2nd | 4.50 |
| Political interference | 2 | 1 | 4 | 17 | 36 | 264 | 0.880 | 3rd | 4.40 |
| Price Fluctuations | 3 | 2 | 5 | 17 | 33 | 255 | 0.850 | 4th | 4.25 |
| Delays in Monthly Payments | 5 | 2 | 4 | 16 | 33 | 250 | 0.833 | 5th | 4.17 |
| Material cost | 7 | 2 | 2 | 16 | 33 | 246 | 0.820 | 6th | 4.10 |
| Fraudulent practises and kickbacks | 6 | 3 | 3 | 17 | 31 | 244 | 0.813 | 7th | 4.07 |
| Poor Financial control on site | 7 | 3 | 2 | 17 | 31 | 242 | 0.807 | 8th | 4.03 |
| Underestimating | 7 | 3 | 3 | 17 | 30 | 240 | 0.800 | 9th | 4.00 |
| Variations | 6 | 4 | 4 | 16 | 30 | 240 | 0.800 | 9th | 4.00 |
| High interest rate charged by banks | 6 | 4 | 6 | 14 | 30 | 238 | 0.793 | 11th | 3.97 |
| Technical Complexity/Project Size | 10 | 3 | 5 | 15 | 27 | 226 | 0.753 | 12th | 3.77 |
| Disputes | 9 | 4 | 6 | 14 | 27 | 226 | 0.753 | 12th | 3.77 |
| Design errors & Omissions | 10 | 3 | 5 | 16 | 26 | 225 | 0.750 | 14th | 3.75 |
| Duration of Contract | 12 | 2 | 4 | 16 | 26 | 222 | 0.740 | 15th | 3.70 |
| Lack of project Knowledge | 16 | 2 | 7 | 13 | 22 | 203 | 0.677 | 16th | 3.38 |

Scale: [1 – not severe, 2 – severe, 3 – neutral, 4 – very severe, 5 – extremely severe]

Source: Field Survey (2019)

Table 4.3 shows that the respondent perceived the bureaucracy in tendering methods as extremely severe issue leading to high cost of road construction in Ghana (x=4.60). In terms of severity, bureaucracy in tendering methods in Ghana is deemed as the highest ranked issue contributing to high cost of road construction in Ghana as indicated by the highest RII value of 0.920. This finding is consistent with several previous studies in the literature that emphasized on bureaucracy in tendering method as a severe issue affecting road construction cost (e.g., Elinwa & Silas, 1993; Mansfield, et al. 1994). The respondent also perceived the delays in construction as extremely severe issue resulting in high cost of road construction in Ghana (x=4.50). In terms of severity, delays in construction in Ghana is deemed as the second highest ranked issue contributing to high cost of road construction in Ghana as indicated by the second highest RII value of 0.900. This finding is consistent with the study of Enshassi, Al-Najjar, and Kumaraswamy (2009) in the Gaza Strip that emphasized on construction delays due to strikes, border closures and material-related issues is a severe issue affecting construction cost. The respondent also perceived political interference as very severe issue resulting in high cost of road construction in Ghana (x=4.40). In terms of severity, political interference in Ghana is deemed as the third highest ranked issue contributing to high cost of road construction in Ghana as indicated by the third highest RII value of 0.880. The government agencies, in most cases are tele guided by the political heavy weight to award contract to party stalwarts at very high prices to offset campaign expenses. This finding is consistent with several previous studies in the literature that emphasized on political interference as a severe issue affecting road construction cost (e.g., Omole, 1986; Dada & Jagboro, 2007).

Table 4.3 shows that the respondent perceived price fluctuations as very severe issue resulting in high cost of road construction in Ghana (x=4.25). In terms of severity, price fluctuations in Ghana is deemed as the fourth highest ranked issue contributing to high cost of road construction in Ghana as indicated by the fourth highest RII value of 0.850. This finding is consistent with several previous studies in the literature that emphasized on price fluctuations or inflation as a severe issue affecting road construction cost (e.g., Kaming, et al 1997; Frimpong et al., 2003; Omoreigie & Radford, 2005; Agyakwa-Baah, 2009; Denini, 2009; Chileshe & Berko, 2010). The respondent also perceived delays in monthly payments as very severe issue resulting in high cost of road construction in Ghana (x=4.17). In terms of severity, delays in monthly payments in Ghana is deemed as the fifth highest ranked issue contributing to high cost of road construction in Ghana as indicated by the fifth highest RII value of 0.833. This finding is consistent with the study of Chileshe and Berko (2010) in Ghana that also identified delays in monthly payments to contractors as a severe issue affecting road construction cost in Ghana. The respondent also perceived material cost as very severe issue resulting in high cost of road construction in Ghana (x=4.10). In terms of severity, material cost in Ghana is deemed as the sixth highest ranked issue contributing to high cost of road construction in Ghana as indicated by the sixth highest RII value of 0.820. This finding is consistent with several previous studies in the literature that emphasized on material cost as a severe issue affecting road construction cost (e.g., Elinwa & Silas, 1993; Frimpong, et al. 2003; Enshassi, Al-Najjar, & Kumaraswamy, 2009; Ogunlana et al., 2002).

Table 4.3 shows that the respondent perceived fraudulent practises and kickbacks as very severe issue resulting in high cost of road construction in Ghana (x=4.07). In terms of severity, fraudulent practises and kickbacks in Ghana is deemed as the seventh highest ranked issue contributing to high cost of road construction in Ghana as indicated by the seventh highest RII value of 0.813. The perpetrators of this act in the industry are predominantly found within the rank and file of contractors, consultants and public clients as evident from the report published by TELL (2002). These include inflated contracts, fraudulent over payment of contractors by some of the agency officials and undue receipts of interest on funds placed in banks by the agencies. This finding is consistent with several previous studies in the literature that emphasized on fraudulent practises and kickbacks as a severe issue affecting road construction cost (e.g., Elinwa & Silas, 1993; Hussein, 1999; TELL, 2002). The respondent also perceived poor financial control on site as very severe issue resulting in high cost of road construction in Ghana (x=4.03). In terms of severity, poor financial control on site in Ghana is deemed as the eighth highest ranked issue contributing to high cost of road construction in Ghana as indicated by the eighth highest RII value of 0.807. The respondent also perceived underestimation of budget as very severe issue resulting in high cost of road construction in Ghana (x=4.00). In terms of severity, underestimation of budget in Ghana is deemed as the ninth highest ranked issue contributing to high cost of road construction in Ghana as indicated by the ninth highest RII value of 0.800. This finding is consistent with several previous studies in the literature that emphasized on underestimation as a severe issue affecting road construction cost (e.g., Kaming, et al. 1997).

Table 4.3 shows that the respondent perceived variations as very severe issue resulting in high cost of road construction in Ghana (x=4.00). In terms of severity, variations in work orders in Ghana is deemed as the ninth highest ranked issue contributing to high cost of road construction in Ghana as indicated by the ninth RII value of 0.800. This finding is consistent with several previous studies in the literature that emphasized on variations as a severe issue affecting road construction cost (e.g., Mansfield et al., 1994; Arain & Pheng, 2005; Oladapo, 2007; Chileshe & Berko, 2010). The respondent also perceived the high interest rate charged by banks as very severe issue resulting in high cost of road construction in Ghana (x=3.97). In terms of severity, the high interest rate charged by banks in Ghana is deemed as the eleventh highest ranked issue contributing to high cost of road construction in Ghana as indicated by the eleventh highest RII value of 0.793. This finding is consistent with several previous studies in the literature that emphasized on high interest rate charged by banks as a severe issue affecting road construction cost (e.g., AL-Khaldi, 1990; TELL, 2002; Oladapo, 2007). The respondent also perceived technical complexity or project size as very severe issue resulting in high cost of road construction in Ghana (x=3.77). In terms of severity, technical complexity or project size in Ghana is deemed as the twelfth highest ranked issue contributing to high cost of road construction in Ghana as indicated by the twelfth highest RII value of 0.753. This finding is consistent with several previous studies in the literature that emphasized on technical complexity or project size as a severe issue affecting road construction cost (e.g., Fisk , 1997; Aibinu & Jagboro, 2002; Chileshe & Berko, 2010).

Table 4.3 shows that the respondent perceived disputes as very severe issue resulting in high cost of road construction in Ghana (x=3.77). In terms of severity, disputes is deemed as the twelfth highest ranked issue contributing to high cost of road construction in Ghana as indicated by the twelfth highest RII value of 0.753. This finding is consistent with several previous studies in the literature that emphasized on disputes as a severe issue affecting road construction cost (e.g., Fisk, 1997; Aibinu & Jagboro, 2002; Chileshe & Berko, 2010). The respondent also perceived design errors and omissions as very severe issue resulting in high cost of road construction in Ghana (x=3.75). In terms of severity, design errors and omissions is deemed as the fourteenth highest ranked issue contributing to high cost of road construction in Ghana as indicated by the fourteenth highest RII value of 0.750. This finding is consistent with several previous studies in the literature that emphasized on design errors and omissions as a severe issue affecting road construction cost (e.g., Carpenter, 1973; Chileshe & Berko, 2010). The respondent also perceived duration of contract as very severe issue resulting in high cost of road construction in Ghana (x=3.70). In terms of severity, duration of contract is deemed as the fifteenth highest ranked issue contributing to high cost of road construction in Ghana relative to the other issue as indicated by the fifteenth highest RII value of 0.740. This finding is consistent with several previous studies in the literature that emphasized on duration of contract as a severe issue affecting road construction cost (e.g., Aibinu & Jagboro, 2002; Chileshe & Berko, 2010). However, the respondent were uncertain or neutral about the severity of lack of project Knowledge as an issue resulting in high cost of road construction in Ghana (x=3.38). In terms of severity, lack of project Knowledge is deemed as the sixteenth and least ranked issue contributing to high cost of road construction in Ghana relative to the other issue as indicated by the sixteenth highest RII value of 0.677.

## 4.4 Measures to Reduce Road Construction Cost in Ghana

This part of the study examines the possible solutions to minimizing road construction cost issues in Ghana. The respondent examined the effectiveness of eleven measures in minimizing road construction cost using the scale of 1 (Ineffective) – 4 (Most Effective). The Relative Importance Index (RII) statistical method was employed to examine the relative effectiveness of the issues in minimizing road construction cost in Ghana. The mean responses of the various measures are also provided in this section. The RII and the mean response values are presented in Table 4.4.

Table 4.4: Measures to Minimizing Road Construction Cost

| Measures | Scale |  |  |  | Weight | RII | Rank | Mean |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 |  |  |  |  |
| Ensure that adequate and regular source of funding is secured for each project | 0 | 2 | 18 | 40 | 218 | 0.908 | 1st | 3.63 |
| Proper tendering procedure needs to be followed | 2 | 3 | 15 | 40 | 213 | 0.888 | 2nd | 3.55 |
| Good Project management practices needs to be encouraged among consultants and contactors | 2 | 2 | 18 | 38 | 212 | 0.883 | 3rd | 3.53 |
| Proper inventory and feasibility studies conducted to ensure accurate and realistic project cost estimates | 3 | 3 | 19 | 35 | 206 | 0.858 | 4th | 3.43 |
| Government agencies needs to operate professionally devoid of political pressure | 5 | 3 | 17 | 35 | 202 | 0.842 | 5th | 3.37 |
| Ensure efficient time management through proper resource planning, duration estimation and schedule development and control. | 8 | 6 | 16 | 30 | 188 | 0.783 | 6th | 3.13 |
| Selected contractor should only be not on the basis of price but also in financial capacity and experience to deliver. | 9 | 5 | 19 | 27 | 184 | 0.767 | 7th | 3.07 |
| Contractors must demonstrate adequate knowledge in road construction. | 10 | 6 | 19 | 25 | 179 | 0.746 | 8th | 2.98 |
| Experience and qualified personnel’s needs to be hired to ensure productivity. | 10 | 7 | 18 | 25 | 178 | 0.742 | 9th | 2.97 |
| Government policies should ensure that material prices are well regulated | 11 | 7 | 18 | 24 | 175 | 0.729 | 10th | 2.92 |
| Bureaucracies in governments departments needs to be eliminated | 15 | 12 | 17 | 16 | 154 | 0.642 | 11th | 2.57 |

Scale: [1 – Ineffective, 2 – Less effective, 3 – Effective, 4 – Most Effective]

Source: Field Survey (2019)

Table 4.4 shows that the respondent perceived that ensuring of adequate and regular source of funding is secured for each construction project as a most effective measure to minimizing road construction cost (x=3.63). The ensuring of adequate and regular source of funding is secured for each project with RII value of 0.908 is ranked the highest in terms of the most effective ways of minimizing road construction cost. Thus, the respondent perceived fund security as critical to road construction cost minimization. The respondent also perceived the following of proper tendering procedure as a critical measure of minimizing road construction cost in Ghana (x=3.55). Thus, the respondent perceived the following of proper tendering process as the second highest most effective measure of minimizing road construction cost as indicated by the RII value of 0.888. The respondent also perceived the encouragement of good project management practices among consultants and contractors as a critical measure of minimizing road construction cost in Ghana (x=3.53). Thus, the respondent perceived the encouragement of good project management practices among consultants and contractors as the third highest most effective measure of minimizing road construction cost as indicated by the RII value of 0.883.

Table 4.4 shows that the respondent perceived proper inventory and feasibility studies to ensure accurate and realistic project cost estimates as an effective measure to minimizing road construction cost (x=3.43). The conduct of proper inventory and feasibility studies to ensure accurate and realistic project cost estimates with RII value of 0.858 is ranked the fourth highest in terms of effective ways of minimizing road construction cost. The respondent also perceived the need for government agencies to operate professionally devoid of political pressure as a critical measure of minimizing road construction cost in Ghana (x=3.37). Thus, the respondent perceived the need for government agencies to operate professionally devoid of political pressure as the fifth highest effective measure of minimizing road construction cost as indicated by the RII value of 0.842. The respondent also perceived the ensuring of efficient time management through proper resource planning, duration estimation and schedule development and control as a critical measure of minimizing road construction cost in Ghana (x=3.13). Thus, the respondent perceived the ensuring of efficient time management through proper resource planning, duration estimation and schedule development and control as the sixth highest effective measure of minimizing road construction cost as indicated by the RII value of 0.783.

Table 4.4 shows that the respondent perceived the need for contractors to be selected not on the basis of only price but also in financial capacity and experience to deliver as an effective measure to minimizing road construction cost (x=3.07). The need for contractors to be selected not on the basis of only price but also in financial capacity and experience to deliver with RII value of 0.767 is ranked the seventh highest in terms of effective ways of minimizing road construction cost. The respondent also perceived the need for contractors to demonstrate adequate knowledge in road construction as a critical measure of minimizing road construction cost in Ghana (x=2.98). Thus, the respondent perceived the need for contractors to demonstrate adequate knowledge in road construction as the eighth highest effective measure of minimizing road construction cost as indicated by the RII value of 0.746. The respondent also perceived the need of hiring experienced and qualified personnel’s as a critical measure of minimizing road construction cost in Ghana (x=2.97). Thus, the respondent perceived the need of hiring experienced and qualified personnel’s as the ninth highest effective measure of minimizing road construction cost as indicated by the RII value of 0.742.

Table 4.4 shows that the respondent perceived the need for government policies to ensure that material prices are well regulated as an effective measure to minimizing road construction cost (x=2.92). The need for government policies to ensure that material prices are well regulated with RII value of 0.729 is ranked the tenth highest in terms of effective ways of minimizing road construction cost. The respondent also perceived the need to eliminate bureaucracies in governments departments as a critical measure of minimizing road construction cost in Ghana (x=2.57). Thus, the respondent perceived the need to eliminate bureaucracies in governments departments as the eleventh and the least effective ranked measure of minimizing road construction cost as indicated by the RII value of 0.642. The findings of this study are consistent with several previous studies in the existing literature that also emphasized on securing adequate and regular project funding, following proper tendering method, Good Project management practices, Proper inventory and feasibility studies and professional practices of government agencies devoid of political pressure as effective strategies of minimizing road construction cost (e.g., Fisk, 1997; Ashworth, 2000; Cooke & Williams, 2003).

## CHAPTER FIVE

## 5.0 SUMMARY OF FINDINGS, CONCLUSION AND RECOMMENDATIONS

The chapter provides a summary of the key findings of the study, concludes and suggest recommendations to reduce road construction cost in Ghana.

## 5.1 Summary of Findings

The key findings of the study are summarized in this part of the study on the basis of the designed research questions and research objectives. The findings are summarized in subsections below.

## 5.1.1 Main Issues Affecting Cost of Road Construction in Ghana

Cost implications or related issues are perceived to exhort enormous effect on the cost of road construction in Ghana. Relatively, the thirteen most important issues perceived to affect the cost of road construction in Ghana were delays in construction, delays in monthly payments, bureaucracy in tendering methods, political interference, poor financial control on site, price fluctuations, variations in work orders, budget underestimation, material cost, fraudulent practices and kickbacks, high interest rate charged by banks, disputes and design errors and omissions. The least three issues perceived to affect the cost of road construction in Ghana were lack of project knowledge, technical complexity or project size, and the duration of contract.

## 5.1.2 Severe Cause of the Issues Leading to High Cost of Road Construction in Ghana

Relatively, the most severe issues leading to high cost of road construction in Ghana were bureaucracy in tendering methods, delays in construction, political interference, price fluctuations, delays in monthly payments, material cost, fraudulent practices and kickbacks, poor financial control on site, budget underestimation, variations in work orders, high interest rate charged by banks, technical complexity or project size, disputes or conflicts and design errors and omissions in order of their severity. The least issue perceived to severely lead to high cost of road construction in Ghana was lack of project knowledge on the part of contractors and consultants.

## 5.1.3 Measures to Reduce Road Construction Cost in Ghana

The perceived relative most effective measures in minimizing road construction cost in Ghana were ensuring that adequate and regular source of funding is secured for each project; following proper tendering procedures; encouraging good project management practices among consultants and contactors; conduct proper inventory and feasibility studies to ensure accurate and realistic project cost estimates; government agencies needs to operate professionally devoid of political pressure; ensure efficient time management through proper resource planning, duration estimation and schedule development and control; select contractors based not on price but also in financial capacity and experience to deliver; adequate knowledge in road construction need to be demonstrated by contractors; hire the services of experience and qualified personnel’s to ensure productivity; government policies should ensure that material prices are well regulated and bureaucracies in governments departments needs to be eliminated in that order of their perceived effectiveness.

## 5.2 Conclusion

Road construction projects in Ghana are often either delayed or left uncompleted. This common phenomenon is partially attributed to the cost implications on road construction cost. The relatively important issues perceived to affect road construction cost in Ghana are delays in construction, delays in monthly payments, bureaucracy in tendering methods, political interference, poor financial control on site, price Fluctuations, variations work orders, budget underestimation and material cost. The relative perceived severe issues leading high cost in road construction projects are bureaucracy in tendering methods, delays in construction, political interference, price fluctuations, delays in monthly payments and material cost. These issues are evidently more related to delays, bureaucracies, political influence, macroeconomic issues and financial management practices. Thus, both internal and external issues contribute to high cost in road construction project in Ghana.

Consultants and contractors therefore could possibly reduce the cost in road construction through effective internal managerial measures in the form of securing adequate source of funds, good project management practices, proper inventor and feasibility studies, efficient time management through proper resource planning, duration estimation and schedule development and control, demonstrate adequate knowledge in road construction, and hire the services of experience and qualified personnel as these are perceived as effective measures in minimizing road construction cost. The managerial efforts of contractors and consultants in minimizing road construction cost can also be completed by government efforts in the form of proper tendering procedures, higher level of professional practices by government agencies, selection of contractors on the basis of not only price, but in financial capacity and experience to deliver, effective regulation of material prices through government policies, and employ more efficient technologies to expedite bureaucratic processes as these measures are perceived as effective in minimizing road construction cost in Ghana. In conclusion, cost minimization in road construction requires both effective internal measures and external measures. The collaboration of government, contractors and consultants is therefore required in minimizing road construction cost in Ghana.

## 5.3 Recommendations

This section of the study suggests various feasible and implementable managerial and policy measures to reduce road construction cost in Ghana.

## 5.3.1 Ensure Adequate and Regular Source of Funding

Securing regular source of funding for road construction projects was perceived as the most effective measure of minimizing road construction cost in Ghana. Thus, consultants need to submit complete project drawings and designs with minimal errors and omissions for funding. Contractors should ensure that estimated budget and funds from government meets the contract timeframe and quality of project. It is therefore essential that budget estimation inculcates price fluctuations. In cases of reliance on credit facilities, contractors should secure adequate funds from financial institutions in Ghana through the collateral support of the Government of Ghana.

## 5.3.2 Good Project Management Practices

There is also the need for contractors and consultants to ensure standard and best project management practices. Project managers of construction companies need to set a clear project scope. Thus, there is the need for stakeholder involvement in approving project scope with a detailed timeline, interim milestones, and the budget. There is also the need for effective plan for setbacks by ensuring extra time in the schedule, and/or extra money in the budget. The project manager should also ensure persistent collaboration and communication with all stakeholders of the road construction project through regular meetings to assess project progress.

A work execution platform can be created by the project manager to ensure easy flow of communication and information. By syncing comments, calendars, documents, and photos in one location, project managers can monitor updates, budgets, and scheduling changes as they occur. This form of robust platform also allows project managers to relay the occurring changes to other managers and accounting offices in real time through instant alerts, automated actions, and easy-to-visualize dashboards, providing a nearly email-free and paperless method of project management.

## 5.3.3 Proper Inventory and Feasibility Studies

The study perceived proper inventory and feasibility studies as effective measure of minimizing road construction cost in Ghana. Thus, the financial officers are required to ensure more proper and effective inventory management practices and feasibility studies in order to reduce carrying cost and shortage cost through appropriate and effective inventory balance. This can be achieved through the altering of inventory levels frequently.

## 5.3.4 Employ Experience and Qualified Personnel

The study revealed the need for the employment of qualified and experience personnel as an effective measure of minimizing road construction cost in Ghana. Thus, this study recommends the employment of experience and highly qualified personnel by contractors and consultants to effectively manage road construction projects in Ghana.

## 5.3.5 Proper Tendering Procedure

The study revealed the following of proper tendering process as very effective measure in minimizing road construction cost in Ghana. Thus, this study recommends proper bidding and tendering process to ensure the selection of the most economically efficient bidder. Bidding and tendering process should be devoid of biases and governmental influences. It is therefore essential for government agencies to be professional in their practices by ensuring that contractors are selected only on the basis of price but in financial capacity and experience to deliver.

## 5.4 Suggested Areas for Further Studies

Methodologically, this study employed RII in identifying the relative important issues affecting cost of road construction in Ghana. Further studies can therefore employ multiple regression by effectively defining a dependent variable in the form of road construction cost. The emphasis of this study was on the issues affecting road construction cost in Ghana. Further studies can also examine best internal cost minimization practices of contractors and consultants in Ghana.

# REFERENCES

Agbodjah, S.L. (2008) PhD Thesis submitted to the Department of Building Technology, Kwame Nkrumah University of science and Technology, Kumasi, Ghana

Agyakwa-Baah, A. (2007), “Stakeholders’ perception of the causes of delay on construction projects”, unpublished B.Sc. Project Dissertation, Kwame Nkrumah    Universities of Science and Technology, Kumasi, Ghana.

Agyakwa-Baah, A. (2009), “A Study into Risk Assessment and    Management Practices within Ghanaian Medium and Large Construction    Organisations”, unpublished M.Sc. Dissertation, Built Environment    Division, Sheffield Hallam University, Sheffield, U.K.

Aibinu, A.A. and Jagboro, G.O. (2002) The Effects of Construction Delays on Projects delivery in the Nigerian Construction Industry. International Journal of Project Management 20, 593 – 599

Asamoah, J. (2002) Satisfying the Energy Hunger in West Africa: A Progress on West Africa Gas Pipeline. African energy, Brooke Patrick Publications, Johannesburg, http//www.africanenergy.co.za

Ankomah, B., Boakye, N. A., & Fugar, F. (2010). Safety on construction sites: The role of the employer and employee. Proceedings of the West Africa Built Environment Research (WABER) Conference (pp. 477 - 498). Accra.

Aje, O.I., Odusami, K.T. and Ogunsemi, D.R. (2009) “The impact of     Contractors management capability on cost and time performance of     construction projects in Nigeria”, Journal of Financial Management of   Property and Construction, Vol 14, Issue No. 1, pp. 171 – 187

AK, Eyiah, and P. Cook, (2003) “Financing small and medium scale contractors in developing countries: A Ghana case study” Construction management and economics Vol 21 (4), pp. 357-367

Arain, F.M. and Pheng, L.S. (2005) “The potential effects of variation orders on   Institutional Building Projects, Journal of Facilities, Vol 23, No. 11/12, pp. 496-    510.

Ashworth, A. (2000), ‘Civil Engineering Contractual Procedures’, New York: John Wiley & Sons

Baiden, B.K., (2006), “Framework for the integration of the project delivery team”, unpublished Doctoral Thesis submitted in partial fulfilment of the requirement for the award of Doctor of Philosophy at Loughborough University, Loughborough United Kingdom

Carpenter, J.L. (1973), “An Analysis of a Guaranteed Achievement Program    to achieve Specific Educational objectives, or Performance Contracting, Chicago Style”. Paper presented at American Educational Research    Association Meeting, 25 February – 1st March 1973, New Orleans, Louisiana

Cooke, B. and Williams P. (2003) Construction Planning, Programming and Control, 2nd edition. Palgrave, New York.

Chileshe, N., and Berko, P. D., 2010, Causes of project cost overruns within the Ghanaian road construction sector, Proc., 5th Built Environment Conference, Durban, South Africa, 18-20

Dada, J.O. and Jagboro, G.O. (2007) “An evaluation of the impact of risk on     project cost overrun in the Nigerian construction industry”, Journal of Financial Management of Property and Construction, Vol. 12, No. 1, pp.     37- 44

Denini, F. (2009) “Delays on large construction projects in Libya”, In: Abu    Bakar (ed.) Proceedings of the 3rd International Conference on Built Environment in Development Countries (Sustainable Built Environment:     Tomorrow’s Agenda Today), 2 – 3rd December 2009, Penang, West     Malaysia, Vol. 2, pp. 819-835.

Elinwa, U., and Buba, S., (1993): Construction Cost Factors in Nigeria. Journal of Construction Engineering and Management. 119, (4) 698-714.

Enshassi, A., Al-Najjar, J. and Kumaraswamy, M.  (2009) “Delays and cost     overruns in the construction projects in the Gaza strip”, Journal of Financial Management of Property and Construction, Vol. 14, No. 2, pp.126-151.

Eyo - Ita – Eyo, (2001) Nigerian Cement Industry is Pathetic. THISDAY People, Leaders and company limited. http:www.thisdayonline.com

Fisk, E. R., 1997, Construction project administration, 5th Edition, Prentice Hall, New Jersey

Frimpong, Y., Oluwoye, J. and Crawford, L. (2003) “Causes of delay and Cost overruns in construction of groundwater projects in developing    countries; Ghana as a case study”, International Journal of Project Management, Vol 21, pp. 321 –  326

Gidisu, J. (2009) “Introductory Remarks by Hon. Joe Gidisu, Minister of     Roads and Highways”, Transport and Sector Conference on Ghana’s Oil   and Gas Industry’15 – 16th July 2009, AICC, Accra, Ghana.

Hussain A.A. (1999) Construction and the National Economy. The Nigerian Quantity Surveyor. 20 – 21

Kaming, P.F., Olomolaiye, P.O., Holt, G.D., Harris, F. (1997), "Factors     influencing construction time and cost overruns on high-rise projects in     Indonesia”, Construction Management and Economics, Vol. 15 pp.83-94.

Kangari K. (1989): Business failure in Industry. Journal of Construction Engineering and Management. 115 (2) 173 – 187

Manelele, I. and Muya, M. (2008) “Risk Identification on community-based     construction projects in Zambia”, Journal of Engineering, Design and Technology, Vol. 6, No. 2, pp. 145 – 161.

Mansfield, N.R., Ogwu, O.O. and Doran, T. (1994) “Causes of delay and    cost     overrun in Nigerian construction projects” International Journal of Project Management, Vol 12, No. 4, pp. 254-260.

Manavazhi, M.R. and Adhikari D.K. (2002) Material and equipment procurement                                         delays in Highway projects in Nepal. International Journal of Project Management 20, 627 – 632.

Mbachu J.I.C. and R.N. Nkado. (2004) Reducing Building Construction Costs; the Views of Consultants and Contractors. COBRA.

Naoum, S.G., (2002), “Dissertation research and writing for construction students”, Oxford: Butterworth-Heinemann

Ofori, G. (2012). Developing the Construction Industry in Ghana: the case for a central agency. Singapore City.

Odeyinka, H.A. and Yusuf, A. (1997), “The causes and effects of    construction delays on completion cost of housing project in Nigeria”, Financial Management Property Construction, Vol. 2, pp. 31-44.

Ogunlana, S., Krit, P. and Vithool, J. (1996) Construction delays in a fast growing economy; comparing Thailand with other economies. International Journal of Project Management 14 (1) 37 – 45

Ogunlana, S.O., Siddiqui, Z., Yisa, S. and Olomolaiye, P. (2002), “Factors and procedures used in matching project managers to construction    projects in Bangkok”, International Journal of Project Management, Vol.     20, No. 5, pp. 385- 400.

Okumbe, J.O. and Vesper, J.J.P. (2008), “Construction Industry     Perspective on Causes and Effects of Delays in South Africa”, In Proceedings of the Construction and Building Research Conference (COBRA), 4 – 5 September 2008, Dublin Institute of Technology.

Oladapo, A.A. (2007), “A quantitative assessment of the cost and time     impact of variation orders on construction projects”, Journal of Engineering Design and Technology, Vol. 5, No. 1, pp. 35 – 48.

Omole A.O. (1986): Causes of the High Cost of Building and Civil Engineering Construction in Nigeria. The Nigerian Quantity Surveyor.  (6) 1-2

Omoregie A. and Radford D. (2006) Infrastructure Delay and Cost Escalations: Causes and Effects in Nigeria, School of Architecture, De Montford University, Leicester, LE 1 9BH England.

TELL (2002) The Rot that was PTF. Nigeria’s independent weekly magazine number 43, Special Report. TELL communications limited.

Vulink, M. (2004). Technology Transfer in the Construction Industry of Ghana. Department of Technology and innovation Policies, Technische Universiteit Eindhoven, Eindhoven.

ZS Al-khaldi (1990), “ Factors Affecting The Accuracy of construction costs Estimating in Saudi Arabia” unpublished M.Sc. Project Dissertation, King Fahd University of Petroleum & Minerals Dhahran, Saudi Arabia

## APPENDIX

KWAME NKRUMAH UNIVERSITY OF SCIENCE AND TECHNOLOGY

MSC PROJECT MANAGEMENT

DEPARTMENT OF CONSTRUCTION TECHNOLOGY AND MANAGEMENT

TOPIC:  FACTORS AFFECTING COST OF ROAD CONSTRUCTION IN GHANA

RESEARCH QUESTIONNAIRE SURVEY

I am BOATENG Enoch, pursuing an MSc Project Management at the Kwame Nkrumah University of Science and Technology (KNUST) This research questionnaire has been designed to solicit your view and information regarding the topic: Factors Affecting Cost of Road Construction in Ghana.

The study is aimed at the factors affecting cost of road construction in Ghana and propose solutions to how road construction cost can be reduced.

The objectives of the research are as follows

- To identify the main factors affecting cost of road construction in Ghana.

- To identify the most severe cause of the factors leading to high cost of road construction in Ghana.

- To propose solutions on how to reduce road construction cost in Ghana.

The questionnaire is in two sections:

- Section A – Respondent Details

- Section B – Main factors, severity ranking, and propose solution

This is purely for academic purposes and all information provided will be treated with strict confidentiality.

SECTION A: RESPONDENT DETAILS

Please read through the following questions, mark [√] and or provide answers where appropriate and applicable

- Please indicate the contracting party/firm you belong to.

- [   ]  Quantity Surveyor                                         b.  [   ]  Civil/Structural Engineer

- [   ]  Project/Construction Manager                       d.  [   ]  Consultant

e.    [   ]  Others (Please specify)………………………………

- How long have you been practicing?

- [   ]  Less than 5 years                                            b.  [   ]  5 – 10 years

c.    [   ]  11 – 15 years                                                  d.  [   ]  16 – 20 years

e.    [   ]  Above 20 years

- Please indicate your level of education.

a.  PhD [    ] 	                            b. MSc [   ]	        c.  BSc [    ]

d. HND [    ]	                            e. CTC [    ]

4.  How well do you understand cost implication on road contracts.

a. Not at all [    ] 	  b. Not very well [   ]	        c. Moderate  [    ]

d. very well [    ]           e. Extremely well  [    ]

5.  Do you agree that cost implication affects road construction cost?

a. [   ]  Yes                        b.[   ]  No

c. [   ]  others (Please specify)…………………………………………………..

SECTION B

Part A

In the table below are factors that affect the cost of road construction projects. Please

indicate the level of importance these factors are on a scale of 1 - 5: please tick (√) in space provided

1 – Not important at all

2 – Not important

3 – Neutral

4 – Important

5 -  Very important

| Item | Factors Affecting Road Construction Cost | Scale |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 1 | 2 | 3 | 4 | 5 |
| 1 | Political interference |  |  |  |  |  |
| 2 | Delays in Monthly Payments |  |  |  |  |  |
| 3 | Price Fluctuations |  |  |  |  |  |
| 4 | Design errors & Omissions |  |  |  |  |  |
| 5 | Variations |  |  |  |  |  |
| 6 | Technical Complexity/Project Size |  |  |  |  |  |
| 7 | Disputes |  |  |  |  |  |
| 8 | Delays in construction |  |  |  |  |  |
| 9 | Lack of project Knowledge |  |  |  |  |  |
| 10 | Fraudulent practises and kickbacks |  |  |  |  |  |
| 11 | Duration of Contract |  |  |  |  |  |
| 12 | Poor Financial control on site |  |  |  |  |  |
| 13 | Underestimating |  |  |  |  |  |
| 14 | Bureaucracy in tendering methods | ` |  |  |  |  |
| 15 | High interest rate charged by banks |  |  |  |  |  |
| 16 | Material cost |  |  |  |  |  |

Part B

In the table below are factors that affect the cost of road construction projects. Please

indicate the level of severity these factors are on a scale of 1 - 5: please tick (√) in the space provided

1 – not severe

2 – severe

3 – neutral

4 – very severe

5 – extremely severe

| Item | Factors Affecting Road Construction Cost | Severity |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 1 | 2 | 3 | 4 | 5 |
| 1 | Political interference |  |  |  |  |  |
| 2 | Delays in Monthly Payments |  |  |  |  |  |
| 3 | Price Fluctuations |  |  |  |  |  |
| 4 | Design errors & Omissions |  |  |  |  |  |
| 5 | Variations |  |  |  |  |  |
| 6 | Technical Complexity/Project Size |  |  |  |  |  |
| 7 | Disputes |  |  |  |  |  |
| 8 | Delays in construction |  |  |  |  |  |
| 9 | Lack of project Knowledge |  |  |  |  |  |
| 10 | Fraudulent practises and kickbacks |  |  |  |  |  |
| 11 | Duration of Contract |  |  |  |  |  |
| 12 | Poor Financial control on site |  |  |  |  |  |
| 13 | Underestimating |  |  |  |  |  |
| 14 | Bureaucracy in tendering methods | ` |  |  |  |  |
| 15 | High interest rate charged by banks |  |  |  |  |  |
| 16 | Material cost |  |  |  |  |  |

Part C:

In the table below are possible solution on how to reduce road construction cost factors. Base on your experience, please indicate how effective the following solutions are using the scale of 1- 4below. Please tick (√) in the space provided.

1 – Ineffective

2 – Less effective

3 – Effective

4 – Most Effective

| Item | Minimizing Road Construction Cost | Scale |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | 1 | 2 | 3 | 4 |
| 1 | Ensure that adequate and regular source of funding is secured for each project |  |  |  |  |
| 2 | Proper tendering procedure needs to be followed. |  |  |  |  |
| 3 | Bureaucracies in governments departments needs to be eliminated. |  |  |  |  |
| 4 | Proper inventory and feasibility studies conducted to ensure accurate and realistic project cost estimates |  |  |  |  |
| 5 | Good Project management practices needs to be encourage among consultants and contactors. |  |  |  |  |
| 6 | Government agencies needs to operate professionally devoid of political pressure |  |  |  |  |
| 7 | Contractors must demonstrate adequate knowledge in road construction. |  |  |  |  |
| 8 | Experience and qualified personnel’s needs to be hired to ensure productivity. |  |  |  |  |
| 9 | Ensure efficient time management through proper resource planning, duration estimation and schedule development and control. |  |  |  |  |
| 10 | Government policies should ensure that material prices are well regulated. |  |  |  |  |
| 11 | Selected contractor should only be on the basis of price but in financial capacity and experience to deliver. |  |  |  |  |