INVESTIGATING THE PROJECT MANAGEMENT PLANNING PRACTICES USED BY CHURCHES: THE CASE OF CONSTRUCTION OF CHAPELS IN THE OBUASI METROPOLIS.

By

Ayifli Bright Frank

(Bsc. Tourism)

A thesis submitted to the Department of Construction Technology and Management, Kwame Nkrumah University of Science and Technology Kumasi, in partial fulfilment of the requirement for the award degree of

MASTER OF SCIENCE IN PROJECT MANAGEMENT

November 2019

# DECLARATION

I hereby declare that this submission is my own work and that, to the best of my knowledge and belief, it contains no material previously published or written by another person nor material which to a substantial extent has been accepted for the award of any other degree or diploma at Kwame Nkrumah University of Science and Technology, Kumasi or any other educational institution, except where due acknowledgement is made in the thesis.

Bright Frank Ayifli (PG 5043018)	…..….……………….	…..……………….

Signature             		Date

Certified by:
Rev. Prof`. Frank Fugar		…..….……………….	…..……………….

Supervisor                          			Signature             		Date

Certified by:
Prof. Bernard Baiden                  	…..….……………….	…..……………….

Head of Department       			Signature        			Date

# ABSTRACT

The construction of the Chapels requires effective project planning practices to improve on the performance of projects executed by churches. The popularity and wide usage of project planning practices has been obvious in numerous sectors. However, very little is heard about project planning practices in churches. Hence the study aimed at assessing the project management planning practices used in Congregational Chapel construction projects. With this aim, three objectives were set which were to identify the project planning practices used by churches in the construction of chapel projects, to identify the project planning Practices currently adopted by Churches in the construction of Chapels and to identify the challenges confronting project planning practices in the construction of Chapels. The study adopted the quantitative research strategy in which structured questionnaire was developed and distributed to charismatic churches registered in the Obuasi Municipality. As at the time of study, there were 227 Charismatic registered churches in the Obuasi Municipality according to Christian Council of Churches, Obuasi Metropolis. A sample of seventy (70) was attained using the Yamane formula hence, seventy (70) questionnaires were distributed whiles fifty (50) were retrieved for the analysis. The data were analyzed using frequencies, percentages and mean score ranking. From the analysis, it was found that despite the fact that churches in the Obuasi municipality followed some planning practices, there were a couple of them due to challenges and difficulties they were not able to adopt such planning practices in the course of making plans for construction of their chapels. The study concluded that, some of the churches lack knowledge in project planning practices as well as the entire project management practices. The study recommended that churches should strive to employ professional project managers to be on their boards since there is the need to open branches of the churches in several towns in the region and across the country.

Keywords: Project management, Project planning

# TABLE OF CONTENTS

DECLARATION	ii

ABSTRACT	iii

TABLE OF CONTENTS	iv

LIST OF TABLES	vii

LIST OF FIGURES	vii

ACKNOWLEDGEMENTS	viii

DEDICATION	x

CHAPTER ONE	1

INTRODUCTION	1

1.1 BACKGROUND OF THE STUDY	1

1.2 PROBLEM STATEMENT	2

1.3 RESEARCH QUESTIONS	3

1.4 THE AIM	3

1.5 OBJECTIVES OF STUDY	3

1.6 RESEARCH METHOD	3

1.7 SCOPE OF THE STUDY	4

1.8 SIGNIFICANCE OF THE STUDY	4

1.9 ORGANIZATION OF THESIS	5

CHAPTER TWO	6

LITERATURE REVIEW	6

2.1 INTRODUCTION	6

2.2 THEORETICAL REVIEW	6

2.2.1 The Life Cycle Theory	6

2.2.2 Application of the Life Cycle Theory to Project Planning Practices	7

2.3 CONCEPTUAL REVIEW	8

2.3.1 Definitions of Project	8

2.3.2 Project Management	8

2.3.3 Project Management Practices in Ghana	10

2.3.4 Project Management Planning Stages	11

2.4 CHALLENGES AFFECTING CONSTRUCTION PROJECT MANAGEMENT PRACTICES	14

2.5 CHALLENGES CONFRONTING PLANNING PROCEDURES IN THE CONSTRUCTION OF CHAPELS	16

2.5.1 Inadequate Scope Definition	16

2.5.2 Execution of the Project	17

2.5.3 Slow Starting Pace of the Projects	17

2.5.4 Lack of Planning Skills	18

2.5.5 Inability to Get Team Members on Board	18

2.5.6 Unclear Responsibility	19

2.5.7 Unforeseen Circumstances	20

2.5.8 Passive Attitudes of Project Managers	20

2.6 CONCLUSION	20

CHAPTER THREE	22

RESEARCH METHODOLOGY	22

3.1 INTRODUCTION	22

3.2 RESEARCH DESIGN	22

3.3 RESEARCH STRATEGY	23

3.4 POPULATION OF THE STUDY	23

3.5 SAMPLING SIZE AND SAMPLING TECHNIQUE	24

3.6 DATA COLLECTION METHOD	24

3.7 DATA ANALYSIS TECHNIQUE	25

3.8 ETHICAL CONSIDERATIONS	25

CHAPTER FOUR	26

ANALYSIS AND DISCUSSION OF RESULTS	26

4.1 INTRODUCTION	26

4.2 DATA PRESENTATION	26

4.3 DEMOGRAPHIC INFORMATION OF RESPONDENTS	26

4.3.1 Age Distribution of Respondents	27

4.3.2 Level of Education of Respondents	28

4.3.3 Marital Status of Respondents	28

4.3.4 Positions of Respondents in the Church	29

4.3.5 Respondents Knowledge in Project Management Practices	29

4.4 PROJECT PLANNING PRACTICES NEEDED TO BE FOLLOWED	30

4.5 PROJECT PLANNING PRACTICES ADOPTED BY THE CHURCHES	36

4.6 CHALLENGES CONFRONTING PLANNING PRACTICES IN THE CONSTRUCTION OF CHAPELS	42

4.7 DISCUSSION OF RESULTS	44

4.7.1 Project Planning Practices Needed to be Followed	44

4.7.2 Project Planning Practices Adopted by the Churches	45

4.7.3 Challenges Confronting Planning Practices in the Construction Of Chapels	46

CHAPTER FIVE	48

CONCLUSIONS AND RECOMMENDATIONS	48

5.1 INTRODUCTION	48

5.2 SUMMARY OF FINDINGS	48

5.3 RECOMMENDATIONS	50

5.3.1 Engagement of Professional Project Manager	50

5.3.2 Education of Church Board Members	50

5.4 RECOMMENDATIONS FOR FURTHER STUDY	50

5.5 CONCLUSION	50

REFERENCES	52

APPENDIX I	63

# LIST OF TABLES

Table 4.1: Age Distribution of Respondents	27

Table 4.2: Educational Level of Respondents	28

Table 4.3: Marital Status of Respondents	28

Table 4.4: Positions of Respondents in the Church	29

Table 4.5: Respondents Knowledge in Project Management Practices	30

Table 4.6: Identifies specific work to be performed and the goals that define the project	31

Table 4.7: Provision of Documented Estimates Regarding Schedule, Resources and Cost for Planning, Tracking, and Controlling the Project	32

Table 4.8: Obtaining Church Board’s Commitments That Are Planned, Documented, And Agreed Upon	33

Table 4.9: Continuing the Development and Documentation of Project Alternatives, Assumptions, and Constraints	34

Table 4.10: Establishing A Baseline of the Plan from Which the Project Will be Managed	35

Table 4.11: Challenges Confronting Planning Practices in the Construction of Chapels	44

# LIST OF FIGURES

Figure 4.1: Identifies specific work to be performed and the goals that define the project	31

Figure 4.2: Provision of Documented Estimates Regarding Schedule, Resources and Cost for Planning, Tracking, and Controlling the Project	32

Figure 4.3: Obtaining Church Board’s Commitments That Are Planned, Documented, and Agreed Upon	33

Figure 4.4: Continuing the Development and Documentation of Project Alternatives, Assumptions, and Constraints	34

Figure 4.5: Establishing A Baseline of the Plan from Which the Project Will be Managed	35

Figure 4.6: Development of Project Goals	37

Figure 4.7: Creation of list of things the project needs to deliver to meet those goals	38

Figure 4.8: Identify, by name, the individuals and organisations with a leading role in the project. For each, describe their roles and responsibilities on the project	39

Figure 4.9: Specification of the Number and Type of People Needed to Carry Out the Project	40

Figure 4.10: Creation of Document Showing Who is to be Kept Informed About the Project and How They Will Receive the Information	41

Figure 4.11: Identification of Risks to the Church’s Project as Possible and be Prepared if Something Bad Happens	42

# ACKNOWLEDGEMENTS

First and foremost, I want to thank God for life, strength and wisdom to put this thesis together. I am eternally grateful to you LORD. Secondly, I want to express my appreciation to my family for the support and peace of mind given me in the course of this work.

Special thanks to Rev. Prof. Frank Fugar. You are not only a Lecturer but a true loving Father, Mentor and a gift to Humanity. I am indeed grateful for everything.

Finally, to all loved ones who supported me in diverse ways, I say God richly bless you

# DEDICATION

I wholeheartedly dedicate this piece of work to God, the source of all my knowledge, wisdom and understanding. Secondly, I wish to dedicate same to my lovely wife, Mrs. Esther Salasie Ayifli-Mensah and my blessed Children. Finally, I dedicate it to all my Spiritual children and church members who desire to adopt effective project management planning procedures in construction projects.

# CHAPTER ONE

# INTRODUCTION

## 1.1 BACKGROUND OF THE STUDY

Project management has evolved over time to a sophisticated and complex process, becoming the principal channel of dealing with change in modern organizations (Thomas & Mengel, 2008). As projects developed and knowledge gained, standards have continuously improved. Project Management is the application of knowledge, skills, tools and techniques to project activities to meet project requirements (PMBOK Sixth Edition, 10 cited in Kerzner, 2017). A project is temporary endeavor undertaken to create a unique product or service (PMBOK Sixth Edition, 4 cited in Kerzner, 2017). One major element in project management practices is the planning stage. A number of researches have shown that, the improvement of construction planning effectiveness can consequently affect construction project performance and also create the effective usage of resources (Faniran, et al., 2000 cited in Escamilla, 2011).

The popularity and wide usage of project planning practices has been obvious in mining sectors, business fields, NGO’s, Government institutions etc., whilst very little is heard about project planning practices in churches (Freeman, 2010). This creates the need to investigate project planning practices used in churches with regards to construction of chapels in the Obuasi Municipality. Many churches are limited in their ministry by not having an adequate meeting place; for others, the cost of renting halls of worship prevents them (Palmer-Atkins, 2018). Many others often purchase their own land and begin construction of their chapels. A chapel is a Christian place of prayer and worship that is usually relatively small, and is distinguished from a church. With the construction of the Chapels, it is important to adopt effective project planning practices to improve on the performance of projects executed by churches.

Hence, this research seeks to assess the project management planning practices used in Congregational Chapel construction projects.

## 1.2 PROBLEM STATEMENT

Churches in most cases are constrained by time and cost in executing projects compelling them to ignore the project planning practices (Amponsah, 2010). Also, there is not much literature on whether churches follow the laid down project management practices in the construction of chapels in order to guide the implementation of future projects especially, the planning phase of a project (Prabhakar, ‎2008). According to Alias et al. (2014), successful construction projects essentially depends on effective practices of project management concerning execution, planning and cost, time and quality accomplishments. Basically, there are weaknesses in the construction of churches in terms of timetable deviations and cost overruns (Altoryman, 2014; González et al., 2014; Hussein and Klakegg, 2014; Kumaraswamy and Chan, 1998). Such inadequacies result from inappropriate risks identification in planning of projects in the initial phase of a project (Hussein and Klakegg, 2014). This shows the significance of effective scheduling and planning in church construction projects.

The significance of project planning in construction has therefore been recognized, but it has not been explicitly addressed by researchers. Winch and Kelsey (2005) acknowledged that construction planning is more likely to be used as a tool for making rapid decisions based on observed views rather than detailed analyses of real requirements and the concerns of project stakeholders. It is in view of this that this study seeks to assess the project management planning practices used in Congregational Chapel construction projects.

## 1.3 RESEARCH QUESTIONS

- How are planning Practices followed by Churches in the construction of Congregational Chapel projects?

- What are the planning Practices adopted by Churches in the construction of Chapels?

- What are the challenges confronting planning Practices in the construction of Chapels?

## 1.4 THE AIM

The aim of the study is to assess the project management planning practices used in Congregational Chapel construction projects.

## 1.5 OBJECTIVES OF STUDY

- To identify the project planning practices used by churches in the construction of chapel projects;

- To identify the project planning Practices currently adopted by Churches in the construction of Chapels; and

- To identify the challenges confronting project planning practices in the construction of Chapels.

## 1.6 RESEARCH METHOD

The study was guided by quantitative research strategies. Churches in the Obuasi Municipality were sampled for the study. Structured questionnaires were used in data collection. Descriptive statistics were used to analyze the data of which recommendations and conclusions were made on the findings.

## 1.7 SCOPE OF THE STUDY

The key to efficiency lies greatly in the infusing of professional project management practices into the construction (Abenlayon, 2010). With the construction of the Chapels, it is normal that the fundamental procedures in project management which comprise of inception, planning, implementation, checking and controlling and finishing are executed exactly so as to dodge failures in the project. The most important part of these processes for project success is the planning stage. This research work investigates whether churches in Obuasi municipality follow project planning practices while constructing their chapels. Quantitative research approach was adopted with the aid of structured questionnaire which was self-administered by targeted respondents of churches in the Obuasi Municipality in the Ashanti Region of Ghana was used for the collection data. The research was focused on empirical understanding of the status of professional project management practices in Charismatic churches.

## 1.8 SIGNIFICANCE OF THE STUDY

The construction industry generally plays a vibrant role in a national economy development due to the usage of its products such as roads, buildings, dams for the production of goods and service. Project management practices increases the efficiency and effectiveness in discharging of project. However, there is no empirical evidence on the project planning procedures in Charismatic churches.

It is therefore expected that, the study will provide useful lessons on the knowledge base of project management practices in the industry which will serve as basis for improvement in the construction industry and the implementation of church construction projects.

## 1.9 ORGANIZATION OF THESIS

The study was separated into five (5) different chapters. The chapter one concentrated on the introduction to the study. The chapter two focused on reviewing literature on the subject area of the study. The chapter three (3) was about the methodological approach adopted for the study. The chapter four (4) focused on the analysis and discussion of data collected. The chapter five (5) is the final chapter of the study which focused on the summary of findings, conclusions and recommendations made for the study.

# CHAPTER TWO

# LITERATURE REVIEW

## 2.1 INTRODUCTION

This chapter reviewed literature on the subject area of the study. In this chapter on studies conducted in the study area was reviewed to aid in the development of an instrument for the study. This section looked at the applicable themes or topics important to this study from existing scholastic sources and perceives where they fit in the whole field of study. The literature review focused on the life cycle theory and its application, the definition of project and project management, project management practices in Ghana, the phases of project planning, the challenges affecting the construction project management and finally, the challenges hindering the planning procedures in the construction of chapels.

## 2.2 THEORETICAL REVIEW

Biological life cycle of birth, maturity, growth and death are the reason for the existence of life cycles in business. The cycle of mortal biological life is viewed as being applicable to a wide range of business enterprises. With its beginnings in pricing of product during the 1950s (Dean 1950), the life cycle was a generally comprehended idea within 10 years in its application (Levitt 1965). From that point onward life cycle methodologies have kept on being created and extended (Cao and Zhao 2011). The life cycle hypothesis was applied to this research

### 2.2.1 The Life Cycle Theory

The terminology 'life cycle' is presently utilized in numerous fields and in various settings and there are life cycles for companies, information technology, products, processes and software development.

The life cycle point of view gives a useful system from which to structure an all involved perspective on a phenomenon in light of the fact that the methodology enables the majority of its angles to be evaluated in a methodical manner. Every life cycle is made out of phases. A phase is characterized as a noteworthy period in the concept’s life that is discernable from what went before and after it. This point of view perceives and highlights that there are various variables that influence the element at each phase of its life. An actual life cycle can be utilized to increase comprehension and control, for planning operationally and for gauging/anticipating (Kotler and Keller 2012).

### 2.2.2 Application of the Life Cycle Theory to Project Planning Practices

As the terminology life cycle can be useful in numerous fields, it is critical to characterize the extent of this research and what precisely is implied by a project management life cycle. Project management life cycle, implies the phases that a company will experience when picking a technique for overseeing projects.  This research centers on a real-life cycle significant to project level administration. The connecting of activities to projects and projects to portfolios and whether projects and portfolios have a comparative life cycle is outside the extent of this present investigation.

With the concept of project management, projects like the construction of chapels have life cycles which have regular phases inside the life of the project that are frequently connected with the field of construction which set out how activities in those divisions are ordinarily separated into stages (Pinto 2013).

## 2.3 CONCEPTUAL REVIEW

### 2.3.1 Definitions of Project

From literature, projects can be defined from varying viewpoints. PMI (1996) described a project as a unique and temporary endeavor undertaken to deliver a product or service. The term temporary implies that the project has a clear point for completion and unique implies that the service or product varies in some distinctive manner from every single comparable service or product (PMI, 1996).

A project can be described as a human endeavor that have a unique set of activities with cost and time constraints. According to Cooke-Davics (2001), the purpose for the execution of a project is to alter or create a product to meet established goals. Ohara (2005) indicated that, a project is portrayed as a value creation task dependent on the point of interest which is finished in a defined time frame. Furthermore, Bradley (2008), viewed a project as a business endeavor that shows the merits and demerits of the process executed within a limited time frame and budget.

### 2.3.2 Project Management

For a project to be successful, there is the need to value the significance of project management practices (Munns and Bjrirmi, 1996). Murphy and Ledwith (2007) indicated that, the theory of project management has existed for a long time with its application most prominent in the Chinese and Egyptian countries for the construction of the Great Wall of China and pyramids of Egypt.

However, the definition of project management and constantly evolved as there is no consensus in its description among researchers (Shenhar and Wideman, 1996). Every definition of project management has direct integration to the concept of the project and the type of the project. Osien (1971) defined project management as the application of a collection of tools and techniques (such as the CPM and matrix organization) to direct the use of diverse resources towards the accomplishment of a unique, complex, one-time task within time, cost and quality constraints. Morris (1993) subsequently defined project management as a process of integrating everything that needs to be done typically using a number of special project management techniques as the project move through its life cycle from project conception to handover in order to meet the objectives of the project.

Burke (1998) considers project management to be a specialized management technique, which involves planning and control of the project under a single point of responsibility. Turner, (1994) also defined project management as the art and science of transforming vision into reality. Additionally, BS6079 (1996) defined project management as the planning, monitoring and control of all aspects of a project and the motivation of all those involved in it to achieve the project objectives on time and to the specified cost, quality and performance.

Despite these definitions, Turner (1999) argues that project management is about managing people to deliver results, rather than the work itself. Other authors have also suggested that, the definition of project management should also describe the cultural, structural and interpersonal aspects of the project (Cleland & Ireland, 2002). Following the divergent view of researchers, Wideman (2003), reviewing Slevin and Pinto, (2007) argues that project management is a philosophy and technique that enables its practitioners to perform to their maximum potential within the constraints of limited resources, thereby increasing profitability. In the same vain, it is still an art of directing and coordinating human and material resources to achieve stated objectives within the limits of time, budget and client satisfaction (Szymczak and Walker, 2003).

Westland (2007) opined that, project management is very significant in the successful implementation of a project. It involves the use of a set of skills and experience to mitigate the risk level within the project and thereby enhance the probability of project success. In order for project managers to improve their chances of success, they use various tools such as planning software, registers, modeling software, document templates, audit checklists and review documents. Numerous procedures and methods are required to assess and control time, cost and quality of a project. For instance, management of cost, management of quality, management of time, risk management, and management of disputes.

In view of this, other researchers have recommended that, the definition ought to be progressively comprehensive and ought to underline the significance of working with partners to characterize the needs of the project (Jugdev and Muller, 2005). In reaction to this the Project, Management Body of Knowledge (PMBOK, 2008), characterized project management as the use of learning, aptitudes, apparatuses and strategies to the activities of the project so as to meet the needs of the stakeholders. The debate about the definition is still ongoing, but the definitions of project management depends on the perspective of the individual researcher.

### 2.3.3 Project Management Practices in Ghana

In Ghana, the presentation of Project Management Concept into the construction industry goes back to the late 1980s when the structure was first acquainted with the Social Security and National Insurance Trust (SSNIT), (Ahadzie and Amoah-Mensah, 2010). Until this, SSNIT depended to a great extent on conventional administration practices in the execution of its accommodation project, which prompted time and cost over-runs; evaluated to be over 100% of the genuine expense and time.

The administrative sector of Ghana and the overall population, whose commitment were being utilized for such project wound up frightened and lost trust in SSNIT as solid accommodation suppliers (Ofori, 1989; Ahadzie and Amoah-Mensah, 2010). It was during this difficult period that SSNIT designated their first Project Manager including the development of 1,637 single story-lodging in the Sakumono territory, Greater Accra Region of Ghana.

Project management presents a component for developing nations, for example, Ghana to compute successfully and proficiently with their developed colleagues (nations) in fields such finance, aviation, construction and engineering. Sadly, enough, project management practices in the emerging and developing economies are nothing but least to be desired, unattractive and cumbersome. (Andersen et al., 2002).

### 2.3.4 Project Management Planning Stages

The planning stage sets up the frameworks that are utilized to oversee and control the work during the project implementation stage. Menches, et al, (2008) recorded a few things that should be incorporated into the planning of the project, including determination of the team for the project, production of the task documentation framework, starting the acquisition of materials, developing of the project calendar and timelines, and a few different exercises that set up a project for implementation. Menches, et. al., (2008) additionally called attention to that there is solid recounted proof that projects are regularly executed with no formal planning, and these casually planned (or unplanned) projects will in general experience a more prominent number of issues, for example, extreme variations, surpassing the financial limit, inability to finish the work on schedule, and low (or no) benefits.

Studies have demonstrated that a fitting procurement framework may upgrade the likelihood of success in the project (Rwelamila and Meyer, 1999; Luu, et al, 2003).

The obtainment (purchasing) stage is a procedure that is regularly alluded to as "purchasing out" the task, or acquiring the work, materials, and tools expected to finish the project (Jackson, 2004). For all materials, buying requests ought to have been issued before the beginning of the construction procedure. The obtainment procedure is in this manner overseen as indicated by a 'push' approach, in order to convey materials to the site in consistence with the due dates set up by the normal construction plan (Caron et al., 1998).

The construction stage starts with a formal letter arranged by the proprietor known as the "Notice to Proceed" (NTP). For this research, the construction stage will address three territories that influence the smooth activities of the project construction stage: coordination of exchanges (trades), preparation, and construction. When the contractual worker has gotten the Notice to Proceed, at that point the manager for construction starts the coordination of subcontractors for the project. This needs the construction manager to set up the standard procedures for the numerous specialists required during the construction stage. The construction administrator likewise has the chance to go over issues, for example, sequencing, work hours, material stockpiling, quality control, access to the site, and numerous other relevant subjects with the newly formed team for the project. Rapport building is fundamental in setting up a situation of trust and participation at the startup of the project (Jackson, 2004).

Assembling or mobilization tends to the majority of the project manager activities which must be achieved preceding the beginning of the construction. Getting ready for these projects to get to a high state of achievement relies upon the management techniques presently accessible to the project supervisor. For instance, (Rad and James, 1983) proposed rules for field manager delineating potential issues they may experience when building up the site design plan.

Contractual workers are very much aware of their exceptional job and are will undoubtedly bring a quality project on schedule and within cost; their business survival relies upon their proceeding with performance in the market place. Subsequently, it might be foreseen that contractual workers will utilize all accessible administrative aptitudes, including current planning methods, to plan and screen their activities on the projects (Cole, 1991).

Various researches have concentrated on approaches to improve the planning process in building construction. Dawson and Dawson (1998) endeavored to characterize the term and sequencing of activities in construction by upgrading the scheduling issue. Chan and Kumaraswamy (2002) built up a forecasting model for duration used in construction that joins notable information and variables that influence the project span. A few researches concentrated on planning of project for conservation work, which was particularly relevant to the present research. These researches called attention to the difficulties of managing existing structures, typically situated in an urban setting (Robson, 1999; Feilden, 2003; Mitropoulos and Howell, 2002) considered renovation enhancement instruments, which brought about the advancement of techniques to avoid rework on the design. In view of this, the study tends to determine if the churches in the Obuasi Municipality follow through all the stages in project management practices.

## 2.4 CHALLENGES AFFECTING CONSTRUCTION PROJECT MANAGEMENT PRACTICES

A lot of project management issues include staying away from issues, handling new grounds, dealing with a group of individuals and accomplishing clear goals rapidly and productively (Reiss, 1995). Nonetheless, in most developing nations, is the other way around. Rwelamila, (2007) additionally noticed that the project management skills of the public sector institutions, which are in charge of development of infrastructure in most developing nations are poor in spite of the fact that these institutions depict themselves as having the option to oversee projects adequately. The business in most developing nations is looked with various deserting of project, as revealed by Ahadzie and Amoah Mensah, (2010) and Nwachukwu et al., (2010). What's more, time and cost overrun, resultant cases and debates remain standards in developing nations (Al-Moumani, 2000; Kumaraswamy and Chan, 1998; Mezher and Tawil, 1998; Ogunlana et al 1996; El-Razek et al., 2008; Assaf and Al-Hejji, 2006; Chan and Kumaraswamy, 1996; Kaming et al., 1997). All the more along these lines lackluster performance is regularly credited to absence of efficient working connections among project members.

The absence of project management idea has prompted low efficiency and low quality, which has been the most despicable aspect of construction businesses in a few nations, especially in developing nations (Mutijwaa and Rwelamila, 2007; Le-Hoai et al., 2008, Gyadu-Aseidu, 2009). Then again, experts in developing nations do not have the capacity to enhance and adjust to better approaches for working (de Ligny and Erkelens, 2008). For example, the construction business in South Africa is stuck in the seventies' frame of mind of adversarialism and pessimism (Gidman, 2001 and Barriere, 2003). It is no big surprise that Thwala and Mvubu, (2008) showed that construction companies in developing nations need limit and can't fulfill the need of construction work. Besides, Ofori, (2003) demonstrated that these difficulties confronting the construction business in developing nations are outstanding because of terrible performances on projects that happens in these countries.

Pleasingly, proficient project management is as yet advancing over the world yet its usage to construction projects in developing nations displays the absolute most difficult fields of which it requires efficient project management procedures (El-Saaba, 2001 and Ahadzie, 2009). These difficulties in usage of efficient project management are because of the way of life and different qualities of the specific culture and design of its financial, political and authoritative framework in developing nations (Barriere, 2003). In buttressing this, Barriere (2003), Abbasi and Al-Mharmah uncover that project management practices ought to be reliable with standards.

What's more is that, Gow and Morss, (1988) demonstrated nine limitations, which are basic to the viable execution of project management practice, which are likewise now predominant in developing nations. These limitations include: incorporates social qualities, political and financial conditions, authoritative situations, social issues, absence of abilities, and absence of assets (Muriithi and Crawford, 2003; Stuckenbruck &Zomorrodian 1987; Gow and Morss, 1988). In the public sector, government administration, corruption and bribery are highly seen as run profound into projects, which is accounted for to be a trouble for project management practice (Stuckenbruck and Zomorrodian, 1987).

Creating viable project administrators anyway is turning into a bigger encounter with the expanding intricacy of projects and the shortage of human capital (Crawford et al, 2006). Also Loo, (2002) demonstrated a few hindrances which retard the advancement or the development of project management practice in various fields and it is likewise along these lines the equivalent in the construction business. These obstructions are authority and hierarchical culture, insufficient investment in training, individual versus group remuneration, time weights and imperatives, resistance to change and no project management champ in the company. Notwithstanding, this difficult business conditions, project management stays an energizing and advancing practice.

## 2.5 CHALLENGES CONFRONTING PLANNING PROCEDURES IN THE CONSTRUCTION OF CHAPELS

Cadence (2007) discussed some biggest problems in project planning that can also be present in the construction of chapels. Among these problems are inadequate scope definition, slow pace of the projects, lack of planning skills, inability to get team members on board, unclear responsibility/task level, uncontrolled changes and passive attitudes of project manager.

### 2.5.1 Inadequate Scope Definition

The planning phase is the phase that forms an integral part following the approval and commencement. This is basic to the accomplishment of the projects. In the course of planning, the focus is building up the roadmap for the project team to pursue throughout the project execution phase. Notwithstanding, building up a project management plan is an ideal opportunity to characterize scope. Deficient scope description poses numerous challenges to the execution of projects (Udo and Koppensteiner, 2004).

Projects normally runs into numerous challenges without well-characterized scope. The scope of a project sets up limits, obligations and techniques to be used. The project team stays concentrated on undertaking the project to meet the desired requirement and avoid scope creep. This constantly ties up important assets and is effectively avoidable with appropriate planning and correspondence.

### 2.5.2 Execution of the Project

The execution stage is the phase that becomes possibly the most important factor following approval and planning. While past stages have disposed of dangers and issues, more will be found in this stage. While the project supervisor and group must be aware of finding these issues and understanding them as ahead of schedule as could reasonably be expected, there is a class of issues brought about by absence of procedure. Truth be told, a portion of these issues are brought about by the executives who don't comprehend the procedures required for good project control, procedures which additionally quicken execution when available (Udo and Koppensteiner, 2004).

### 2.5.3 Slow Starting Pace of the Projects

One of the serious issues in construction projects planning is the way that customers in some cases griped of the moderate beginning pace of the projects. Explanations behind these moderate beginnings differ, and some are profoundly conflicting. For instance, some gripe that there is an excessive amount of time, while others grumble that there are no sufficient opportunities. Other regular reasons given are that there are unanswered inquiries, they do not think enough about the project, or there are insufficient individuals on the team for the project.

Once in a while, the reasons offered relate to the work done in preceding stages. Possibly the work was fragmented or lacking. The primary concern, however, is those projects normally fall behind in light of the fact that the pace was not set toward the start of the project. Despite the fact that individuals are hectically working, no genuine advancement is being made on the project (Agyekum, Ayarkwa, and Adinyira, 2012).

### 2.5.4 Lack of Planning Skills

A typical issue that it is routinely observe with customers in an expansive range of businesses is that numerous individuals basically would not be able to design their area of the work required for the project to be effective. Planning is not an ability that easily falls into place for a great many people. It requires decided, dedicated mental exertion – as Henry Ford is presumed to have stated: “Thinking is the hardest work there is, which is probably the reason why so few engage in it!”  There are devices to help with planning of projects, yet these don't really separate the project into the segment bit by bit parts that every individual should contribute.

This issue can result in the project failing to get off the ground by any means, or then again, continuing in a progression of little gains pursued by mishaps because of an absence of appropriate planning. This thus can prompt demoralization and negative inclination with respect to all included.

### 2.5.5 Inability to Get Team Members on Board

A typical issue numerous churches face in project management is just having the option to get enough individuals onto the team for the project. To gather significant speed, an effective project requires adequate colleagues to deal with all parts of the planning and execution.  What makes this issue particularly treacherous is that now and again, it might at first give the idea that there are enough ready colleagues for the project. What winds up evident as the project gets in progress anyway is that a noteworthy number of these individuals are as of now overcommitted on different projects and thusly incapable to contribute completely in their job as proposed.

This can likewise be a timing issue, where individuals appointed prior to the project are inaccessible at its beginning because of different tasks they are associated with running late. At that point there are circumstances where as of late finished projects fall flat, prompting crisis circumstances that involve human asset, leaving the project stuck on the runway.

Many committed workers like to appear as accommodating as could reasonably be expected, which is the reason it is regular for line administrators to acknowledge new projects notwithstanding when they know that their area of expertise has no extra asset. This is setting up the project for disappointment even before it has started. It is basic that there is adequate asset accessible to you at the beginning of the project, as a slow beginning is dispiriting for the group and brings about wasted time and dissatisfaction, and some of the time to the entire project being re-propelled a long time after the expected date when it was expected to be completed.

### 2.5.6 Unclear Responsibility

This is a typical hindrance for organizations which shows up at the planning and execution phase, when tasks have been selected however real obligations and assignments are not clear. While the general aim of the project may have been defined, normally, the tasks that are expected to push the whole project ahead are not adequately detailed. Some vital projects might be neglected through and others are not allocated to the suitable individual (Jordan, 1999).

### 2.5.7 Unforeseen Circumstances

Indeed, even teams for the project with the best expectations endure the difficulties of and there are various contributing components. For instance, team members frequently don't have a total comprehension of projects during the planning stage and make changes to the work they're doing past the midpoint of the project. Project administrators consent to changes without fair treatment, with an end goal to give great client support, without understanding the progressions being mentioned.

Supervisors are awkward with cutoff points. They need the adaptability to make changes when they consider them since they live in a world which is continually changing and they're always improving acclimations to give client care, better support of their customers in this living working condition. In any case, a sloppy change procedure turns into a circle that makes the timetable slip, assignments to be late, and has a possibly negative by and large project effect.

### 2.5.8 Passive Attitudes of Project Managers

There's central perplexity in firms between coordination and authority. An organizer helps the project administrator in the logistical necessities and backing of the project. Then again, project managers are solid and steady with reasons guarding poor project execution. Projects delay because of conditions outside their ability to control.

## 2.6 CONCLUSION

Project management practices include completing the everyday administration exercises and choices to meet set project goals. These practices may differ from company to company, as accentuated by (Hobday, 2000), one size doesn't fit all. This is particularly so for business institutions when contrasted with churches. This requires discovering of the connection between project management practices and its performance. Project performance is viewed as attached to project achievement and this is related with hierarchical target just as its performance. Company’s performance is hence estimated utilizing certain criteria created dependent on the project goals. Project performance has been estimated with a few measurements, for example, cost, time, quality, advantages to end clients, and advantages to national infrastructure, ecological effect, and wellbeing and security prerequisites among other benchmarks. This study takes into consideration whether the churches in Obuasi Municipality put into practice project management planning in building their chapels.

# CHAPTER THREE

# RESEARCH METHODOLOGY

## 3.1 INTRODUCTION

In order to develop effective planning procedures in Congregational Chapel Buildings projects, there is the need for data to be collected from the churches on project planning procedures. In view of this, the chapter discussed the techniques as well as the methodology utilized in the collection of the data. This chapter basically dealt with the research design, the research strategy, the population under study, the techniques for sampling as well as the sample size, the instruments for data collection and the data analysis strategies.

## 3.2 RESEARCH DESIGN

Research design is the procedures used to enquire into a particular circumstance, while strategies are the individual methods for collection of data, analysis and so on (Easterby-smith, et al. 2002). Cohen et al, (2007) states that if methodology is termed as procedures and techniques utilized during the time spent in collecting data, the goal of the procedure at that point is to define ways and approaches to deal with, sorts and ideal models of research. The research techniques are divided into two main types that is qualitative and quantitative. The study basically adopted the quantitative research strategy.

Saunders et al. (2003) depict that in quantitative study the analyst poses questions that require precise answers. Moreover, quantitative takes into consideration numerical estimation and statistical data. It utilizes scientific models to test the assumptions, and supports the perspective on the positivist model that there is an objective reality that can be measured and estimated. As indicated by Yin (1994) the connection between the research question and the research procedure is significant in choosing the fitting methodology for the study. The study therefore adopted the survey research design due to the research questions formed in relation to the objectives of the study.

## 3.3 RESEARCH STRATEGY

Carrie (2007), discussed three (3) basic research strategies. They are quantitative, qualitative and mixed research method. The choice of a research strategy depends on the type of data required for the study. There are basically two (2) forms of data. These are numerical data and textural data.

Quantitative studies deal with numerical data whiles textural data and normally used for qualitative research. The mixed research method uses both numerical and textural data as it combines the strengths of both quantitative and qualitative research. The quantitative research is specifically used for survey and experiment researches as it builds upon existing theories (Leedy and Ormod, 2001).

From the above description, the quantitative research strategy was deemed most suitable for the study. This is because, this study utilized numerical data and mathematical tools for the analysis which are significant features of quantitative research.

## 3.4 POPULATION OF THE STUDY

The population of the study entails set of individuals who share or exhibit similar characteristics which are of great interest to the researcher (Creswell, 2003; Morgan, 1997). The population of the study consisted of Charismatic churches registered in the Obuasi Municipality. As at the time of study, there were 227 Charismatic registered churches in the Obuasi Municipality according to Christian Council of Churches, Obuasi Metropolis.

## 3.5 SAMPLING SIZE AND SAMPLING TECHNIQUE

Sample is a fragment of a masses or universe of a population. It is a standard language in research which express that the high the size of the sample, the higher the relentless reliability and unwavering validity in the result and the opposite as well (Creswell, 2003; Tailor, 2005). The study utilized the convenient sampling technique in data collection. With the convenient sampling technique, respondents were contacted based on their availability and reediness to participate in the study. Using the convenient sampling technique, the number of churches taken into consideration in relation to the churches was 10 out of the 227 registered Charismatic churches. In view of this, 5 officials from each of the churches were sampled making a total of 50 church personnel. Therefore, the sample size for the study was 50. The researcher arrived at a sample size based on the Roscoe (1975) rule of thumb for determining a sample size in behavioral research which states that a sample size greater than 30 and less than 500 is good enough for most studies.

## 3.6 DATA COLLECTION METHOD

The researcher considered several data collection instruments and finally chose structured questionnaires. This was because questionnaires have the tendency to cover a wider area within a short time. Moreover, it is preferred in studies which adopt the quantitative research design approach. And this study is not an exception.

The questionnaires were distributed to the targeted respondents of the study. Two main measurement scales were adopted and used in the study. That is nominal and ordinal. In the nominal scale the variables that were affected include. Age group, marital status, education and the knowledge of project management were included. In the ordinal scale, a five-point scale was used where 5-implies strongly agree and 1-plies strongly disagree. The questionnaires were further grouped according to the objectives of the study for easily validity and identification

## 3.7 DATA ANALYSIS TECHNIQUE

Analysis of data is the way toward changing raw data into valuable outcome. The researcher adapted quantitative research plan strategy for the study (Creswell, 2003; Tailor, 2005). This makes statistical analysis vital in this research. Consequently, Statistical Package for Social Sciences (SPSS 20) will be adapted to break down the field information. This will be executed with the guide of Microsoft Excel. The field information was enough validated to expel potential omissions, blunders, irregularities, and non-response. Descriptive statistics such as means, standard deviations and frequencies were used tools for analysis. The outcomes were exhibited utilizing tables and graphs. The discoveries were additionally talked about with recently done researches (Sakara, 2000).

## 3.8 ETHICAL CONSIDERATIONS

Research ethics relates to how to formulate and clarify a research topic, design a research and gain access, collect data, process and store data, analyse data and write up research findings in a moral and responsible way (Saunders, Lewis, & Thornhill A., 2009). Whether colleagues, respondents, assistants, or people in positions of authority are involved, ethical concerns in the field is inevitable (Perecman & Curran, 2006). In line with Mugenda and Mugenda (2003) who stated that researchers should avoid physical or psychological harm to the participants, the questionnaire was designed such that personal information about the respondent remains anonymous and information obtained from the respondents in the process of the whole research was kept confidential.

# CHAPTER FOUR

# ANALYSIS AND DISCUSSION OF RESULTS

## 4.1 INTRODUCTION

The main aim of this study is to develop effective planning practices in Congregational Chapel Buildings projects. This section of the thesis takes into consideration the analysis of the data and discussion of results from the analysis. The discussion will be based on the objectives of the study. This chapter basically, discusses how the study answered the research questions and its implications. That is, to establish planning practices followed by churches in the construction of chapel projects; identify the planning Practices currently adopted by Churches in the construction of Chapels; examine the challenges confronting planning Practices in the construction of Chapels and make recommendations for effective project management Practices for the Churches in the Obuasi Municipality.

## 4.2 DATA PRESENTATION

A total number of fifty church officials were sampled for the study. In view of this, a total of fifty questionnaires were distributed to the respondents to aid in the collection of data. Taking this into cognizance, all of the questionnaires were returned fully completed. This was a 100% response rate. The response rate was considered very effective because at least more than 50% of the targeted respondents participated in the study. The researcher felt that the views expressed in the questionnaire is therefore representative of the target population.

## 4.3 DEMOGRAPHIC INFORMATION OF RESPONDENTS

This section of the chapter presents the demographic and background information of the respondents. The age,	level of education, marital status, the position in the church as well as the knowledge on project management practices of the respondents were the demographics considered in the study. These characteristics of the respondents were quite critical for the purpose of whether the respondents in the research are a representative sample of the target population for generalization purposes.

### 4.3.1 Age Distribution of Respondents

Research proposes the presence of a connection between age and making of decisions. For instance, a research by Czaja et al. (1995) observed age to be a determinant on enunciation of decisions made on projects; research by Obst et al. (2011) also observed age to be associated with risk decisions. In accordance with these researches, this research likewise anticipates that decisions of project management practices should be impacted by the age of project management professionals.

With that in mind, the study collected data on the age of the respondents. The study therefore revealed that, 20% of the respondents were between the ages of 18 years and 25years, 30% of them were between the ages of 26 years and 34years, 30% of them were between the ages of 35years and 44years and 20% of the respondents were between the ages of 45 years and 54years. This basically implies that majority of the respondents were below the ages of 45 years.

#### Table 4.1: Age Distribution of Respondents

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | 18-25 | 10 | 20.0 | 20.0 | 20.0 |
|  | 26-34 | 15 | 30.0 | 30.0 | 50.0 |
|  | 35-44 | 15 | 30.0 | 30.0 | 80.0 |
|  | 45-54 | 10 | 20.0 | 20.0 | 100.0 |
|  | Total | 50 | 100.0 | 100.0 |  |

Source Field Survey, (2019)

### 4.3.2 Level of Education of Respondents

Decision making process is generally influenced by the level of knowledge. The level of education of respondents was sought for as part of the demographic data. This is basically due to the fact that the level of education tends to affect the decisions made on the project management especially at the planning stage. The study discovered that majority of the respondents as shown by 54% have their level of education up to the Senior High/Technical/Vocation, 24% of the respondents also had their educational level up to the tertiary and the rest representing 22% had their level of education up to Basic level.

#### Table 4.2: Educational Level of Respondents

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Basic | 11 | 22.0 | 22.0 | 22.0 |
|  | Senior High/Technical/Vocation | 27 | 54.0 | 54.0 | 76.0 |
|  | Tertiary | 12 | 24.0 | 24.0 | 100.0 |
|  | Total | 50 | 100.0 | 100.0 |  |

Source (Field Survey, 2019)

### 4.3.3 Marital Status of Respondents

With respect to the marital status of the respondents, 62% of the respondents were married, 24% of the respondents were single and the rest of the 14% were separated/divorced

#### Table 4.3: Marital Status of Respondents

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Single | 12 | 24.0 | 24.0 | 24.0 |
|  | Married | 31 | 62.0 | 62.0 | 86.0 |
|  | Separated/Divorced | 7 | 14.0 | 14.0 | 100.0 |
|  | Total | 50 | 100.0 | 100.0 |  |

Source (Field Survey, 2019)

### 4.3.4 Positions of Respondents in the Church

The positions of the respondents in the church were also asked from the respondents. This is due to the fact that the position of the respondents will definitely determine whether the respondent is basically involved in the decisions and planning of the projects in the church. The study shown that, among the respondents, 20% of them were the Head Pastors of the church, 40% of them were administrators of the church, 26% of the respondents were Assistant Pastors and 14% of them were the Secretaries of the Church.

#### Table 4.4: Positions of Respondents in the Church

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Head Pastor | 10 | 20.0 | 20.0 | 20.0 |
|  | Assistant Pastor | 13 | 26.0 | 26.0 | 46.0 |
|  | Administrator | 20 | 40.0 | 40.0 | 86.0 |
|  | Secretary | 7 | 14.0 | 14.0 | 100.0 |
|  | Total | 50 | 100.0 | 100.0 |  |

Source (Field Survey, 2019)

### 4.3.5 Respondents Knowledge in Project Management Practices

So as to actualize projects and convey change, members of the team must will and be ready to share information and their knowledge in project management (Dietrich et al 2010). The knowledge possessed by the members of the team is a fundamentally part of the change exertion, and knowledge integration capacity is a significant component of making of decisions effectively during the planning stage of the project (Garcia-Penalvo and Conde, 2014).

Results from the study revealed that majority of the respondents as shown by 60% have no knowledge in project management practices while the rest of the 40% of the respondents had knowledge in project management practices. This implies that, members of the team will be faced with a lot of challenges in the planning of any church projects and thereby influence the effectiveness and efficiency of the projects in question. The other sections of the chapter will determine if such was the case.

#### Table 4.5: Respondents Knowledge in Project Management Practices

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Yes | 20 | 40.0 | 40.0 | 40.0 |
|  | No | 30 | 60.0 | 60.0 | 100.0 |
|  | Total | 50 | 100.0 | 100.0 |  |

Source (Field Survey, 2019)

## 4.4 PROJECT PLANNING PRACTICES NEEDED TO BE FOLLOWED

The intricacy of conservation work of memorable buildings structures will in general be less well-planned and harder to control than the development of new structures (Egbu, 1999). In this manner, improvement of project planning strategies is fundamental to help control activities throughout a project. To comprehend the intricacy of issues related with planning an effective project, there is the need to spell out the procedures needed to be followed in churches in the construction of chapel.  The study therefore sought to establish what planning practices must be followed by churches in the construction of chapel projects. The following were the results from the study.

The study revealed that, majority of the respondents agreed or strongly agreed representing 56% that as part of project planning practices, there is the need to identify specific work to be performed and the goals that define the church project, 12% of the respondents neither agreed nor disagreed to that, while 32% of them disagreed or strongly disagreed. Further illustration can be found in Figure 4.1 and Table 4.6.

#### Table 4.6: Identifies specific work to be performed and the goals that define the project

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Strongly Disagree | 5 | 10.0 | 10.0 | 10.0 |
|  | Disagree | 11 | 22.0 | 22.0 | 32.0 |
|  | Neither Agree nor Disagree | 6 | 12.0 | 12.0 | 44.0 |
|  | Agree | 17 | 34.0 | 34.0 | 78.0 |
|  | Strongly Agree | 11 | 22.0 | 22.0 | 100.0 |
|  | Total | 50 | 100.0 | 100.0 |  |

Source (Field Survey, 2019)

##### Figure 4.1: Identifies specific work to be performed and the goals that define the project

Source (Field Survey, 2019)

The study further revealed that 56% of the respondents representing the majority agreed or strongly agreed that providing documented estimates regarding schedule, resources and cost for planning, tracking and controlling the church project is part of the project planning procedures needed to be followed. On the other hand, 34% of them disagreed or strongly disagreed while 12% neither agree nor disagreed. Table 4.7 and Figure 4.2 further demonstrate the findings on this.

#### Table 4.7: Provision of Documented Estimates Regarding Schedule, Resources and Cost for Planning, Tracking, and Controlling the Project

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Strongly Disagree | 10 | 20.0 | 20.0 | 20.0 |
|  | Disagree | 7 | 14.0 | 14.0 | 34.0 |
|  | Neither Agree nor Disagree | 7 | 14.0 | 14.0 | 48.0 |
|  | Agree | 11 | 22.0 | 22.0 | 70.0 |
|  | Strongly Agree | 15 | 30.0 | 30.0 | 100.0 |
|  | Total | 50 | 100.0 | 100.0 |  |

Source (Field Survey, 2019)

##### Figure 4.2: Provision of Documented Estimates Regarding Schedule, Resources and Cost for Planning, Tracking, and Controlling the Project

Source (Field Survey, 2019)

The findings from the study also showed that 58% of the respondents agreed or strongly agreed that obtaining the church board’s commitments that are planned, documented and agreed upon is a necessary procedure to following project planning. 12% of the respondents neither agreed nor disagreed and 30% of them disagreed or strongly disagreed that obtaining the church board’s commitments that are planned, documented and agreed upon is not a necessary procedure to following project planning.  Table 4.8 and Figure 4.3 demonstrate the findings further.

#### Table 4.8: Obtaining Church Board’s Commitments That Are Planned, Documented, And Agreed Upon

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Strongly Disagree | 8 | 16.0 | 16.0 | 16.0 |
|  | Disagree | 7 | 14.0 | 14.0 | 30.0 |
|  | Neither Agree nor Disagree | 6 | 12.0 | 12.0 | 42.0 |
|  | Agree | 12 | 24.0 | 24.0 | 66.0 |
|  | Strongly Agree | 17 | 34.0 | 34.0 | 100.0 |
|  | Total | 50 | 100.0 | 100.0 |  |

Source (Field Survey, 2019)

##### Figure 4.3: Obtaining Church Board’s Commitments That Are Planned, Documented, and Agreed Upon

Source (Field Survey, 2019)

Moreover, findings from the study showed that 54% of the respondents agreed or strongly agreed that continuing the development and documentation of the project alternatives, assumptions and constraints is also a critical part of the project planning practices needed to be followed. 32% of the respondents on the contrary, disagreed or strongly agreed while 14% neither agreed nor disagreed. The results are displayed in Table 4.9 and Figure 4.4.

#### Table 4.9: Continuing the Development and Documentation of Project Alternatives, Assumptions, and Constraints

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Strongly Disagree | 8 | 16.0 | 16.0 | 16.0 |
|  | Disagree | 8 | 16.0 | 16.0 | 32.0 |
|  | Neither Agree nor Disagree | 7 | 14.0 | 14.0 | 46.0 |
|  | Agree | 14 | 28.0 | 28.0 | 74.0 |
|  | Strongly Agree | 13 | 26.0 | 26.0 | 100.0 |
|  | Total | 50 | 100.0 | 100.0 |  |

Source (Field Survey, 2019)

##### Figure 4.4: Continuing the Development and Documentation of Project Alternatives, Assumptions, and Constraints

Source (Field Survey, 2019)

The study moreover discovered that 48% of the respondents agreed or strongly agreed that the issue of establishing a baseline of the plan from which the project will be managed is also a factor of the project planning practices, while 30% of the respondents disagreed or strongly disagreed to the statement and 22% neither agreed nor disagreed. Table 4.10 and figure 4.5 illustrate the results from the study.

#### Table 4.10: Establishing A Baseline of the Plan from Which the Project Will be Managed

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Strongly Disagree | 8 | 16.0 | 16.0 | 16.0 |
|  | Disagree | 7 | 14.0 | 14.0 | 30.0 |
|  | Neither Agree nor Disagree | 11 | 22.0 | 22.0 | 52.0 |
|  | Agree | 16 | 32.0 | 32.0 | 84.0 |
|  | Strongly Agree | 8 | 16.0 | 16.0 | 100.0 |
|  | Total | 50 | 100.0 | 100.0 |  |

Source (Field Survey, 2019)

##### Figure 4.5: Establishing A Baseline of the Plan from Which the Project Will be Managed

Source (Field Survey, 2019)

The findings from the study established that the churches are of the views that identification of specific work to be performed and the goals that define the project; provision of documented estimates regarding schedule, resources and cost for planning, tracking, and controlling the project; obtaining of church board’s commitments that are planned, documented, and agreed upon and continuing the development and documentation of project alternatives, assumptions, and constraints are the	 planning procedures that must be followed by churches in the construction of chapel projects.

## 4.5 PROJECT PLANNING PRACTICES ADOPTED BY THE CHURCHES

The planning stage sets up the frameworks that are utilized to oversee and control the work during the project implementation stage. Menches, et al (2008) recorded a few things that should be incorporated into the planning phase. The study therefore sought to identify the planning Practices currently adopted by Churches in the construction of Chapels. The following were the results from the study.

The graph below depicts that majority of the respondents representing 60% almost every time or frequently adopt as part of the planning practices in the construction of their chapels develop the project goals, 22% of them almost never or never adopted and 18% occasionally or sometimes adopted. This implies that the purpose or the reason why the church project is constructed is defined and developed. Figure 4.6 further demonstrates the findings in relation to this.

##### Figure 4.6: Development of Project Goals

Source (Field Survey, 2019)

The study further discovered that 42% of the respondents almost every time or frequently adopted the creation of list of things the project needs to deliver to meet those goals as part of the procedures adopted in the construction of their chapels in the municipality. On the other hand, 42% almost never or never adopted that and 16% of the respondents occasionally or sometimes adopted. The implication here is that, the churches fails to create list of things the project need to deliver after the development of the church project goals and objectives. Figure 4.7 spells out the results graphically.

##### Figure 4.7: Creation of list of things the project needs to deliver to meet those goals

Source (Field Survey, 2019)

With regards to the findings of the study, 62% of respondents almost every time or frequently adopted as part of the planning practices in the construction of chapels, they identify by name, the individuals and organization with leading role in the project; for each the roles are described as well as their responsibilities on the project. On the contrary, 28% of the respondents almost never or never adopted and 10% of the respondents occasionally or sometimes adopted that. Figure 4.8 graphically displays the results.

##### Figure 4.8: Identify, by name, the individuals and organisations with a leading role in the project. For each, describe their roles and responsibilities on the project

Source (Field Survey, 2019)

Another critical planning practices needed to be adopted in the construction of church projects is by specifying the number and type of people needed to carry out the project. The findings of the study revealed that 56% of the respondents almost every time or frequently adopted such procedure as part of their planning procedures while 28% of the respondents almost never or never adopted the procedure and 16% occasionally or sometimes adopted the procedure. This implies that despite the lack of knowledge of project management among the respondents, they perceived the need to make sure that the number and type of people needed to carry out the project are critically specified. Figure 4.9 illustrates the results.

##### Figure 4.9: Specification of the Number and Type of People Needed to Carry Out the Project

Source (Field Survey, 2019)

The respondents were further asked to provide feedback on whether they adopted the “Creation of document showing who is to be kept informed about the project and how they will receive the information” as part of the planning practices in construction of their chapels. The results from the study showed that 48% of the respondents almost every time or frequently adopted the procedure while 34% almost never or never adopted the practice and 18% of them occasionally or sometimes adopted the practice. The implication here is that, churches in the municipality did not create document showing who is to be kept informed about the project and how they will receive the information. This will make monitoring and accountability of the activities of the construction of church projects in the municipality very challenging. Figure 4.10 demonstrates the findings.

##### Figure 4.10: Creation of Document Showing Who is to be Kept Informed About the Project and How They Will Receive the Information

Source (Field Survey, 2019)

The results from the study established that 50% of the respondents almost every time or frequently adopted the practice of identifying as many risks to the church’s project as possible and be prepared if something bad happens as part of the planning practices of construction of church in the municipality. On the contrary, 34% of the respondents almost never or never adopted the procedure and 16% occasionally/sometimes adopted such practice. This finding means that in the planning practices of construction of the chapels, the officials tend to Identify as many risks to the church’s project as possible and be prepared if something bad happens. In view of this, there is the possibility that in the course of constructing the chapels, risks can be avoided. Figure 4.11 demonstrates the results of the study.

##### Figure 4.11: Identification of Risks to the Church’s Project as Possible and be Prepared if Something Bad Happens

Source (Field Survey, 2019)

## 4.6 CHALLENGES CONFRONTING PLANNING PRACTICES IN THE CONSTRUCTION OF CHAPELS

There are challenges confronting the project management activities especially the planning practices in the construction of chapels. Respondents were asked to provide feedback on the difficulties they are faced with as they planned for the construction of their chapels in the Obuasi Municipality. This segment of the chapter discussed the findings on the challenges confronting the planning procedures in the construction of the chapels.

Table 4.11 shows descriptive statistics that reveal the extent to which variables were perceived as challenges. In this table, variables highly perceived as challenges have mean scores closer to 5, which is the highest value on the measurement scale. Variables lowly perceived as challenges have low mean scores which are close to 1, the lowest value on the measurement scale.

On the basis of these criteria, the variables that are lowly perceived as challenges included “Unforeseen Circumstances” has the smallest mean score (M = 3.06, SD=1.490), “Inability to Get Team Members on Board” (M = 3.12, SD = 1.466) and “Inadequate Scope Definition” (M = 3.18, SD = 1.480) also have small mean scores. Therefore, these three variables, based on the perceptions of the church officials, do not represent strong challenges faced by them in the planning procedures of the construction of chapels.

The other variables however have large mean scores, suggesting that they are highly perceived as challenges faced in the planning practices of the construction of chapels. These include: “Lack of Planning Skills” (M = 3.20, SD = 1.370), “Unclear Responsibility tasks for project members” (M = 3.24, SD = 1.393); “Passive Attitudes of Project Managers” (M = 3.32, SD = 1.449) and “Slow Starting Pace of the Projects” (M = 3.48, SD = 0.515).

The lack of planning skills as a major challenge to the church officials as they plan for the construction of chapel can be attributed to the lack of knowledge on project management practices as well as its importance in construction. Again, the issue of church officials having unclear responsibility tasks for the members of the project team might be due to the failure of these officials to create the list of things the project needs to deliver to meet those goals. In view of this, supervision and monitoring of the activities of the project will become another huge challenge to be dealt with. With unclear responsibility tasks for the members of the project, the project manager will definitely involve with the planning of the construction project passively. This is due to the fact that the manager may not be certain with the responsibilities as well as the activities of the project.

#### Table 4.11: Challenges Confronting Planning Practices in the Construction of Chapels

|  | N | Minimum | Maximum | Mean | Std. Deviation |
| --- | --- | --- | --- | --- | --- |
| Inadequate Scope Definition | 50 | 1 | 5 | 3.18 | 1.480 |
| Slow Starting Pace of the Projects | 50 | 1 | 5 | 3.48 | 1.515 |
| Lack of Planning Skills | 50 | 1 | 5 | 3.20 | 1.370 |
| Inability to Get Team Members on Board | 50 | 1 | 5 | 3.12 | 1.466 |
| Unclear Responsibility tasks for project members | 50 | 1 | 5 | 3.24 | 1.393 |
| Unforeseen Circumstances | 50 | 1 | 5 | 3.06 | 1.490 |
| Passive Attitudes of Project Managers | 50 | 1 | 5 | 3.32 | 1.449 |
| Valid N (listwise) | 50 |  |  |  |  |

Source (Field Survey, 2019)

## 4.7 DISCUSSION OF RESULTS

In comparison to the literature reviewed in the chapter 2 of the study, the results of the current study will be discussed in order to determine if the results are in line with previous studies conducted on the same concept. These discussions were done according to the objectives of the study.

### 4.7.1 Project Planning Practices Needed to be Followed

Menches, et al (2008) recorded a few things that should be incorporated into the planning phase of the construction, including determination of the team members, formation of the project documentation framework, starting the obtaining of materials, creation of the calendar and timelines, and a few different activities that set up a project for execution.

Moreover, the American Society of Civil Engineers, (2012) asserted that prior to entering a contract; the owner needs to prepare general plans for construction. The key activities of project planning practices include defining the specific project goals and objectives, assessing the capabilities, evaluating resources, compliance with regulatory laws and guidelines, evaluating and preparing construction site, and reviewing construction alternatives and contractual agreements. The owner is responsible for the planning before construction contract is awarded.

The findings from the study established that the churches are of the views that identification of specific work to be performed and the goals that define the project; provision of documented estimates regarding schedule, resources and cost for planning, tracking, and controlling the project; obtaining of church board’s commitments that are planned, documented, and agreed upon and continuing the development and documentation of project alternatives, assumptions, and constraints are the planning practices that must be followed by churches in the construction of chapel projects. These are in line with Menches, et al (2008) and the American Society of Civil Engineers, (2012).

### 4.7.2 Project Planning Practices Adopted by the Churches

There were a number of project planning practices adopted by the churches as they planned for the construction of their chapels. With regards to the findings of the study, the development of project goals; identification of as many risks to the church’s project as possible and be prepared if something bad happens; creation of list of tasks that need to be carried out for each deliverable identified; the identification, by name, of the individuals and organizations with a leading role in the project. For each, describe their roles and responsibilities on the project and the specification of the number and type of people needed to carry out the project were the planning practices adopted by the churches in the planning of the construction of their chapels.

In tandem with the results, Friblick and Olsson (2009) asserted that a couple of examples of what planning can be is; flow of material plans, weekly planning meetings, resource planning, work preparation etc. To simplify how planning is conducted in a construction project, it can be described as a process where the planner tries to identify the required activities for reaching a predetermined result (Hendrickson 1998). E.g. contractors often start with a description of what the building will look like and then try to reason backwards to be able to generate the required activities to reach the desired result (Friblick and Olsson 2009). The planning process also involves estimation of required resources, estimation of the duration of tasks and identification of possible interactions between different tasks. However, there are no guarantees that a plan will not be interrupted no matter how much effort and time that are put into it (Maylor 2005).

### 4.7.3 Challenges Confronting Planning Practices in the Construction Of Chapels

Menches et al (2008) also asserted that there is solid narrative proof that tasks are frequently executed with no formal planning, and these casually planned (or impromptu) projects will in general experience a more noteworthy number of issues, for example, extreme changes, surpassing the financial limit, inability to finish the work on schedule, and low (or no) benefits. Patil, (2016) also discussed some challenges in project planning that can be also be present in the construction of chapels. These challenges include inadequate scope definition, slow pace of the projects, and lack of planning skills, inability to get team members on board, unclear responsibility/task level, uncontrolled changes and passive attitudes of project manager.

The current also discovered a couple of challenges that churches faced in their planning practices in the construction of their chapels. These challenges included lack of planning skills, unclear responsibility tasks for project members, passive attitudes of project managers and slow starting pace of the projects.

# CHAPTER FIVE

# CONCLUSIONS AND RECOMMENDATIONS

## 5.1 INTRODUCTION

The main aim of this study is to develop effective planning practices in Congregational Chapel Buildings projects. In order to make sure this aim is achieved, specific objectives for the study were formulated. This section of the thesis, took a look at the research questions and objectives in order to throw more light on the aim of the study and how that was achieved through the various stages of the study. The study further made some recommendations and conclusions on the findings of the study as well as any suggestions on future research that needed to be conducted.

## 5.2 SUMMARY OF FINDINGS

Specifically, the study sought to establish the planning Practices must be followed by churches in the construction of chapel projects, identify the planning Practices currently adopted by Churches in the construction of Chapels, examine the challenges confronting planning Practices in the construction of Chapels and make recommendations for effective project management Practices for the Churches in the Obuasi Municipality. The study adopted the quantitative research strategy of which purposive sampling was used to select the personnel of the churches who constitute the sample. Structured questionnaires were used to collect the data and descriptive statistics was the tool used in analysing the data collected.

Results from the study revealed that majority of the respondents as shown by 60% have no knowledge in project management practices while the rest of the 40% of the respondents had knowledge in project management practices. The findings from the study also showed that 58% of the respondents agreed or strongly agreed that obtaining the church board’s commitments that are planned, documented and agreed upon is a necessary procedure to following project planning.

The study revealed that, that the churches are of the views that identification of specific work to be performed and the goals that define the project; provision of documented estimates regarding schedule, resources and cost for planning, tracking, and controlling the project; obtaining of church board’s commitments that are planned, documented, and agreed upon and continuing the development and documentation of project alternatives, assumptions, and constraints are the planning practices that must be followed by churches in the construction of chapel projects.

The also revealed that the churches adopted as part of the planning practices in the construction of their chapels  by developing the project goals, identifying by name, the individuals and organization with leading role in the project; for each the roles are described as well as their responsibilities on the project, creation of document showing who is to be kept informed about the project and how they will receive the information, identifying as many risks to the church’s project as possible and be prepared if something bad happens as part of the planning practices of construction of church in the municipality.

The study discovered that lack of planning skills was a major challenge to the church officials as they plan for the construction of chapel which can be attributed to the lack of knowledge on project management practices as well as its importance in construction. Again, the issue of church officials having unclear responsibility tasks for the members of the project team might be due to the failure of these officials to create the list of things the project needs to deliver to meet those goals.

## 5.3 RECOMMENDATIONS

Based on the findings of the study, the following are the recommendations.

### 5.3.1 Engagement of Professional Project Manager

Churches should strive to employ professional project manager to be on the board of the church since there is the need to open branches of the church in several towns in the region and across the country. The project manager comes with expert knowledge of project planning procedures which would help in the building of church projects in the region and beyond.

### 5.3.2 Education of Church Board Members

Education on project management practices is very critical in the construction of the churches. The church board members especially those directly involved in the church projects needs to be educated on the project management practices so that they would have knowledge on how to follow the practices. In view of this, the productivity and efficiency of the church construction would be improved. With this in place, the challenges and difficulties encountered will be minimized or eliminated if possible.

## 5.4 RECOMMENDATIONS FOR FURTHER STUDY

The study further recommends that study on how the planning procedures of project management influence the efficiency and productivity of church projects.

## 5.5 CONCLUSION

According to Alias et al. (2014), successful construction projects basically rely on successful practices of project management in regard to planning, implementation and cost, time and quality achievements. But in the case of churches, they are mostly constrained by time and cost in executing projects compelling them to ignoring the Project Management Practices (Amponsah, 2010). Again, there is not much literature on whether Churches follow the laid down Project Management Practices in the construction of chapels in order to guide the implementation of future projects especially taking the planning phase into consideration (Prabhakar, ‎2008).

The study concludes that, churches lack knowledge in project planning procedures as well as the entire project management procedures. They are therefore faced with challenges and difficulties in the construction of their chapels. In view of this, there is the need for them to adopt all the practices needed in the church project planning by bringing on board professional project manager. The study further concludes that church board members especially those directly involved in the church projects needs to be educated on the project management practices so that they would have knowledge on how to follow the practices. Since churches are in the practice of constructing chapels in different geographical areas in order to expand their activities, it is very critical for leaders of the church to draw up policies that will guide the team members in charge of chapel construction. This can be done by making sure that the team members are fully educated on project management practices.

# REFERENCES

Abbasi, G.Y. and Al-Mharmah, H., 2000. Project management practice by the public sector in a developing country. International Journal of Project Management, 18(2), pp.105-109.

Abenlayon M. 2010. The Role of Project Management Office in Achieving Project Success, Unpublished BSc Report, Ghana Institute of Management and Public Administration, Accra

Agyekum, K., Ayarkwa, J. and Adinyira, E., 2012. Consultants’ perspectives on materials waste reduction in Ghana.

Ahadzie, D.K. and Amoa-Mensah, K., 2010. Management practices in the Ghanaian house building Industry. Journal of Science and Technology (Ghana), 30(2).

Ahadzie, D.K., 2009. Ghana in need of construction industry development agenda. Ghana Home Page, http://www. ghanaweb. com/GhanaHomepage/feature/artikel. php.

Alias, Z., Zawawi, E.M.A., Yusof, K. and Aris, N.M., 2014. Determining critical success factors of project management practice: A conceptual framework. Procedia-Social and Behavioral Sciences, 153, pp.61-69.

Al-Momani, A.H., 2000. Construction delay: a quantitative analysis. International journal of project management, 18(1), pp.51-59.

Altoryman, A., 2014. Identification and assessment of risk factors affecting construction projects in the Gulf region: Kuwait and Bahrain (Doctoral dissertation, The University of Manchester (United Kingdom)).

Amponsah, C.T., 2011. Application of multi-criteria decision-making process to determine critical success factors for procurement of capital projects under public-private partnerships. International Journal of the Analytic Hierarchy Process, 3(2).

Amponsah, R., 2010. Improving project management practice in Ghana with focus on agriculture, banking and construction sectors of the Ghanaian economy.

Artto, K.A. and Wikström, K., 2005. What is project business?. International Journal of Project Management, 23(5), pp.343-353.

Assaf, S.A. and Al-Hejji, S., 2006. Causes of delay in large construction projects. International journal of project management, 24(4), pp.349-357.

Atkinson, R., 1999. Project management: cost, time and quality, two best guesses and a phenomenon, its time to accept other success criteria. International journal of project management, 17(6), pp.337-342.

Badewi, A. and Shehab, E., 2013, September. Cost, Benefit, and Financiall Risk (CoBeFR) of ERP Implementation. In Proceedings of the 11th International Conference on Manufacturing Research (ICMR2013), Cranfield University (pp. 19-20).

Barriere, C., 2003. A study of project management development in South Africa (Doctoral dissertation).

Birkhead, M., Sutherland, M. and Maxwell, T., 2000. Core competencies required of project managers. South African Journal of Business Management, 31(3), pp.99-105.

Bradley, J., 2008. Management based critical success factors in the implementation of enterprise resource planning systems. International Journal of Accounting Information Systems, 9(3), pp.175-200.

Burke, P., 1998. The European Renaissance: centers and peripheries. Wiley-Blackwell.

Camilleri, E., 2011. Project Success. Critical factors and behaviours: Gower Publishing Limited, England.

Cao, Y. and Zhao, L., 2011. Intellectual property management model in enterprises: a technology life cycle perspective. International Journal of Innovation and Technology Management, 8(02), pp.253-272.

Caron, F., Marchet, G. and Perego, A., 1998. Project logistics: integrating the procurement and construction processes. International Journal of Project Management, 16(5), pp.311-319.

Carrie W., (2007), Research method, “Journal of Business and Economic research”, Vol 5, pp. 65-71.

Chan, D.W. and Kumaraswamy, M.M., 1996. An evaluation of construction time performance in the building industry. Building and Environment, 31(6), pp.569-578.

Chan, D.W. and Kumaraswamy, M.M., 2002. Compressing construction durations: lessons learned from Hong Kong building projects. International journal of project management, 20(1), pp.23-35.

Chih, Y.Y. and Zwikael, O., 2015. Project benefit management: A conceptual framework of target benefit formulation. International Journal of Project Management, 33(2), pp.352-362.

Child, J. and McGrath, R.G., 2001. Organizations unfettered: Organizational form in an information-intensive economy. Academy of management journal, 44(6), pp.1135-1148.

Cleland, D.I. and Ireland, L.R., 2002. Project management: strategic design and implementation (Vol. 4). New York: McGraw-Hill.

Cole, L.J.R., 1991. Construction scheduling: principles, practices, and six case studies. Journal of Construction Engineering and Management, 117(4), pp.579-588.

Cooke-Davies, T.J., 2001. Towards improved project management practice: Uncovering the evidence for effective practices through empirical research. Universal-Publishers.

Cooke-Davies, T.J., Schlichter, J. and Bredillet, C., 2001, November. Beyond the PMBOK guide. In Proceedings of the 32nd Annual Project Management Institute 2001 Seminars and Symposium, Nashville, TN.

Crawford, et al., 2006. Practitioner development: From trained technicians to reflective practitioners. International Journal of Project Management, 24(8), pp.722-733.

Cserháti, G. and Szabó, L., 2014. The relationship between success criteria and success factors in organisational event projects. International Journal of Project Management, 32(4), pp.613-624.

Dalcher, D., 2012. Book Review: Project Management for the Creation of Organisational Value.

Dawson, R.J. and Dawson, C.W., 1998. Practical proposals for managing uncertainty and risk in project planning. International Journal of Project Management, 16(5), pp.299-310.

de Ligny, E.V.E.D. and Erkelens, P., 2008. Construction technology diffusion in developing countries: limitations of prevailing innovation systems. Journal of Construction in Developing Countries, 13(2).

Dean, R.W., 1950. Summer Control of Orchard Mites in eastern New York. Journal of Economic Entomology, 43(2).

Dhalla, N.K. and Yuspeh, S., 1976. Forget the product life cycle concept. Harvard Business Review, 54(1), pp.102-112.

Dobson, M.S., 1996. Practical project management: Secrets of managing any project on time and on budget. SkillPath Publications.

Dvir, D., et al., 2003. An empirical analysis of the relationship between project planning and project success. International journal of project management, 21(2), pp.89-95.

Egbu, C.O., 1999. Skills, knowledge and competencies for managing construction refurbishment works. Construction Management & Economics, 17(1), pp.29-43.

El-Razek, M.E., et al., 2008. Causes of delay in building construction projects in Egypt. Journal of construction engineering and management, 134(11), pp.831-841.

El-Sabaa, S., 2001. The skills and career path of an effective project manager. International journal of project management, 19(1), pp.1-7.

Escamilla, E., 2011. Investigation of Project Management Planning practices for renovation of historical buildings in urban contexts located in Texas. Texas A&M University.

Faniran, O.O., et al., 1999. Optimal allocation of construction planning resources. Journal of Construction Engineering and Management, 125(5), pp.311-319.

Feilden, B., 2003. M. (1982), Conservation of historic buildings.

Freeman, K.C., 2010. The HERMES Project: Reconstructing Galaxy Formation. In Galaxies and their Masks (pp. 319-326). Springer, New York, NY.

Gidman, J., 2001. The role of the personal tutor: a literature review. Nurse Education Today, 21(5), pp.359-365.

González, S.A., Sarmiento, O.L., Cohen, D.D., Camargo, D.M., Correa, J.E., Páez, D.C. and Ramírez-Vélez, R., 2014. Results from Colombia’s 2014 report card on physical activity for children and youth. Journal of Physical Activity and Health, 11(s1), pp. S33-S44.

Goodwin RSC 1993. Skills Required of Effective Project Managers, Journal of Management in Engineering, ASCE, 1993, Vol. 9 pp. 217-226

Gow, D.D. and Morss, E.R., 1988. The notorious nine: Critical problems in project implementation. World Development, 16(12), pp.1399-1418.

Gyadu-Asiedu, W., 2009. Assessing construction project performance in Ghana: Modelling practitioners’ and clients’ perspectives. Eindhoven: Technische Universiteit.

Hobday, M., 2000. The project-based organisation: an ideal form for managing complex products and systems?. Research policy, 29(7-8), pp.871-893.

Hussein, B.A. and Klakegg, O.J., 2014. Measuring the impact of risk factors associated with project success criteria in early phase. Procedia-Social and Behavioral Sciences, 119, pp.711-718.

Jackson, T., 2004. Management and change in Africa: A cross-cultural perspective. Psychology Press.

Jugdev, K. and Müller, R., 2005. A retrospective look at our evolving understanding of project success. Project management journal, 36(4), pp.19-31.

Kaming, P.F., Olomolaiye, P.O., Holt, G.D. and Harris, F.C., 1997. Factors influencing construction time and cost overruns on high-rise projects in Indonesia. Construction Management & Economics, 15(1), pp.83-94.

Kerzner, H., 2003. Advanced project management: Best practices on implementation. John Wiley & Sons.

Kerzner, H., 2017. Project management: a systems approach to planning, scheduling, and controlling. John Wiley & Sons.

Kissi, E., 2013. Empirical understanding of the status of professional project management practices in the Ghanaian building industry (Doctoral dissertation).

Kotler, P. and Keller, K., 2012. Dirección de marketing (Decimocuarta ed.). Naucalpan de Juárez: Pearson Education.

Kumaraswamy, M.M. and Chan, D.W., 1998. Contributors to construction delays. Construction Management & Economics, 16(1), pp.17-29.

Laufer, A. and Cohenca, D., 1990. Factors affecting construction-planning outcomes. Journal of Construction Engineering and Management, 116(1), pp.135-156.

Leedy, P. and Ormrod, J. 2001. Practical research: Planning and design (7th ed.). Upper Saddle River, NJ: Merrill Prentice Hall.  Thousand Oaks: SAGE Publications.

Le-Hoai, L., et al., 2008. Delay and cost overruns in Vietnam large construction projects: A comparison with other selected countries. KSCE journal of civil engineering, 12(6), pp.367-377.

Levitt, T., 1965. Exploit the product life cycle. Harvard business review, 43, pp.81-94.

Love, P.E. and Li, H., 2000. Quantifying the causes and costs of rework in construction. Construction Management & Economics, 18(4), pp.479-490.

Luu, D.T., Ng, S.T. and Chen, S.E., 2003. A case-based procurement advisory system for construction. Advances in Engineering Software, 34(7), pp.429-438.

Maylor, H., Brady, T., Cooke-Davies, T. and Hodgson, D., 2006. From projectification to programmification. International Journal of Project Management, 24(8), pp.663-674.

Menches, et al, 2008. Impact of pre‐construction planning and project characteristics on performance in the US electrical construction industry. Construction Management and Economics, 26(8), pp.855-869.

Mercer, D., 1993. A two‐decade test of product life cycle theory. British Journal of Management, 4(4), pp.269-274.

Mezher, T.M. and Tawil, W., 1998. Causes of delays in the construction industry in Lebanon. Engineering, construction and architectural management, 5(3), pp.252-260.

Midler, C., 1995. “Projectification” of the firm: The Renault case. Scandinavian Journal of management, 11(4), pp.363-375.

Mitropoulos, P. and Howell, G.A., 2002. Renovation projects: Design process problems and improvement mechanisms. Journal of Management in Engineering, 18(4), pp.179-185.

Morris, C., 1993. The Birsay Bay Project: a résumé. The Viking Age in Caithness, Orkney and the North Atlantic, 294.

Morris, P. W. G. 1998. Key issues in project management, in J. K. Pinto, ed., 'Project Management Institute Project Management handbook', Newtown Square, PA: Project Management Institute.

Munns, A.K. and Bjeirmi, B.F., 1996. The role of project management in achieving project success. International journal of project management, 14(2), pp.81-87.

Murphy, A. and Ledwith, A., 2007. Project management tools and techniques in high-technology SMEs. Management research news, 30(2), pp.153-166.

Mutijwaa, P. and Rwelamila, D., 2007. Project Management Competence in Public Sector Infrastructure Organisation. Construction Management and Economics, 25(1), pp.55-66.

Nwachukwu, C.C. et al., 2010 “Project Management Factor Indexes; a Constraint to Project Implementation Success in the Construction Sector of a Developing Economy European” Journal of Scientific Research ISSN 1450-216X Vol.43 No.3 (2010), pp.392-40

Ofori, G., 1989. Housing in Ghana: the case for a central executive agency. Habitat International, 13(1), pp.5-17.

Ofori, G., 2003. Frameworks for analysing international construction. Construction Management and Economics, 21(4), pp.379-391.

Ogunlana, S.O., et al., 1996. Construction delays in a fast-growing economy: comparing Thailand with other economies. International Journal of project management, 14(1), pp.37-45.

Ohara, S., 2005. A guidebook of project and program management for enterprise innovation. Management Association of Japan.

Oisen RP 1971. Can Project Management Be Defined? Project Management Quarterly 2(1):12-14

Palmer-Atkins, C.B., 2018. An Exploratory Study of a Nondenominational Church and Leadership Behaviors, Principles, Strategies, and Practices.

Patil, G.V.2016 Project Management Challenges. Project Management, 3(11)

PMI Standards Committee, 1996. A guide to the project management body of knowledge. Project Management Institute.

Polli, R. and Cook, V., 1969. Validity of the product life cycle. The Journal of Business, 42(4), pp.385-400.

Prabhakar, G.P., 2008. What is project success: a literature review? International Journal of Business and Management, 3(9), pp.3-10.

Project Management Institute. (2008). A guide to the project management body of knowledge (PMBOK ® Guide) (6th ed.). Newton Square, PA: Project Management Institute.

Rad, P.F. and James, B.M., 1983. The layout of temporary construction facilities. Cost Engineering, 25(2), pp.19-27.

Reiss, M., 1995. Bridled ambition: Why countries constrain their nuclear capabilities. Woodrow Wilson Center Press.

Robson, R., 1999. Object-oriented instructional design and applications to the web. In EdMedia+ Innovate Learning (pp. 698-702). Association for the Advancement of Computing in Education (AACE).

Rwelamila, P.D. and Meyer, C., 1999. Appropriate or default project procurement systems?. Cost Engineering, 41(9), p.40.

Rwelamila, P.M.D., 2007. Project management competence in public sector infrastructure organisations. Construction Management and Economics, 25(1), pp.55-66.

Sanvido, V., et.al., 1992. Critical success factors for construction projects. Journal of construction engineering and management, 118(1), pp.94-111.

Sessions, R., 2009. The IT complexity crisis: Danger and opportunity. White paper, November.

Shenhar, A.J. and Wideman, R.M., 1996. Project management: from genesis to content to classification. Operations Research and Management Science (INFORMS), Washington, DC.

Slevin, D.P. and Pinto, J.K., 2007. An overview of behavioral issues in project management. The Wiley guide to project organization & project management competencies, pp.1-19.

Stuckenbruck, L.C. and Zomorrodian, A., 1987. Project management: the promise for developing countries. International Journal of Project Management, 5(3), pp.167-175.

Szymczak, C.C. and Walker, D.H., 2003. Boeing–a case study example of enterprise project management from a learning organisation perspective. The Learning Organization, 10(3), pp.125-137.

Thomas, et al., 2008. Developing an effective project: Planning and team building combined. Project Management Journal, 39(4), pp.105-113.

Thomas, J. and Mengel, T., 2008. Preparing project managers to deal with complexity–Advanced project management education. International journal of project management, 26(3), pp.304-315.

Thwala, W.D. and Mvubu, M., 2008. Current challenges and problems facing small and medium size contractors in Swaziland. African Journal of Business Management, 2(5), pp.093-098.

Turner, I.M., 1994. Sclerophylly: primarily protective?. Functional ecology, 8(6), pp.669-675.

Turner, J.R., 1994. Project management: future developments for the short and medium term.

Udo, N. and Koppensteiner, S., 2004. What are the Core Competencies of a Successful Project Manager?. na.

Wang, Y.R. and Gibson Jr, G.E., 2008. A study of preproject planning and project success using ANNs and regression models. Automation in Construction, 19(3), pp.341-346.

Westland, J., 2007. The Project Management Life Cycle: A Complete Step-by-step Methodology for Initiating Planning Executing and Closing the Project. Kogan Page Publishers.

Wideman, R.M., 2003. Modeling project management. AEW Services, Vancouver, BC.

Winch, G.M. and Kelsey, J., 2005. What do construction project planners do? International Journal of Project Management, 23(2), pp.141-149.

# APPENDIX I

QUESTIONNAIRE

My name is Bright Frank Ayifli, a student of Kwame Nkrumah University of Science and Technology (KNUST) pursuing _____________________________________________. I am conducting a research on the topic “Investigating Project Management Practices in Churches: A Case of construction of Chapels” leading to Master’s Degree.

This questionnaire is meant to solicit information for the purpose of the research. All information gathered is purposely for the research and will be treated with strict confidentiality. Kindly answer the following questions by either ticking the appropriate answer or just stating your opinion.

SECTION I – DEMOGRAPHIC DATA

1. Age:

18-25 [ ] 	26-34 [ ]	 35-44 [ ] 	45-54 [ ]

2.	Educational level

Basic/SHS [ ] 	Senior High/Technical/Vocation [ ] 	Tertiary [ ]

Others specify………………………………………………………………………

3. Marital status:	Single [ ] 	Married [ ] 	Separated/Divorced [ ]

4. Position in the Church……………………………………………………………….

5. Do you have any knowledge in project management practices?  Yes [ ]		No [ ]

SECTION II – PROJECT PLANNING PROCEDURES FOLLOWED

The following procedures are you usually followed in the construction of projects generally. Please indicate your level of agreement with the following statements based on the extent to which your church organization follows these planning procedures. Indicate the level of agreement by ticking the appropriate number using the key given below:

: 5 = strongly agree 4= Agree 3=Neutral 2 = Disagree 1= strongly Disagree

| PROJECT PLANNING PROCEDURES FOLLOWED | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| - Identifies specific work to be performed and the goals that define the chapel project |  |  |  |  |  |
| - Provides documented estimates regarding schedule, resources and cost for planning, tracking, and controlling the chapel project |  |  |  |  |  |
| - Obtains church board’s commitments that are planned, documented, and agreed upon |  |  |  |  |  |
| - Continues the development and documentation of chapel project alternatives, assumptions, and constraints |  |  |  |  |  |
| - Establishes a baseline of the plan from which the chapel project will be managed |  |  |  |  |  |
| - Others state |  |  |  |  |  |

SECTION III: PROJECT PLANNING PROCEDURES ADOPTED

Indicate your level of Agreement on the following statements by ticking the appropriate number using the key given below: 5 = Very Important 4= Important 3=Neutral 2 = Not Important 1= Not at all Important

| PROJECT PLANNING PROCEDURES ADOPTED | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| - Development of chapel project Goals |  |  |  |  |  |
| - Create a list of things the chapel project needs to deliver to meet those goals |  |  |  |  |  |
| - Create a list of tasks that need to be carried out for each deliverable identified |  |  |  |  |  |
| - Identify, by name, the individuals and organizations with a leading role in the chapel project. For each, describe their roles and responsibilities on the chapel project |  |  |  |  |  |
| - Specify the number and type of people needed to carry out the project |  |  |  |  |  |
| - Create a document showing who is to be kept informed about the project and how they will receive the information. |  |  |  |  |  |
| - Identify as many risks to the church’s chapel project as possible and be prepared if something bad happens. |  |  |  |  |  |
| - Others state |  |  |  |  |  |

SECTION IV: CHALLENGES CONFRONTING PLANNING PROCEDURES IN THE CONSTRUCTION OF CHAPELS

Indicate your level of Agreement on the following statements by ticking the appropriate number using the key given below: 5 = Very Serious Challenge 4= Serious Challenge 3=Moderate Challenge 2 = Minor Challenge 1= Not at a Challenge

| CHALLENGES CONFRONTING PLANNING PROCEDURES IN THE CONSTRUCTION OF CHAPELS | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| - Inadequate Scope Definition |  |  |  |  |  |
| - Slow Starting Pace of the Projects |  |  |  |  |  |
| - Lack of Planning Skills |  |  |  |  |  |
| - Inability to Get Team Members on Board |  |  |  |  |  |
| - Unclear Responsibility tasks for project members |  |  |  |  |  |
| - Unforeseen Circumstances |  |  |  |  |  |
| - Passive Attitudes of chapel project Managers |  |  |  |  |  |
| - Others state |  |  |  |  |  |