AN ASSESSMENT OF PROJECT SCHEDULE MANAGEMENT AT THE GHANA PORTS AND HARBOURS AUTHORITY

By

Ebo Kobina Simpson

(BSc. Construction Technology and Management)

A Thesis Submitted to the Department of Construction Technology and Management, Kwame Nkrumah University of Science and Technology, Kumasi, in partial fulfilment of the requirements for the degree of

MASTERS OF SCIENCE IN PROJECT MANAGEMENT

November,2019

DECLARATION

I hereby declare that this submission is my own work and that, to the best of my knowledge and belief, it contains no material previously published or written by another person nor material which to a substantial extent has been accepted for the award of any other degree or diploma at Kwame Nkrumah University of Science and technology, Kumasi or any other educational institution, except where due acknowledgement is made in the thesis.

Ebo Kobina Simpson (PG5328418)    …………………….   ……………………

Student                                                    Signature                    Date

Certified by:

Dr. Emmanuel Adinyira                   …………………….      …………………….

Supervisor                                             Signature                      Date

Certified by:

Prof. Bernard Kofi Baiden               …………………….      …………………….

Head of Department                             Signature                       Date

# ABSTRACT

Developing project plan and schedule is a critical task in the management of any project. The planning obviously requires competent and experienced personnel. Unfortunately, the emerging trends suggest a skill shortage in the area of project planning. Compounding this problem of skills shortage is the limited time experienced project managers have to plan on most projects whereas construction processes are becoming more complex and logistically challenging. To bridge these gaps, this study is designed to achieve this aim; ‘to assess project schedule management at the Ghana Ports and Harbours Authority’ through the achievement of the following objectives; To identify the various techniques, tools and methods used in scheduling projects executed by/for the GPHA, to identify factors that affect project schedule management and to identify the challenges project managers face in the use of project scheduling techniques and methods. It was found that Microsoft Project, PERT, and Critical Path Method are important techniques/tools used in scheduling projects. Project complexity, team experience, task dependencies, deadline, stakeholders, and budget are the most important factors that affect project schedule management. Lack of project management training, role of senior leadership, triple constraints, human or people factors, poor adoption of project are the key challenges of schedule management. Simplifying of project, ensuring good training for project teams, setting project time are recommended by this study as ways of improving on project schedule management.

TABLE OF CONTENTS

DECLARATION	i

ABSTRACT	ii

LIST OF TABLES	vi

LIST OF FIGURES	vii

DEDICATION	ix

CHAPTER ONE	1

GENERAL INTRODUCTION	1

1.1 BACKGROUND	1

1.2 PROBLEM STATEMENT	2

1.3 AIM	3

1.4 OBJECTIVES	3

1.5 RESEARCH QUESTIONS	3

1.6 SCOPE OF THE STUDY	4

1.7 RESEARCH DESIGN	4

1.8 SIGNIFICANCE OF THE STUDY	4

1.9 ORGANISATION OF THE STUDY	5

1.10 RECOMMENDATIONS FOR FUTURE RESEARCH	5

CHAPTER TWO	7

LITERATURE REVIEW	7

2.1 INTRODUCTION	7

2.2 PROJECT SCHEDULE MANAGEMENT	7

2.2.1 Schedule Planning	7

2.2.2 Schedule Development	10

2.2.3 Schedule Control	11

2.3 PROJECT SCHEDULING TECHNIQUES AND TOOLS	12

2.3.1 Program Evaluation Review Technique (PERT)	12

2.3.2 Critical Path Method	13

2.3.3 Celoxis	14

2.3.4 Hive	15

2.3.5 Projectmanager.com	15

2.3.6 Monday.com	16

2.3.7 Mavenlink	16

2.3.8 GanttPRO	16

2.3.9 Microsoft Project Online	17

2.3.10 Wrike	17

2.3.11 Asana	18

2.4 MEASUREMENT OF PROJECT SCHEDULE PERFORMANCE	18

2.4.1 Earned Value Measurement	18

2.5 PROJECT SCHEDULE MANAGEMENT CHALLENGES	19

2.5.1 Implementation Challenges	19

2.5.2 Role of Senior Leadership	19

2.5.3 Human or People Factors	20

2.5.4 Triple Constraints	20

2.5.5 Project management office (PMO) or No Project management office (PMO)	21

2.5.6 Poor Adoption of Project Management Standards	21

2.5.7 Lack of PM training	22

2.6 FACTORS THAT AFFECTS PROJECT SCHEDULE MANAGEMENT	22

2.7 SUMMARY OF CHAPTER	26

CHAPTER THREE	28

RESEARCH METHODOLOGY	28

3.1 INTRODUCTION	28

3.2 DESIGN OF THE STUDY	28

3.2.1 Research Design	28

3.2.2 Research Method	28

3.3.2 Data Collection Methods	29

3.4 Data Analysis	30

3.4.1 Relative Important Index (RII)	30

3.5 SAMPLING	31

3.5.1 Population	31

3.5.2 Sample Size	32

3.5.3 Sampling Technique	33

CHAPTER FOUR	35

DATA PRESENTATION AND DISCUSSION	35

4.1 Introduction	35

4.2 Results of the Survey	35

4.3 DEMOGRAPHIC VARIABLES	35

4.3.1 Levels of Education	36

4.3.2 Years of Experience	37

4.3.3 Conversance level of respondent	38

4.4 TECHNIQUES, TOOLS AND METHODS USED IN SCHEDULING PROJECTS EXECUTED BY/FOR THE GPHA	38

4.5 CHALLENGES PROJECT MANAGER’S FACE IN THE EFFECTIVE USE OF PROJECT SCHEDULING TECHNIQUES AND METHODS	40

4.6 FACTORS THAT AFFECTS PROJECT SCHEDULE MANAGEMENT.	41

4.7 SUMMARY	44

CHAPTER FIVE	45

CONCLUSION AND DISCUSSION	45

5.1	Introduction	45

5.1 SUMMARY OF FINDINGS	45

5.1.1 Objective One	45

5.1.2 Objective Two	45

5.1.3 Objective Three	46

5.2 CONCLUSIONS	47

REFERENCES	48

APPENDIX 1	50

QUESTIONNAIRE	50

# LIST OF TABLES

Table 4.1: Techniques, Tools And Methods	39

Table 4.2: Challenges Project Managers Face	40

Table 4.3: Factors That Affects Project Schedule Management	42

Table 4.4: Client Responses With Respect To Techniques, Tools And Methods Used In Scheduling Projects By Gpha	43

# LIST OF FIGURES

Figure 4.1: Level Of Education	36

Figure 4.2: Years Of Experience	37

Figure 4.3: Conversant Level Of Respondent	38

ACKNOWLEDGEMENTS

I wish to thank God Almighty. I am grateful to all Lecturers of this training.

Special thanks to my partner and wife, Efua Mensima Simpson and our kids Kobina, PapaKojo and Maame Efua. This one is for you.

# DEDICATION

I dedicate the project report to the Almighty God for His guidance and protection throughout this study.

I dedicate this work also to my Wife and Kids and my entire family for their support and understanding as well as encouragement.

# CHAPTER ONE

# GENERAL INTRODUCTION

## 1.1 BACKGROUND

Project scheduling is a mechanism for communicating which tasks need to be accomplished and which organizational resources will be allocated in which timeframe to complete those tasks. A project schedule is a document collecting all the work required for timely delivery of the project (Weglarz, 2019).  Invariably, successful projects lead to increased profit and effectiveness. One of the main duties of project management (PM) is the successful completion and delivery of any project, involving project planning and scheduling (Hancher, 2003; Li et al., 2012). Furthermore, comprehensive planning and scheduling are of utmost importance for both construction and civil works (Chau et al., 2005). Planning is the springboard of all initiatives that all other activities are or are dependent on (Li et al., 2012). Planning, however, is onerous, complex and time-consuming above all. In order to accommodate future changes, due to its complicated nature project plans are flexed. This may be summarized by Li et al. (2012) in the declaration− at the first attempt even seasoned building managers consider it difficult to build / design an extensive and faultless master building scheme.

Efforts to plan, direct and regulate project operations to guarantee achievement have been produced for many years (Hancher, 2003). There was no usually accepted project management method until recently. Project management was based on Project Managers ' level of knowledge and intuition. As a result, each PM had a distinct scheme that generally included using the Gantt graph or bar chart (Hancher, 2003). However, the need to create complicated instruments that encapsulate the complicated demand of projects became evident as projects became more complicated.  As a result, the network analysis was created. Several efforts have since been made to create even more complicated instruments that meet modern project demands. However, in latest years, much study has concentrated on simulating and visualizing project plans to decrease highway building time and issues.

According to Allen and Smallwood (2008), project planning and scheduling have existed for several years; however, it has been focused more sharply on the overall lack of competence. To this end, Allen and Smallwood (2008) rightly believed that construction planning would play an increasingly critical role in the infrastructure sector, and more so because of the unprecedented development of the sector.

## 1.2 PROBLEM STATEMENT

Developing a project plan and timeline is a critical job in managing any project (Hendrickson, 2000, Heesom and Mahdjoubi, 2004). Obviously, planning needs skilled and experienced staff (Illingworth, 2000). Unfortunately, the evolving trends indicate a lack of project scheduling skills (Heesom and Mahdjoubi, 2004). There are far fewer accessible skilled planners than is needed (Allen and Smallwood, 2008). Compounding this skill shortage issue is the restricted amount of time that project executives have to plan for most building and IT projects (Kelsey et al., 2001). Building procedures are also becoming more complicated and difficult logistically (Allen and Smallwood, 2008).

The research will investigate the planning procedures and techniques described in the Ghana Ports and Harbors Authority, GPHA, with these gaps identified.

## 1.3 AIM

Assess project schedule management of projects at the Ghana Ports and Harbours Authority is the aim of the study.

## 1.4 OBJECTIVES

To be able to achieve the above mentioned aim the following objectives were set:

- To identify the various techniques, tools and methods used in scheduling projects executed by/for the GPHA

- To identify factors that affect project schedule management.

- To identify the challenges project managers, face in the effective use of project scheduling techniques and methods.

## 1.5 RESEARCH QUESTIONS

This study is designed to answer the following questions:

- What techniques, tools and methods were used in scheduling projects executed by/for the GPHA?

- How well do projects undertaken by/for the GPHA perform based on the project techniques, tools and methods used?

- What are the challenges project managers face in the effective implementation of project schedule techniques and methods?

## 1.6 SCOPE OF THE STUDY

Geographically, this study was limited in scope to the Ghana Ports and Harbours Authority, Takoradi Port. One of the reasons for the selection of GPHA for this study is proximity to researchers and also, access to information. There are a lot of construction activities currently going on in the Port. The focus of this study was selected projects at the Ghana Ports and Harbours Authority. The scope is limited to construction works executed between 2016 to date whether complete or not.

## 1.7 RESEARCH DESIGN

The approach adopted for this study was considered in three aspects: research philosophy, the research strategy, and the specific research method. With respect to the philosophy, the study adopted a constructivist paradigm. Based on this philosophical paradigm, the aim and objectives, and the number of respondents, the study adopted a quantitative research design strategy. It was a case study of the Takoradi Port Authority of Ghana Ports and Harbours. A set of semi-structured questionnaires with closed-ended issues was the research tool intended to gather information for the study. The findings were gathered using techniques of quantitative research approach involving questionnaire administration. The information was then analysed using quantitative analytical instruments for information.

## 1.8 SIGNIFICANCE OF THE STUDY

Other than the fact that project schedule management as a knowledge area in Project Management helps to cut off unnecessary wastage of time, resources, and project costs, this study is very important in the sense that preliminary literature review indicates the need to expand the scope of study into project schedule management, especially in developing countries. A number of developed nations, according to Twumasi (2015), have devoted the last decade to finding methods to streamline building operations, particularly in bridges and highway construction. Twumasi (2015) further indicated that while the findings of the developed nations are more compelling to disregard, its implementation in Ghana's construction industry is not practical due, among other factors, to variations in a cultural context. In perspective of this, it is extremely probable that this research will benefit stakeholders managing building projects in Ghana, building planners and project managers.

## 1.9 ORGANISATION OF THE STUDY

This thesis is organised into five chapters. Chapter One comprises brief background of the study, problem statement, aims and objectives of the study, research questions, significance of the study and the scope of the study. Chapter Two reviews literature such as books, book sections, articles in journals and periodicals, published and unpublished theses related to the topic researched. Chapter Three discusses the methodology with which the research was undertaken. It included the research strategy and approach, primary and secondary sources of data; population and sampling techniques, as well as how data collected through were analysed. Chapter four presents and analysed the data collected. Lastly, conclusion, remarks and recommendation based on the findings was discussed in Chapter Five.

## 1.10 RECOMMENDATIONS FOR FUTURE RESEARCH

The stated initial aim of this Thesis was to assess project schedule management of projects at the Ghana Ports and Harbours Authority. During the research, it became evident that, schedule management goes hand in hand with the cost of the project.

It is recommended that this research will be done for all projects by/for the Ghana ports and harbours Authority, to ascertain if the finding do actually cut across the the entire organisation.

Secondly, as stated above, the use of earned value can also be used against the schedule and cost timelines to determine how much is lost when schedule is not managed properly. This I believe will be good information for the management.

# CHAPTER TWO

# LITERATURE REVIEW

## 2.1 INTRODUCTION

This chapter presents a review of literature for this research. Relevant literature pertaining to the scheduling of work in the Ghana Ports and Harbour Authority were reviewed. The Concept of project scheduling management, types of schedule, project schedule tools and techniques, measures and challenges of project schedule performance are examined in this chapter as well as the factors that affect project schedule management

## 2.2 PROJECT SCHEDULE MANAGEMENT

Schedule management includes the required processes for the timely completion of the project. But typically, a project manager should have a job breakdown framework (WBS), an estimate of effort for each task, and a resource list with accessibility for each resource prior to the creation of a project schedule. A schedule is created using a consensus-driven estimation method; the reason for this is that a schedule itself is an estimate: each date is estimated in the schedule, and if those dates don't have the buy-in of the people who will do the job, the schedule will be inaccurate.

### 2.2.1 Schedule Planning

After the initiation stage, the project is planned to an appropriate level of detail. The planning process group helps gather information from sources with each having varying level of completeness and confidence (PMI’s PM BOK Guide, 3rd Edition 46). Planning is done for time, cost, resources and risk management during execution. Project planning is an iterative and ongoing process throughout the project's life. Hinze (2004) claim that the method of project planning contributes to the growth and maintenance of a workable system to fulfil the project's company requirements. It involves defining general scope, identifying scheduling strategy, creating cost and timetable work breakdown structure, refining estimates and commitments analysis, optimizing the project plan, creating risk management plans, and arranging the project team to create a project-driven organizational atmosphere. According to Kerzner (2003), the planning process consist of developing the scope statement, risk planning, determining how to plan, identifying the deliverables and creating a work break down structure (WBS), selecting the planning team, estimating the resource requirement for the activities, identifying the activities needed to complete those deliverables and networking the activities in logical sequence, estimating time and cost for the activities, gaining formal approval to begin work, developing a budget and schedule.

Ghana Ports and Harbours Scheduling Planning Process is an ongoing process that starts from the time an investment decision is made and goes through to project delivery. As recognized by Dvir, Raz and Shenhar (2003), this process can be differentiated into three primary stages:

- End-user level, where planning focuses mainly on the functional features of the project end product;

- technical level, which focuses on the technical specifications of the project deliverables required to help functional demands;

- project management level, which focuses on planning the operations and procedures to be carried out to guarantee that I have functional demands;

These levels are further explained by Dvir et al. (2003) as the phases of project delivery. A very significant element of planning any project is to produce a suitable project schedule that places all the project's duties in a logical and sequential order. Variations in the series of assignments may be feasible depending on the sort of project tasks. The start and end dates of each assignment, their corresponding length, their relationships and dependence on other tasks and the kinds of dependence between different tasks will be included in a fundamental timetable. Some extra data like floating between one assignment and the other may also be included in the schedules (Zanen and Hartmann, 2010). We must first define the activities, sequence them in the right order, estimate the resources needed, and estimate the time it will take to complete the tasks in order to develop our schedule (Hinze, 2004).

A further breakdown of the WBS work package components is the activity definition method. The specific activities needed to fulfil the deliverables detailed in the WBS are documented. These activities are not the results themselves, but the individual work units that have to be completed in order to fulfil the results (Hinze, 2004). Activity definition utilizes everything about the project that we already understand to split the job into operations that can be estimated. You may want to look at all the lessons that your business has learned from comparable projects to get a good idea of what you need to do on the present one.

Expert judgment in the form of project team members who have previous experience in developing statements of project scope and WBS can help you define activities. If you are asked to handle a project in a fresh domain, experts in that specific sector may also be used to assist identify duties so that you can comprehend what activities are going to be involved. You may want to produce a list of activities and then have it reviewed by the specialist and propose modifications. Alternatively, from the very start you could involve the specialist and ask to have an activity definition discussion with him or her before you even make your first draft of the list. You begin a project sometimes without understanding much about the job you're going to do later. Rolling-wave planning allows you to plan and schedule only the part you understand to plan well (Hinze, 2004). You can use placeholders for the unknown portions until you understand more when you don't know enough about a project. These are additional things that are placed in the WBS at elevated concentrations so you can plan for the unknown.

### 2.2.2 Schedule Development

A schedule in project management is a listing of the milestones, activities, and outcomes of a project, usually with planned start and finish dates. These products are often estimated by dependencies and planned occurrences in terms of resource allocation, budget and length. A timetable is widely used as part of project management in project planning and project portfolio management. Elements on a schedule may be closely related to terminal elements of the "Work Breakdown Structure," the Statement of Work, or a List of Contract Data Requirements. The development and maintenance of the project schedule is the responsibility of a full-time scheduler or team of schedulers in many industries, such as engineering and construction, depending on the size of the project schedule management includes the processes needed to ensure timely project completion. But typically, a project manager should have a job breakdown framework (WBS), an estimate of effort for each task, and a resource list with accessibility for each resource prior to the creation of a project schedule. A schedule is created using a consensus-driven estimation method; the reason for this is that a schedule itself is an estimate: each date is estimated in the schedule, and if those dates do not have the buy-in of the people who will do the job, the schedule will be inaccurate.

Development comprises of the procedures used to finish the project management plan established to fulfil project demands (PM BOK Guide 3rd, 55). It includes the coordination of individuals and resources and the integration and execution of project operations in accordance with the project management plan. During the execution phase, actual project work is performed. The PMBOK Guide, 3rd edition 56–58 defines the operations that are being carried out as

- Direct and manage project execution

- Perform quality assurance

- Acquire project team

- Develop project team

- Information distribution

- Select sellers

### 2.2.3 Schedule Control

Monitoring and control comprise of those procedures conducted to monitor the execution of the project in order to identify prospective issues in a timely way and to take corrective action if needed. (PMI, 3rd edition of PM BOK, 59). The method of project control guarantees that project goals are achieved by evaluating progress and taking corrective action when needed. It involves gathering the status of project advancement, analysing variances and communicating the status of the project. The main advantage of surveillance and controlling is that the performance of the project is frequently observed and analysed to detect variances from the project management plan. Dye (2002) shows that it includes operations of surveillance and control;

- Measuring (where we are) continuing project activities.

- Monitoring of project variables against the project management plan (cost, time, scope, quality).

- Identify corrective activities to adequately tackle problems and hazards.

- Influencing factors that might bypass integrated change control in order to implement only authorized modifications.

## 2.3 PROJECT SCHEDULING TECHNIQUES AND TOOLS

PM has many complicated tasks and is a difficult job. Fortunately, there are many instruments available to assist accomplish the duties and fulfil the duties. Some need a laptop that supports software, while others can be manually used. Project managers should choose a project management tool that suits their management style best. No tool addresses all project management demands. The Technique for Program Evaluation Review (PERT) and Gantt Charts are two of the most frequently used instruments for project management and are explained below. Both of these project management tools can be manually generated with project management software that is commercially accessible.

### 2.3.1 Program Evaluation Review Technique (PERT)

In the late 1950s, the U.S. Navy created the PERT Program Evaluation Review Technique for the Ballistic Missile Program to discover an easy system for managing and organizing complicated goals and thousands of companies. Activities are listed in this technique, activity durations are determined using three estimation methods, dependencies are established between the activities and the longest path is recognized through forward and backward calculations. The list below is the estimate principle are;

- Most Likely Estimate

- Optimistic Estimate

- Pessimistic Estimate

Just like in CPM, to plan a project using PERT, you will need to first define assignments and their order based on the milestones of your project. Using a CPM-like network structure composed of these duties, distinct timelines for a project can be estimated based on the level of trust:

- Duration compression

- Most-likely timing

- Optimistic timing

- Pessimistic timing

### 2.3.2 Critical Path Method

Let's look first at the CPM. Think of the critical path as of the tree diagram of your project. The Critical Path Method enables you discover the longest timeline and the shortest timeline for the project. You can also label critical assignments with the CPM and those that can float. The timetable will not be affected by changes in the shipment of the latter.

In order to use the CPM, you need to know the scope of your project and all the tasks required to complete it. Next, estimate the duration of each assignment. You ought to also notice all dependencies among the duties after that. This way you understand which ones you can do individually and which ones you need to complete prior assignments. Finally, add milestones and results to your project. The technique of critical path is a sophisticated technique of scheduling created in the late 1950s. It was then used to schedule any sort of projects, including building, aviation and defence, creation of software, IT, etc. Activities are connected by using dependencies in a network diagram in this technique. These groups of activities form routes. The critical path is the network diagram's shortest path. Activities are listed in this technique, durations of activity are determined, dependencies are established between the activities and the longest path is recognized through forward and backward calculations. The critical path method is a visual technique that allows the same diagram to display operations, activity dependencies and durations.

Since you already understand what a critical path is, this is a different way to use it. Fast-tracking enables you to discover assignments that can be accomplished at the same time or partly overlapped to accelerate delivery of the project. Take a look at the critical path to determine which operations can be tracked quickly.

Say you would have begun a fresh project and all the requirements have already been collected. You can begin with the design stage at this stage and only begin with the creation of software if the design is prepared.

But if you need to quickly monitor both procedures, the most significant designs are prepared to begin software development after first. Then, keep preparing the latter opinions while programmers are implementing materials that they have already obtained. While quick tracking may seem attractive, remember the hazards as well. Since you're going to have to handle several significant operations at once, making expensive errors or sacrificing quality is simpler.

### 2.3.3 Celoxis

Celoxis comes packed with strong planning and scheduling instruments when it comes to project scheduling to assist you create vibrant project plans that automatically adapt to altering real-world circumstances. Armed with one of the most versatile, quick and responsive interactive Gantt graphs, Celoxis can manage big project plans with various sub-task concentrations, inter-project dependencies and various resources per task. Its automatic planning function accommodates nearly every real-world situation for a solid and reliable timetable of projects. Celoxis makes project tracking a breeze with characteristics such as automatic email alerts, RAG health indicators, and critical path analysis. Celoxis gives visibility of what each member does and enables you to track resource loads in real-time.

### 2.3.4 Hive

Hive is a stage for venture the executives and participation with organizations, for example, Starbucks, Uber, WeWork and IBM. Hive streamlines your activity in one concentrated stage with AI-based examination, a huge number of combinations, flexible task sentiments, and the sky is the limit from there. Utilized by groups of variable sizes, running from 10 to 1,000 people, Hive is a superb decision for an assortment of organizations and working styles. Hive's time following, examination and adaptable review abilities empower straightforward information of the activity of other colleagues and future undertakings that can be observed through activity cards.

### 2.3.5 Projectmanager.com

ProjectManager.com is balanced, grant-winning programming that some significant names, for example, NASA, Volvo, Brookstone, and Ralph Lauren use. This is an amazing choice to deal with different tasks on the double, specifically. This device gives a huge amount of supportive task arranging and booking attributes: you can create venture plans (Gantt outlines), handle assignments, produce reports, and handle timesheets, uses, and remaining tasks at hand utilizing this device. This application for undertaking arranging likewise offers a supportive capacity that enables you to switch between suppositions effectively between Gantt outline, task rundown, and assessments of the Kanban board. In the correspondence attributes of the in-application, you can remark on assignments and appoint them to colleagues.

### 2.3.6 Monday.com

Monday.com is a timetable instrument that features intuitive cooperation that is simple to learn and comprehend rapidly. It is an extremely customizable instrument that enables you to explain the job sequence and see your project progress and status at a glance.  Most of monday.com's project planning characteristics are in the "timelines" feature— this is where you can schedule projects, set deadlines, assign team members, break down duties, and set dependencies.  By merely clicking and dragging, you can reassign assignments, and you can view your timelines as spreadsheets, lists, maps, Kanban boards, and other opinions.

### 2.3.7 Mavenlink

Mavenlink is a comprehensive instrument that includes modules for project planning and management, accounting, resource management, company intelligence, and team collaboration — all in one. It also provides a dashboard system, live time tracking and cost monitoring characteristics, an excellent system for document management. And all these best-in-class characteristics are provided by simple, minimalist design.

### 2.3.8 GanttPRO

GanttPRO is very user-friendly internet Gantt chart software. Making a project plan online is one of the most inexpensive alternatives, particularly if you sign up with a tiny team. It provides a pleasant UX / UI design: becoming a sophisticated user is a matter of minutes and creating your first timetable for project management. More than 350 K customers already appreciate the tool and are highly recognized by single users and teams including Salesforce, Sony, HubSpot, NASA, GitHub, and Vodafone teams. This timeline project software also allows you to deploy your funds on your project schedules. Using remarks, attachments, and real-time notifications, you can invite actual team members or virtual assets, set costs for them, handle resource workload, estimate project costs, and cooperate with a team. You can share your project with stakeholders, customers, and any other third parties with the Public URL feature.

### 2.3.9 Microsoft Project Online

Learning how to use scheduling software for Microsoft Project can demonstrate hard for some because it is an enormous program that involves mastering knowledge. It can be used as a desktop app with an Office 365 subscription. Even if you do not have the Microsoft Project permit, you can use any MS viewer software to view MPP files. Many multi-million-dollar businesses use Microsoft scheduling software. Despite being (or perhaps because of it) a legacy project management software, many new PM and medium capacity agencies prefer alternatives to Microsoft project because MS project files are large and can't always be easily shared online.

### 2.3.10 Wrike

This product is expected explicitly for huge organizations and attributes a community-oriented apparatus continuously. It is utilized by promoting and imaginative groups, yet because of the number of supportive incorporations with advancement instruments like Jira and GitHub, it is likewise common for item groups to utilize Wrike as a product venture organizer. Wrike is an across the board PM programming that has an inseparable tie to arranging, revealing, coordinated effort, a combination of outsiders and computerization of work processes. It rearranges your life by connecting with your task in one area every one of the assignments, reports, discussions, messages and newsfeed to give you a general picture of the headway of your undertaking. Wrike additionally has an insightful revealing component that has a lot of infographics refreshing itself at regular intervals, so you don't need to stress over getting new information.

### 2.3.11 Asana

Asana is an exceptionally normal undertaking planning programming; for some multi-million-dollar organizations, it has been around longer than numerous different instruments and is the go-to item. It's the fantasy apparatus of an undertaking supervisor as it arranges all your work in one spot, so you don't sit around between messages, clingy notes, and tablets. Asana is one of the most outwardly stunning booking applications, making it a breeze to move and quickly fathom Asana's task booking qualities including a venture arranging schedule and course of events that enables you to outline undertaking plan: making, imagining, and overseeing assignments, due dates, doles out, and conditions. I T has a brilliant dashboard that gives you a chance to set custom territories to screen the most significant stuff for you.

## 2.4 MEASUREMENT OF PROJECT SCHEDULE PERFORMANCE

### 2.4.1 Earned Value Measurement

The earned value method of measuring project’s performance is a known reliable measurement method used in project performance management. Its reliability has been emphasised by many experts in project management. Vanhoucke (2009) Earned Value Management is probably the most reliable way to track and manage schedule performance, but getting right is also quite complex, especially if you don't have previous experience operating in an EV setting. You may discover that a complete EV strategy is overkill on a tiny project. It is a nice discipline, however, so if you have the time to set it up correctly and think it would be beneficial in your project setting, you will get precise and helpful outcomes with it.

It is calculated by multiplying by the project budget the actual percentage of the completed work.it is the value of the actual completed work to date.

## 2.5 PROJECT SCHEDULE MANAGEMENT CHALLENGES

### 2.5.1 Implementation Challenges

Adopting best practices can lead the organisation to better outcomes. While there are many best practices in efficient project management, there are also different views on the use of best practices (Chemuturi, 2013). The role of senior leadership in shaping project organization is crucial. Implementation of best practices in the project depends on the existing organizational culture, which directly influences the project organization. Project managers must focus on key challenges areas while implementing best practices. Role of senior leadership, effectiveness of PMO, human factors, PM training, poor adoption of the PM standards, and triple constraints are some of the important challenges that can occur while implementing best Practices.

### 2.5.2 Role of Senior Leadership

The function of senior management is paramount among the many difficulties encountered by applying best practices. Management assistance is needed for the successful application of best practices, as efficient project management depends on senior management for guidance and support (Fui-Hoon Nah et al 2001; Somers and Nelson, 2004). Top leadership assistance is vital to align the top management objectives with the project objectives. The previous study has shown that assistance from top management can considerably change the way customers accept or dismiss the final item or project (Pinto and Slevin, 1987). Leadership assistance along with adequate financing for the project organisation can assist create PMO, adopt the right methodology, and adequate project planning and implementation.

### 2.5.3 Human or People Factors

Effective project management implies that individuals are doing the correct stuff. Issues linked to teaching, training, and recruiting the correct resources can affect best practice execution. An organisation that has chosen the route of agile methodology may find it hard to implement it if there is no qualified project manager who understands the basic values. Finney and Corbett (2007) argued that a champion of the project, a balanced team and empowered decision-makers are critical to the achievement of the project. Project management abilities and capacities are also crucial for user practice, education and development (Somers and Nelson, 2004). Project organisation must, therefore, have competent and effective project managers, PMO employees, advisors, and project team members with the necessary expertise and abilities to implement best practices. Evaluating the capacity of individuals in the project as soon as possible can also drive the project to achievement (Chemuturi, 2013).

### 2.5.4 Triple Constraints

For implementing best practices, it is necessary to consider the implementation scope, time and cost for proper project planning. After obtaining senior leadership consent, project manager or PMO must develop a detailed project plan. The plan should cover the best practices that needs to be implemented, when and how. The project plan must also outline strategic resources required, and the time-line for adopting and implementing best practices. As best practices cover the entire organization, it is necessary to discuss the project plan initially with all the stakeholders before finalizing it. Implementing the plan within the budget and time may be a task, and any cost variance or scheduling mistakes during the execution of best practices must also be carefully monitored by PMO or project director (Chemuturi, 2013).

### 2.5.5 Project management office (PMO) or No Project management office (PMO)

As a structured project organization, project management office has a large role to play in any organization. However, some organizations discard its importance and relegate its role to the one who just sends a project start note. In applying best practices and managing projects, PMO with a powerful managerial power can provide enormous service to the organisation (Andersen et al., 2007). By taking into consideration the complexity of the project, PMO can also provide specialist guidance, choose and embrace the best methodology practices. In the absence of PMO, the implementation of best practices may not be possible. A knowledgeable and capable senior project manager, who can provide expert opinion and guidance to other project managers, normally heads the PMO. It will be a challenge, if there is no PMO available to implement best practices (Chemuturi, 2013).

### 2.5.6 Poor Adoption of Project Management Standards

Besides instruments, clear guidelines and norms need to be adopted for adequate project execution. Unless there are adequate project guidelines or norms in place, it is simple to compromise the quality of the deliverable. To successfully organize the project, it is necessary to maintain rigid rules and norms during the implementation and support phases. This data must be made accessible for future use throughout the organisation after identifying norms and guidelines. Therefore, a consistent application of extensive rules and norms can guide the organisation of the project to achievement (Chemuturi, 2013; Thamhain, 1996; Pinto and Slevin, 1987).

### 2.5.7 Lack of PM training

Project executives who usually come from technical backgrounds in most organisations learn from experience, or by observing other PMs, project management abilities. Due to lack of experience in managing various projects, the knowledge acquired by PMs may be limited and therefore require formal PM training (Chemuturi, 2013). Lack of formal training for project executives can have an undue effect on efficient project management as one of the obstacles to best practices. Organization must guarantee that all project executives receive official PM training based on the guiding principles of PMBOK with particular emphasis on conventional instruments, methodologies and procedures. It is also advisable to provide training in agile and extreme methodologies that can assist handle complicated projects in relation to traditional project management best practices.

## 2.6 FACTORS THAT AFFECTS PROJECT SCHEDULE MANAGEMENT

Rongala (2015) indicated the following factors that affect schedule management;

1.  Deadline

Due date is one of the fundamental components of how to deal with an undertaking. Missing a due date gives your group a poor inclination. Finishing a venture on schedule, be that as it may, doesn't infer you're settling on quality. You both should be educated about the time and watch out for quality. On the off chance that the venture has tight due dates with exacting clients or partners, venture chiefs ought to be aware of any conceivable front-end impediments and play it safe so quality items or administrations can be conveyed on an on-time premise. The administrator ought not exclusively to be on their toes yet ought to likewise impart a similar methodology among colleagues. Colleagues should banner issues, issues, and hindrances when gone up against with the goal that choices can be quickly searched for.

2.  Budget:

Budget is another critical factor determining the advancement and management of a project. If the budget is big, then there will also be more days to complete the project and so will be the number of funds assigned to it. Do not rush in such circumstances; instead, concentrate entirely on providing high-quality products or services with maximum resource usage. If the budget is lesser, however, you need to adjust with constraints such as absence of resources, thus money and time. You can't compromise on quality, however, which means you and your team's stress level rises. Your angry overworked team members may need to be motivated by promoting them to perform well and acknowledging their efforts through rewards.

3.  Stakeholders:

Management of project techniques would differ depending on the type of project stakeholders. In the event that a project has various stakeholders from distinct backgrounds, they may disagree. In situation like this, project management becomes very thought-provoking because unhappy stakeholders and clients cannot be afforded. In such instances, there is a need for great convincing and negotiating abilities to achieve agreement. It can be time-consuming, thus decrease the real resource dedicated time. In such cases, the project manager must adopt tactful approaches and do the work.

Project manger

Management of project methods is determined by the cumbersomeness faced by these managers, which in turn depends on the type of team he or she is dealing with. If the team consists of employees with distinct backgrounds and skills, a gap in team spirit may occur. Obviously, this has an impact on the job. Consequently, a PM should use methods to close the team. He should ensure that the periodic team meets formally and informally. People from different backgrounds are bound to communicate in team conferences and outings. This generates a bond between employees and is prepared for each other to be there.

5.  Demand:

Demand is another key factor influencing the techniques of PM. Variables like product or services, usability is what demand relies on. the nature of demand of vegetables differs from that of clothing which can be stored for long and still have that value. For services, such as creating instruction manuals for electronic goods, demand relies on the amount of market consumers. Depending on the type of demand and the nature of the product or services offered, appropriate management techniques must be applied by a project manager to ensure goods and services are delivered on time.

An app development firm, for instance, is developing a product from XYZ for a fresh mobile offering that will be published on the market after 6 months. Therefore, at least a month before the launch, the app requires to be prepared. The project manager needs to keep in mind of allocating of resources and team formation. Quite some number of methods would require daily morning stand-ups, periodic testing sessions, in-house study, pilot testing among chosen technology geeks. Then again, if an association behaviours instructional courses on undertaking the board accreditations, the system of the task chief may include statistical surveying, the arrangement of administrations at a lower than the market rate, the quest for potential up-and-comers who can take up the confirmations, limits if an individual takes more than one course, an internet advertising group to advance the administrations.

6.  Supply:

To fulfil the need inside stipulated date and time, the store of advantages is fundamental. An endeavour overseer needs to ensure that supply is good with the objective that the due date isn't undermined for the requirement for resources. For example, the association has arranged an instructional gathering with 15 understudies on a given date. Understudies have paid charges and they have been given the date, time and setting of the session. In any case, more people started enlisting for the session and the total number touched base at 25. The present setting has a breaking point of 20 people. By and by, the readiness provider should be in a circumstance to arrange some other setting speedily for the instructional course. In case the session gets dropped due to the nonattendance of room, it will be noteworthy adversity for the association both with respect to money and reputation.

7.  Price:

Price is a key element of PM. Price is determined by high-level executives after studying market trends in consultation with project sponsors. Price is a significant determinant of sale and profit and after thorough calculation should be determined. The sort of product or service to be regarded when speaking about price determination is a significant consideration. We will classify products into three kinds for comfort: perishable goods, non-perishable products, and specific products. There are two factors to consider here: the amount to be sold and the price to be paid by the customer. Demand is never a restriction in the event of non-perishable products such as cooking oil, grains and pulses, coal. In addition, the products can be stored and marketed throughout the year as non-perishable. The factors of storage and demand balance the price. Usually, these types of products are not priced exorbitantly high.

The following factors also affect project schedule management:

Resource availability

The less resources the project has been allotted, the longer the timetable for the project.

Complexity of the project

If the project has complicated activities and never finished them, then surely the project manager must accommodate this reality in his timetable of the project.

Task dependencies

There are many tasks that cannot be began before others are completed, as well as some tasks that need to start together. Dependence on tasks will dictate the function sequence and will also dictate the project's need for funding at any point.

Team experience

If the project team is weak or has no experience on similar projects, then the project manager must account for that in his project schedule and must pad his estimates

## 2.7 SUMMARY OF CHAPTER

Improved and efficient methods in project management are crucial for project success. Best practices in project management enhance project effectiveness and provide better rules, methodologies and procedures that can be followed throughout the organisation. Adopting best practices in project management can generate the required result of the project, thus helping the organisation to attain its organisational goals and goals strategically. Top management assistance is most critical to the growth of best practices as a critical success factor. Lack of assistance from senior leadership, inadequate PMO, human factors, and absence of formal PM training are some of the major problems faced by organisations while implementing best practices for project management.

CHAPTER THREE

# RESEARCH METHODOLOGY

## 3.1 INTRODUCTION

This chapter seeks to discuss the various methods and procedures adopted in order to espouse information from respondents to answer the problems of the study through a research design, population, sampling and sampling techniques, data collection procedures as well as data presentation and analysis procedures.

## 3.2 DESIGN OF THE STUDY

## 3.2.1 Research Design

The study outlined, analysed and interpreted the opinions of Ghana Port and Harbour Authority (GHPA) experts to define the numerous techniques, instruments and methods used in planning activities carried out by / for GPHA to identify the difficulties faced by executives in the efficient use of project planning techniques and methods. To analyse the reaction, the study research design used the quantitative questionnaire survey.

## 3.2.2 Research Method

This study is qualitative. Shank (2002) defines qualitative research as “a form of systematic empirical inquiry into meaning”. By systematic he means “planned, ordered and public”, following rules agreed upon by members of the qualitative research community. By empirical, he means that this type of inquiry is grounded in the world of experience. Inquiry into meaning says researchers try to understand how others make sense of their experience. Denzin and Lincoln (2000) claim that qualitative research involves an interpretive and naturalistic approach: “This means that qualitative researchers study things in their natural settings, attempting to make sense of, or interpret, phenomena in terms of the meanings people bring to them”.

The advantages of doing qualitative research on leadership include (Conger, 1998; Bryman et al, 1988; Alvesson, 1996):

Flexibility to follow unexpected ideas during research and explore processes effectively; sensitivity to contextual factors; ability to study symbolic dimensions and social meaning; increased opportunities to develop empirically supported new ideas and theories; for in-depth and longitudinal explorations of leadership phenomena; and for more relevance and interest for practitioners.

3.3 RESEARCH DATA

3.3.1 Sources of Data

Both primary data and secondary sources of data will be used for the study. Interview is the main instruments used for primary data collection for this study. Secondary data was gathered from various statutes/instruments, reports, journals, articles, papers and the internet. A review of literature on the study from secondary sources, will help the researcher discover major issues relating to the project schedule management of projects at the Ghana Ports and Harbour Authority. Seminar/conferences/workshop presentations/addresses, journals, reports, memoranda, newsletters statutes/instruments and books that contained materials relevant to the study will also be acknowledged and cited.

## 3.3.2 Data Collection Methods

This discussed the various instruments used to espouse information from respondents. It enabled respondents provide the necessary information for the study.  As mentioned earlier, the main instrument that will be used is the administering of questionnaires. The researcher administered the questionnaires to staff and managers of third-party contractors with the needed knowledge in project management. The questionnaires were administered electronically or manually.

## 3.4 Data Analysis

Data analysis is mainly done to see whether the data is able to provide answers to the research question set out in achieving the purpose of the study (Saunders et al., 2009). Kwofie (2015) opined that this process generally refers to how data are organised, examined, categorized, tabulated, interpreted and tested. There are several ways in which data is tested statistically. The decision to use one method over the other depends on the type of analysis, accuracy of work and the kind of information which the researcher want to get from the primary data. The various methods are also influenced by the research design, data distribution and type of variable. Mostly, normally distributed data uses the parametric tests while the non-normally distributed data adopts the non-parametric tests (Saunders et al., 2009). The next sections below provide information on the tool which was used in analysing the primary data which was obtained from the survey.

### 3.4.1 Relative Important Index (RII)

The RII helps in identifying the relative importance of variables, and informing the researcher in making a choice one out of the several variables which best explains or is critical to achieving the objective at hand (Carpio et al., 2007). RII was proposed by Soofi et al. (2000) as a tool for determining the relative significance of quantities through the formulation of indexes from which the various characteristics are ranked (hence, understanding the contribution of each variable to a response variable). Kapadia-Kundu and Dyalchand (2007) opined that adopting a five-point Likert scale is very good in measuring statement which would be solved using the RII tool. Hence, this study adopted a similar approach in its questionnaire formation.

RII has been used by several scientists in their analysis in variant factions (for example see Johnson, 2000; Jeyamathan and Rameezdeen, 2006; Antwi-Afari et al., 2018; OwusuManu et al., 2018 etc.). Therefore, adopting the use of RII for this study proves worthy because it has been used and adopted in identifying the relative significance of variables in works as shown in the citations above. One more reason for adopting RII in on the avowal of Capiro et al. (2007) who said that RII is best for group of variables, and the questionnaires of this study was formulated as such. In Summary, Relative Importance Index was adopted to identifying the militating factors of sustainable development of smart cities of developing countries.

∑𝑾

RII was calculated based on this formula; RII =   where W is the weight given to each

𝑨∗𝑵

factor by respondent ranging from 1 – 5, N is the total number of respondents, and A is the highest response integer (5 in this case).

## 3.5 SAMPLING

## 3.5.1 Population

The target population is the project management team and third-party contractors working for the Ghana Port and Harbour Authority's Civil Engineering Department, Takoradi. The project manager plays a main role in the project and is responsible for effectively finishing it. The manager's task is to guarantee that the project continues to achieve its objectives within the defined timeframe and within the defined budget. Project managers guarantee that projects receive appropriate funds while preserving relationships with contributors and stakeholders.

The Ghana Ports and Harbours Authority (GPHA) is Ghana's national port authority, responsible for managing, maintaining and operating Ghana's ports, mainly Sekondi-Takoradi Port and Tema Port, and Tema Fishing Harbour. The GPHA headquarters are located in Sekondi-Takoradi and Tema. The GPHA is a logistics service provider that provides its clients with port equipment and services. The Authority manages and operates the Tema Port and the Takoradi Port in collaboration with a host of private service providers in the fields of containerized and general cargo handling, stevedoring, transfer, storage, receiving and delivery. Others are services of security, security and preservation. The GPHA also leases a broad variety of service suppliers from plants and machinery. The major clients we serve include: Ship Owners and their Agents, Freight Forwarders, Cargo Handlings Companies, Importers and Exporters, Haulage Companies, Ship Chandlers, Off-Dock Terminal Operators, Warehouse Companies, Dock Labour Pool Operators, etc.

## 3.5.2 Sample Size

Sample size is a word used to define the number of topics included in a sample in studies. Sample is understood as a group of subjects selected from the general population and considered a representative for that particular study of the true population.

To access project schedule management at the Ghana Port and Harbour Authority, it will not be feasible to target the entire staff, therefore, the researcher will sample out some staff and target the needed data and information. Sample size measures the number of individual samples measured or observations used in a survey or experiment (Zamboni, 2018).

## 3.5.3 Sampling Technique

Tongco (2007) indicated that the issue the investigator is interested in answering is of utmost significance in selecting a sampling method for informant choice. The issue will decide on the goals to be based on the methodology. The first concern is whether to study the whole population for the study, but due to time constraint, a sample of the population is taken but efficient one. How many individuals are going to participate? What level of organisation, individual or community, would be sampled? What sampling method should be used to ensure that the sample is representative and replicable, robust and meaningful information gathered (Alexiades 1996, Bernard 2002). The researcher must then decide whether the most suitable tool for the study is purposeful sampling. If so, the investigator is willing to search for suitable formants. Preparation is required in order to find knowledgeable and reliable informants most effectively (Snedecor 1939) before one sample the population. It is also possible to take the sample from prior study expertise (McDonald et al. 2003). Using a number of techniques in data collection, purposeful sampling can be used (Godambe 1982). A survey may start a study, followed by purposeful sampling based on the survey (Brown 2005). In an acculturation study, Robbins et al. (1969) used a questionnaire as a systematic way of finding informants.

A purposeful and snowball sampling method was used because interviewing the entire GPHA employees is not practical and viable. In addition, not all personnel members may be in the field knowledgeable. A sample is a component of a group or aggregate of whole items chosen for data about a whole (Commonwealth of Learning, Research Methodology, 2008).  Few individuals would be sampled from the study population who possess greater understanding in this sector.

The purposeful sampling method is, according to Tongco (2007), a form of non-probability sampling that is most efficient when studying a certain domain with knowledgeable professionals. Using both qualitative and quantitative research methods, purposeful sampling may also be used.

# CHAPTER FOUR

# DATA PRESENTATION AND DISCUSSION

## 4.1 Introduction

The aim of this study was to assess project schedule management of projects at the Ghana Ports and Harbours Authority.

Methodology consisting of a literature review and a survey of the project team of the Ghana Ports and Harbours Authority and project managers of third parties to obtain how Project Schedule Management is conducted in the preceding chapters to achieve the purpose of the study. Therefore, this section provides the outcomes of the survey, analysis of the study's outcomes and conclusions.

## 4.2 Results of the Survey

Questionnaires were sent to 100 persons, Ghana Ports and Harbours Authority’s Project team and third-party contractor’s project managers in Takoradi of which 84 responses were received for a response rate of 84%. The responses were further analysed to determine the profile of respondents, the respondents‟ position; whether respondents were familiar with the assessment of project schedule management at their workplace.

## 4.3 DEMOGRAPHIC VARIABLES

The views of the respondents are considered here as those of the principals of the various departments who are in charge of project schedule management of projects at the Ghana Ports and Harbours Authority for the purpose of the analysis. The general information being sought are the level of education, years of experience. It also probes their level of conversance on project schedule management.

## 4.3.1 Levels of Education

Figure 4.1: Level of Education

From the above figure 4.1 shows that 30 respondents have had their formal and higher education up to the first degree (BSc.) level representing 36% while 9 respondents representing 11% had masters` degree (MSc.). 17 of the respondents had Diploma which represents 20 %. 5 of the respondents had the Doctor of Philosophy degree representing 6% and last but not least 23 of the respondents had other certificates representing 27%.

The above table clearly shows that most of the respondents had their formal and higher education up to the first degree (BSc)

## 4.3.2 Years of Experience

Figure 4.2: Years of Experience

The above Diagram 4.2, clearly shows in terms of the working experience of the, 10 respondents representing 11.9% said they had working experience which is less than 5years, 19 respondent representing 22.6% said they had working experience of between (5 – 10) years, 15 respondent representing 17.8% said they had working experience of between (11 – 15) years and 40 respondent representing 47.9% said they had working experience of more than 15 years. From the above table it is its clear that most of the respondents have working experience of above 15 years.

## 4.3.3 Conversance level of respondent

Figure 4.3: Conversant Level of Respondent

Apropos the extent of conversancy figure 4.3 states that 23 respondents representing 27% said they were very conversant, 41 which constituting 49% said they were conversant with project schedule management, 5 respondents representing 6% indicated that they were fairly conversant with project schedule management 14 of the respondents representing 17% indicated that they were not sure with project schedule management as well as 1 respondent indicating 1% as not conversant. It was evident that, almost all the respondents were conversant with project schedule management considering the fact that all respondents had attained tertiary education in works project schedule management.

## 4.4 TECHNIQUES, TOOLS AND METHODS USED IN SCHEDULING PROJECTS EXECUTED BY/FOR THE GPHA

A Likert scale was used by experts to express their opinions from not important to very important some techniques, tools and methods used in scheduling projects executed by/for the GPHA.

Table 4.1: Techniques, Tools and Methods

| techniques, tools and methods used in scheduling projects executed by/for the GPHA | ΣW | RII | Rank |
| --- | --- | --- | --- |
| Microsoft Project | 356 | 0.848 | 1st |
| PERT | 330 | 0.786 | 2nd |
| Critical Path Method | 328 | 0.781 | 3rd |
| GanttPRO | 327 | 0.779 | 4th |
| primavera | 325 | 0.774 | 5th |
| Celoxis | 322 | 0.767 | 6th |
| Forecast | 315 | 0.750 | 7th |
| Project Manager.com | 311 | 0.740 | 8th |
| Crashing | 308 | 0.733 | 9th |
| Wrike | 307 | 0.731 | 10th |
| monday.com | 298 | 0.710 | 11th |
| Mavenlink | 296 | 0.705 | 12th |
| Asana | 294 | 0.700 | 13th |

Source: Field Survey 2019

From the above table, Microsoft Project was ranked 1st   with an RII of 0.848 followed by the 2nd rank that was given to PERT representing 0.786. Critical Path Method Was given the 3rd position with an RII of 0.781 whiles ProjectManager.com came 4th with 0.779 as an RII. Hive and celoxis took the 5th and 6th rank with an RII of 0.774 and 0.767 respectively. Forecast was given the 7th rank representing 0.750. GanttPRO was awarded the 8th rank with an RII of 0.740. Crashing firmly took the 9th position representing 0.733 leaving PERT and monday.com as 10th and 11 with an RII of 0.731 and0.710 respectively. Mavenlink could not be left unranked hence it took the 12th position representing 0.705 and last but not lease Microsoft Project Online takes the 13th rank with an RII of 0.700.

From the above table all the techniques had weighting below 400 hence it means that respondents found those techniques to be very relevant. Again, using relative important index RII all the techniques had less than 0.9 thus it can be which established all the thirteen (13) techniques, tools and methods used in scheduling projects executed by/for the GPHA are very significant

## 4.5 CHALLENGES PROJECT MANAGER’S FACE IN THE EFFECTIVE USE OF PROJECT SCHEDULING TECHNIQUES AND METHODS

A Likert scale was used by experts to express their opinions from not important to very important some challenges managers do confront in the effective use of project scheduling techniques and methods

Table 4.2: Challenges Project Managers Face

| Challenges project managers face in the effective use of project scheduling techniques and methods | ΣW | RII | Rank |
| --- | --- | --- | --- |
| Lack of project management training | 353 | 0.840 | 1st |
| Lack of support from Senior Management | 352 | 0.838 | 2nd |
| Poor understanding of Triple Constraints | 351 | 0.836 | 3rd |
| Poor Human or People Factors | 348 | 0.829 | 4th |
| Poor Adoption of Project Management Standards | 346 | 0.824 | 5th |
| Lack of training in Implementation | 330 | 0.786 | 6th |

Source: Field Survey 2019

The table above shows the challenges that project managers face in the effective use of project scheduling technique. Questionnaires were given to respondents and they graded it as following.

Overall, the first rank goes to Lack of project management training who has an RII of 0.840, followed by the 2nd position which was given to Role of Senior Leadership representing 0.838. The 3rd and 4th was given to Triple Constraints and human or People Factors with an RII of 0.836 and 0.829 respectively.  Poor Adoption of Project Management Standards firmly held on to the 5th position with an RII of 0.824 and last but not least the 6th and final rank was administered to Implementation Challenges which has an RII of 0.786.

From the above table all the challenges had weighting below 400 hence it means that respondents found those challenges to be very relevant. Again, using relative important index RII all the techniques had less than 0.9 thus it can be which established all the six (6) challenges faced by project managers in the effective application of project scheduling technique and methods are very significant.

## 4.6 FACTORS THAT AFFECTS PROJECT SCHEDULE MANAGEMENT.

A Likert scale was used by experts to express their opinions from not important to very important some factors that affects project schedule management.

Table 4.3: Factors that Affects Project Schedule Management

| FACTORS THAT AFFECTS PROJECT SCHEDULE MANAGEMENT. | ΣW | RII | Rank |
| --- | --- | --- | --- |
| Project complexity | 340 | 0.810 | 1st |
| Team experience | 339 | 0.807 | 2nd |
| Task dependencies | 338 | 0.805 | 3rd |
| Deadline | 327 | 0.779 | 4th |
| Stakeholders | 327 | 0.779 | 5th |
| Budget. | 321 | 0.764 | 6th |
| Project Members | 314 | 0.748 | 7th |
| Demand | 313 | 0.745 | 8th |
| Supply | 310 | 0.738 | 9th |
| Price | 309 | 0.736 | 10th |
| Resource availability | 302 | 0.719 | 11th |

Source: Field Survey 2019

Table 4.8 discusses some important factors that affects project schedule management that was sent to respondents to share their thoughts on and the results of their analysis are as follows:

Project complexity was ranked first with an RII of 0.810 followed by the 2nd position that was given to Team experience representing 0.807. Task dependencies and Deadline was ranked 3rd an 4th with an RII of 0.805 and 0.779 respectively, followed by the 5th rank that was administered to Stakeholders hence the RII of 0.779. Budget firmly held on to the 6th rank representing 0.764 and Project Members followed next with an RII of 0.748 holding the 7th rank. The 8th and 9th rank was administered to Demand and Supply representing 0.745 and 0.738 respectively. The 10th rank was given to Price with an RII of 0.736 and the final rank thus the 11th position was given to Resource availability with an RII of 0.719

From the above table all the factors had weighting below 400 hence it means that respondents found those factors to be very relevant. Again, using relative important index RII all the factor had less than 0.9 thus it can be which established all the eleven (11 factors that affects project schedule management are very significant

Table 4.4: Client Responses with Respect to Techniques, Tools and Methods Used in Scheduling Projects by GPHA

| FACTORS THAT AFFECTS PROJECT SCHEDULE MANAGEMENT. | 1 | 2 | 3 | 4 | 5 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project complexity | 1 | 2 | 14 | 42 | 25 | 84 |
| Team experience | 1 | 5 | 16 | 30 | 32 | 84 |
| Task dependencies | 2 | 10 | 2 | 40 | 30 | 84 |
| Deadline | 4 | 1 | 15 | 44 | 20 | 84 |
| Stakeholders | 3 | 7 | 11 | 38 | 25 | 84 |
| Budget | 3 | 2 | 20 | 41 | 18 | 84 |
| Project Members | 5 | 9 | 9 | 41 | 20 | 84 |
| Demand | 4 | 9 | 15 | 34 | 22 | 84 |
| Supply | 10 | 4 | 7 | 44 | 19 | 84 |
| Price | 9 | 5 | 10 | 40 | 20 | 84 |
| Resource availability | 6 | 13 | 5 | 45 | 15 | 84 |

Source: Field Survey 2019

The Table 4.4 show the Clients' Responses to the Relative Importance of factors that affects project schedule management. The respondents were asked to measure by using 1-Not important, 2-Quite important, 3-Moderately important, 4-Important and 5-Very important.

According to the table, it is evident that most of the respondent saw Project complexity to be the most influential factors that affects project schedule management.

## 4.7 SUMMARY

It is interesting to know that most of the respondents had their education up to BSc and they constituted 36% while the remaining 64% was distributed among MSc, Diploma, Postgraduate Diploma level and others. Most of the respondents were staff at the Ghana Ports and Harbours Authority. The working experience of most of the respondents was above 15 years. Most of the respondents (49%) admitted to be very conversant with project schedule management. The techniques, challenges and factors that affects the project schedule management had all their weighting below 400 therefore it means that respondents considered them to be very important. Again, using relative important index RII all the results came out to be less than 0.9 thus it can be concluded that all the techniques, challenges and factors proved very significant.

# CHAPTER FIVE

# SUMMARY OF FINDINGS, CONCLUSION AND DISCUSSION

## Introduction

This chapter captures a review of the objectives, the findings of the research and suggests recommendations for practical implications. The chapter also concludes giving a few areas for future directions into the same or related research.  The conclusion to the entire research is also captured further below.

## 5.1 SUMMARY OF FINDINGS

The assumptions as follows were therefore presented as per the objectives of the research.

## 5.1.1 Objective One

To identify the various techniques, tools and methods used in scheduling projects executed by/for the GPHA

From the reaction of the employees at the Ghana Ports AND Harbours Authority, there was a powerful appreciation of the leadership of the project schedule and its significance in the sector. Regarding the particular management problems, the techniques, instruments and methods used in planning projects carried out by/for the GPHA were unanimously agreed. For instance, many of the Project managers agreed that Microsoft Project, PERT, and Critical Path Method are an important technique/ tool used in scheduling projects.

## 5.1.2 Objective Two

To identify factors that affect project schedule management and measure the performance of the project schedule development using Earned Value Method The research established that factors that affect project schedule differ in the form of factors involved. After critically analysing the data received, it was certain that most of the respondent chose project complexity as the most important factors that affect project schedule management. This is because out of 84 respondents, 67 of them saw how project complexity plays a very important factor in schedule management. However, there were also some factors that respondents saw to be important as well, they are: team experience, task dependencies, deadline, stakeholders, and budget. The above factors were ranked from 2nd to 6th

## 5.1.3 Objective Three

Identifies the difficulties facing project managers in the efficient use of techniques and methods for project planning. With regard to the above goals, answers were simply sorting from Ghana ports employees and Harbours Authority employees. The reactions showed that absence of project management training is a major challenge faced by project executives in the efficient use of project planning technique and methodology; other difficulties faced by project executives include senior leadership roles, triple constraints, human or human factors, bad adoption of project management standards and difficulties of execution.

## 5.2 Conclusions

Within the industry, there is a strong appreciation of the importance of project scheduling and its importance within the industry. Indeed, various levels tools and techniques have been established within the industry, and based on the analysis obtained, it is obvious that Asana, Wrike, Critical Path Method, ProjectManager.com and Hive are ranked as the most important technique/ tool and methods used in scheduling project executed by/for the GPHA.

Lack of project management training, Role of Senior Leadership, Triple Constraints, Human or People Factors, Poor Adoption of Project Management Standards, Implementation Challenges was also ranked as the most important challenges project managers faced in the effective use of project scheduling techniques and methods since it strongly affects the performance of staff at the Ghana Ports and Harbours Authority. Also, Project complexity, Team experience, Task dependencies, Deadline and Stakeholders are also relevant factors that affect project schedule management.

5.3 Recommendations

It is recommended that, project managers regularly use these applications as it contributes hugely to project success.

# REFERENCES

Chau, K.W., Anson, M., and Zhang, J.P. (2005). “4D dynamic construction management and visualization software: 1. Development.” Automation in Construction, Vol. 14(4), 512-524.

Creswell, J.W. (2009). Research design: qualitative, quantitative, and mixed methods approaches. 3rd ed. California: Sage Publications.

Hancher, D.E. (2003). “Construction planning and scheduling.” The Civil Engineering Handbook, 2nd Edition, CRC Press LLC.

Heesom, D., and Mahdjoubi, L. (2004). “Trends of 4D CAD applications for construction planning.” Construction Management Economics, 22(2), 171- 182.

Hendrickson, C. (1998). Project Management for Construction. Department of Civil and Environmental Engineering, Carnegie Mellon University, Pittsburgh, PA 15213.Available online from:(http://www.ce.cmu.edu/pmbook/)

Illingworth, J.R. (2000). Construction Methods and Planning, 2nd ed., E and FN Spon, London.

Li, M. H. ; Robinson, E. H. ; Oberle, D. F. ; Lucas, P. M. ; Bosworth, B. G., 2012. Evaluation of corn gluten feed and cottonseed meal as partial replacements for soybean meal and corn in diets for pond-raised hybrid catfish, Ictalurus punctatus * I. furcatus. J. World Aquacult. Soc., 43 (1): 107-113

Smallwood, J., and Allen, C. (2008, March). Improving construction planning through 4D planning. RESEARCH GATE, 6(1), 566. Retrieved May 24, 2019, from https://www.researchgate.net/publication/235290017_Improving_construction_planning_through_4D_planning

Twumasi, H. N. (2015, November). Construction planning and scheduling practices in road construction firms in ghana. pp. 69. Retrieved May 24, 2019, from http://ir.knust.edu.gh/bitstream/123456789/8303/1/SCHEDULING%20THESIS.pdf

Carpio, C.E., Sydorovych, O. and Marra, M.C., 2007. Relative importance of environmental attributes using logistic regression (No. 1367-2016-108330).

Kapadia-Kundu, N. and Dyalchand, A., 2007. The Pachod Paisa Scale: A numeric response scale for the health and social sciences. Demography India, 36(2), pp.303-313.

Kwofie, E.T., 2015. Contribution of unique features of mass housing projects to project team communication performance (Doctoral dissertation).

Owusu-Manu D. G., Antwi-Afari P., and Edwards D. J. 2018. Expanding Understanding on Attributes of Innovation Champions: Firms and Individual Perspectives of Professional Quantity Surveying Firms. American Journal of Civil Engineering, 6(6), 178-184. doi: 10.11648/j.ajce.20180606.11

Saunders, M., Lewis, P. and Thornhill, A., 2009. Research methods for business students 5th edition. Perntice Hall.

Soofi, E.S., Retzer, J.J. and Yasai‐Ardekani, M., 2000. A framework for measuring the importance of variables with applications to management research and decision models. Decision Sciences, 31(3), pp.595-625.

Kelsey, J.M., Winch, G.M. and Penn, A., 2001. Understanding the project planning process: requirements capture for the virtual construction site.

Allen C, Smallwood J. Improving construction planning through 4D planning. Journal of Engineering, Design and Technology. 2008 Mar 28;6(1):7-20.

Kerzner, H., 2003. Advanced project management: Best practices on implementation. John Wiley and Sons.

Dvir, D., Raz, T. and Shenhar, A.J., 2003. An empirical analysis of the relationship between project planning and project success. International journal of project management, 21(2), pp.89-95.

Zanen, P. and Hartmann, T., 2010. The application of construction project management tools an overview of tools for managing and controling construction projects. University of Twente, 1.

Dye, L. ed., 2002. Managing multiple projects: planning, scheduling, and allocating resources for competitive advantage. CRC Press.

Vanhoucke, M., 2009. Measuring time: Improving project performance using earned value management (Vol. 136). Springer Science and Business Media.

Chemuturi, M., 2013. Mastering IT project management: best practices, tools and techniques. J. Ross Publishing.

Fui-Hoon Nah, F., Lee-Shang Lau, J. and Kuang, J., 2001. Critical factors for successful implementation of enterprise systems. Business process management journal, 7(3), pp.285-296.

Somers, T.M. and Nelson, K.G., 2004. A taxonomy of players and activities across the ERP project life cycle. Information and Management, 41(3), pp.257-278.

Pinto, J.K. and Slevin, D.P., 1987. Critical factors in successful project implementation. IEEE transactions on engineering management, (1), pp.22-27.

Finney, S. and Corbett, M., 2007. ERP implementation: a compilation and analysis of critical success factors. Business process management journal, 13(3), pp.329-347.

Andersen, B., Henriksen, B. and Aarseth, W., 2007. Benchmarking of project management office establishment: Extracting best practices. Journal of Management in Engineering, 23(2), pp.97-104.

Rongala, A., 2015. Top 6 Manual Data Entry Challenges Companies Face.

Weglarz, J. ed., 2012. Project scheduling: recent models, algorithms and applications (Vol. 14). Springer Science & Business Media.

Hinze, J., 2004. Construction planning and scheduling (Vol. 228, p. 229). Pearson/Prentice Hall.

# APPENDIX 1

## QUESTIONNAIRE

RESEARCH TOPIC:  ASSESSMENT OF PROJECT SCHEDULE MANAGEMENT OF PROJECTS AT THE GHANA PORTS AND HARBOURS AUTHORITY

INTRODUCTION

The researcher is a final year student of Kwame Nkrumah University of Science and Technology-Kumasi and from the Department of Building Technology. He intends to execute this research as part of the university’s academic requirement for the completion of his degree of Masters of Project Management. Your objective response to this questionnaire is an invaluable aid to this research work. All information provided would be treated as confidential and for academic purposes only. There are no rights or wrong answers.

In case of any doubt/s or need for clarification, please contact any of the addresses given below.

Thank You.

Supervisor                                                             	Student

Dr. Emmanuel Adinyira				Ebo Kobina Simpson

SECTION A – DEMOGRAPHIC QUESTIONS

Below are some demographic questions. Kindly respond appropriately by ticking.

1.  What is your age?

[ ] 18-30 yrs.   [ ] 31-40 yrs.   [ ] 41-50 yrs.   [  ] above 50 Yrs.

2.  What is your sex?

[ ] Male            [ ] Female

3.  What is the highest level of education you have attained?

[ ] PhD      [ ] M.Sc.         [ ] B.Sc.         [ ] Diploma

Others, Please specify…………………………………………………………… [ ]

4.  For how long have you been practicing as a project Manager?

[ ] 0-4 yrs    [  ] 5-10 yrs       [ ] 11-15yrs            [  ] Above 15 yrs

5.   How conversant are you with project schedule management of projects at the Ghana ports and harbours authority?

[ ] Very Conversant [ ] Conversant [ ] Not Sure [ ] Fairly Conversant [ ] Not Conversant

SECTION B – TECHNIQUES, TOOLS AND METHODS USED IN SCHEDULING PROJECTS EXECUTED BY/FOR THE GPHA

1.      Below are techniques, tools and methods used in scheduling projects executed by/for the GPHA. From your experience, kindly express your opinion on how frequent they are used by ticking the appropriate cell. Use the following likert scale:

1 Always       2 Often       3 Sometimes       4 seldom       5 Never

| TECHNIQUES, TOOLS AND METHODS USED IN SCHEDULING PROJECTS EXECUTED BY/FOR THE GPHA | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| 1. Forecast |  |  |  |  |  |
| 2. Celoxis |  |  |  |  |  |
| 3. Hive |  |  |  |  |  |
| 4. ProjectManager.com |  |  |  |  |  |
| 5. monday.com |  |  |  |  |  |
| 6. Mavenlink |  |  |  |  |  |
| 7. GanttPRO |  |  |  |  |  |
| 8. Microsoft Project Online |  |  |  |  |  |
| 9. Wrike |  |  |  |  |  |
| 10. Asana |  |  |  |  |  |
| 11. PERT |  |  |  |  |  |
| 12. Critical Path Method |  |  |  |  |  |
| 13. Crashing |  |  |  |  |  |

SECTION C – Challenges Project Managers Face in The Effective Use of Project Scheduling Techniques and Methods

1.      Below are challenges project managers face in the effective use of project scheduling techniques and methods. From your experience, kindly express your opinion on the level of agreement by ticking the appropriate cell. Use the following Likert scale:

1 Strongly Disagree       2 Disagree       3 Neutral       4 Agree       5 Strongly Agree

| Challenges Project Managers Face In The Effective Use Of Project Scheduling Techniques And Methods | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| 1. Lack of training in Implementation |  |  |  |  |  |
| 2. Lack of support from Senior Management |  |  |  |  |  |
| 3. Poor Human or People Control |  |  |  |  |  |
| 4. Poor understanding of Triple Constraints |  |  |  |  |  |
| 5. Poor Adoption of Project Management Standards |  |  |  |  |  |
| 6. Lack of project management training |  |  |  |  |  |

SECTION D – FACTORS THAT AFFECTS PROJECT SCHEDULE MANAGEMENT.

Below are communication techniques/tools that impact time, cost and quality.  kindly express your opinion on how influential they are by ticking the appropriate cell. Use the following Likert scale:

1 Not Influential

2 slightly Influential

3 Somewhat Influential

4 Very Influential

5 Extremely Influential

| LEVEL OF INFLUENCE ON SCHEDULE PERFORMANCE | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| 1. Deadline |  |  |  |  |  |
| 2. Budget. |  |  |  |  |  |
| 3. Stakeholders |  |  |  |  |  |
| 4. Project Members |  |  |  |  |  |
| 5. Demand |  |  |  |  |  |
| 6. Supply |  |  |  |  |  |
| 7. Price |  |  |  |  |  |
| 8. Resource availability |  |  |  |  |  |
| 9. Project complexity |  |  |  |  |  |
| 10. Task dependencies |  |  |  |  |  |
| 11. Team experience: |  |  |  |  |  |