COST OVERRUNS RESULTING FROM PAYMENT DELAYS IN GHANAIAN PUBLIC SCHOOL PROJECTS: EXPLORING THE COST BENEFITS TO THE CLIENT

BY

Prince-Charles Gbagbo

(BSc. Construction Technology and Management)

A thesis submitted to the Department of Construction Technology and Management, Kwame Nkrumah University of Science and Technology, Kumasi in partial fulfillment of the requirements for the award degree of

MASTER OF SCIENCE IN CONSTRUCTION MANAGEMENT

November 2019

# DECLARATION

I hereby declare that this submission is my own work towards the award of a Master of Science in Construction Management and that, to the best of my knowledge, it contains no material previously published or written by another person nor material which to a substantial extent has been accepted for the award of any other degree at Kwame Nkrumah University of Science and Technology, Kumasi or any other educational institution, except where due acknowledgment is made in the thesis.

PRINCE-CHARLES GBAGBO (PG5055018)………………      ………………… Name of Student and  ID                                         Signature 	           Date

Certified by

DR. GABRIEL NANI                                    ..…………………..      ………………… Name of Supervisor                           		           Signature 	      	 Date

Certified by

PROFESSOR B. K. BAIDEN                   ..…………………..      …………………

Name of Head of Department                                    Signature 		 Date

# ABSTRACT

The construction industry is plagued with the myriad occurrence of cost-related problems paramount of which is cost overruns. Many factors have been identified as the causes of and solutions to cost overrun. Principal among these factors is delayed payments. This research Sought to explore the cost benefits accrued to the client when payment is delayed. The cost data of 81 Ghanaian school projects were sampled through purposive sampling and analyzed in order to achieve the aim and objectives of the study. The findings are presented as follows: as regards objective 1, it was discovered that 91 % of the projects in the sample experienced cost overruns by an average of 52.90 %. A total of 91.36 % of projects sampled experienced schedule overruns by as much as 286.13%. Objective 2 involved the evaluation of cost trends in relation to schedule trends. It was discovered that a positive correlation exists between the cost trends and schedule trends. A rise in the schedule (time) resulted in a rise in cost. Further studies found that 38.18% of the variation in Cost is explained by the variation in Time, whereas 61.82 % is unexplained. It is recommended that the factors behind the unexplained 61.82% require further investigation to uncover. The following regression module was formulated to illustrate the relationship between cost and time trends: Percentage of Cost Variance = -0.006 + 0.187 (Percentage of Time Variance)

Objective 3 sought to explore cost-benefit accrued to the client when payments are delayed. It was determined that the average period of delay in honoring certificates was 24.54 months approximately two calendar years. The study also revealed that cost benefits average 39.89% of the certified amount are accrued to clients as a result of delayed payment. Also, the mean cost-benefit accrued to the clients resulting from delayed payment of final certificates was 32.05% of the certified final certificates. Overall the cost-benefit due the client resulting from delayed payment leading to cost overruns was revealed to be 1% of the contract sum.

Recommendations made as a result of the study include taking care through prudent management practices to prevent schedule overruns and hence preventing cost overruns.

Policies on payment for construction projects should be structured such that, delayed payments are discouraged. Note should be taken that value accruing to the client indicates value lost by the contractor.

Keywords: Cost Overrun, Schedule Overrun, Delayed Payment, Payment Certificate.

# TABLE OF CONTENTS

DECLARATION	ii

ABSTRACT	iii

TABLE OF CONTENTS	iv

LIST OF TABLES	vi

LIST OF FIGURES	vii

ACKNOWLEDGMENT	viii

DEDICATION	ix

CHAPTER ONE	1

INTRODUCTION	1

1.1 BACKGROUND TO THE STUDY	1

1.2 RESEARCH PROBLEM	2

1.3 RESEARCH QUESTIONS	3

1.4 AIM OF THE RESEARCH	3

1.5 OBJECTIVES	3

1.6 SIGNIFICANCE OF THE STUDY	4

1.7 SCOPE OF THE STUDY	4

1.5 BRIEF METHODOLOGY	4

1.6 ORGANIZATION OF CHAPTERS	5

CHAPTER TWO	6

LITERATURE REVIEW	6

2.1 INTRODUCTION	6

2.2 COST OVERRUNS	6

2.3 SCHEDULE DELAYS	8

2.4 DELAYED PAYMENT	12

CHAPTER THREE	14

METHODOLOGY	14

3.1 INTRODUCTION	14

3.2 RESEARCH PHILOSOPHY	14

3.3 FRAMEWORK OF THE RESEARCH	17

3.4 DATA COLLECTION	18

3.5 DATA ANALYSIS	19

3.6 INTEREST RATE:	21

3.7 COMPOUND AMOUNT FACTOR	22

3.8 PRESENT VALUE FACTOR	22

3.9 TESTS	22

3.10 SUMMARY	22

CHAPTER FOUR	23

ANALYSIS AND DISCUSSION OF RESULTS	23

4.1 INTRODUCTION	23

4.2 NATURE OF THE PROJECTS	24

4.3. COST PERFORMANCE OF PROJECTS	25

4.4 SCHEDULE PERFORMANCE	31

4.5 COST TRENDS AND CORRESPONDING SCHEDULE TRENDS OF THE SAMPLED PROJECTS	36

4.6 EXPLORING COST BENEFITS OF DELAYED PAYMENTS TO THE CLIENT	40

4.7 TIME VALUE ANALYSIS	54

CHAPTER FIVE	75

SUMMARY OF FINDINGS, CONCLUSION AND RECOMMENDATIONS	75

5.1 INTRODUCTION	75

5.2 SUMMARY OF RESEARCH PROCEDURE	75

5.3 SUMMARY OF RESEARCH FINDINGS	76

5.3 CONCLUSION	77

5.3 LIMITATIONS AND DELIMITAIONS	78

5.4 RECOMMENDATIONS	78

5.5 RECOMMENDATIONS FOR FURTHER STUDIES	79

REFERENCES	80

APPENDIX	87

# LIST OF TABLES

Table 2. 1 Causes of cost and time overruns	10

Table 3. 1 Research Paradigms: Terminologies, Methods and Data Collection Techniques	15

Table 3. 2 comparative analysis of research paradigms and philosophy	16

Table 4. 1Cost Performance Analysis	26

Table 4. 2 Statistical Description of percentage of cost variance	30

Table 4. 3 Schedule Performance Analysis	32

Table 4. 4 Statistical Description of percentage schedule variance	36

Table 4. 5 Coefficient of correlation	37

Table 4. 6 Regression Statistics	39

Table 4. 7 Payment Details (1 Certificate Considered)	41

Table 4. 8 Descriptive statistics of the period of delays	49

Table 4. 9 Descriptive statistics of  percentage period of delays in payment	50

Table 4. 10 Coefficient of correlation for variables	52

Table 4. 11 Descriptive statistics for Percentage of  Nvp Over Estimsted Cost	55

Table 4. 12 Time  Value of Money Analysis	56

# LIST OF FIGURES

Figure 4. 1 Nature of projects	24

Figure 4. 2 Cost Performance	30

Figure 4. 3 Schedule performance of projects	35

Figure 4. 4 Cost-Time Performance graph	36

Figure 4. 5 Interim payment Certificates considered	49

# ACKNOWLEDGMENT

I am grateful to the Almighty God for His Grace, divine guidance and protection throughout my period of study.

I also wish to express my sincere gratitude to Dr. Gabriel Nani, my project supervisor for his guidance, direction, and support throughout the project duration. I learned from him essential hard work ethics. Thank you very much for your relentless effort in making this project a success.

To the PPMC Family, thank you for your tolerance, support, and understanding during the period of this study.

To my parents especially my mom Miss Annie Adzie, thank you very much for your unrelenting love and support.

# DEDICATION

I dedicate this work to the ALMIGHTY GOD, my family and all those who contributed in diverse ways in making this study successful.

# CHAPTER ONE

# INTRODUCTION

## 1.1 BACKGROUND TO THE STUDY

A successful project is one that is completed within the estimated duration, budgeted cost and meets the satisfaction of all stakeholders (The Standish Group 2015). Cost and time are hence the most critical parameters in project delivery. However, many projects experience delays and exceed cost estimates to the displeasure of project participants. According to (Enshassi, 2009 ) Extensive research has been conducted on aspects of cost and time performance on construction projects and many indicators identified as contributory to the unsatisfactory performance of construction time and cost (Ammar et al. 2013).

According to (Peters et al., 2019) Clients worldwide though obligated contractually to timely pay for works executed have continuously breached this requirement. Payments are usually delayed or not honored at all. This ultimately has a tremendous effect on the contractors’ cash flow forecast and the chances of having the project completed. In 2012 the amount owed contractors in the UK being late or delayed payment exceeded USD 50 Billion, a sharp rise from the USD 26 recorded in 2008 (DBIS 2015), this trend is similar in China and other parts of the world as illustrated by (Peters et al., 2019).

Fugar and Agyakwah-Baah (2010)  identified the causes of project delays and ranked them in order of importance, they include; delayed honoring of payment certificates (ranked first), underestimation of project cost, undervaluation of how complex a projects is, difficulty in sourcing funds from financial institutions and poor supervision. Before the study by Fugar and Agyakwah-baah (2010), Frimpong et al. (2003) ranked monthly payment difficulties first as per response from contractors and consultants and ranked it second for overall importance. Other factors the researcher identified include; poor contractor management, poor technical performance, and escalation of material prices. Drawing from the above, “delayed honoring of payment certificates” is of critical importance in discussions regarding the performance of cost and time of construction projects and is of paramount interest to this study. There seem to be a continues trend of payment delays worldwide, this, however, presumes that there may be some favorable benefit for which the trend remains prevalent. This study, therefore, intends to explore these benefits.

## 1.2 RESEARCH PROBLEM

Delayed honoring of payment certificates has been identified as a cause of project delays (Frimpong et al. 2003) which translates into cost overruns. Cost overruns are always looked at in a negative light. whereas there could be a positive outcome of a sort from delayed payment to the client. This study seeks to identify the opportunity cost of cost overrun resulting from delayed payment or the cost benefits the Client is likely to benefit either intentionally or inadvertently from late or delayed payments. Understanding the opportunity cost of the cost overrun resulting from delayed payment could challenge the assertion that actual losses are made by clients. It could be argued that interest payments and or payment of fluctuation indicates additional payments, however, these interests paid (if there are), do not always offset the liabilities of the contractors. Delayed payments could be on works ongoing as well as completed works. In the case of completed works, the client is likely to resume full operation of the facilities hence debunking the accession of loss of revenue. For uncompleted works, assuming the delayed payments are considered loans from the contractors at the commercial rate, the interest due to the contractors may not measure up with commercial lending rates from financial institutions.  Bearing in mind that many contract forms make provisions for payment on delayed payments, these provisions are usually modified in datasheets or not adhered to at all. Whether the client pays interest on delayed payments or not, some gains may be made when payment is delayed.

## 1.3 RESEARCH QUESTIONS

These questions should be answered in order to achieve the aims of the study:

- Are there trends in the cost and time performance of public school projects?

- Are there similarities between the cost performance trends of projects and time performance trends?

- Are there any cost benefits of delayed payment accruing to the client?

## 1.4 AIM OF THE RESEARCH

This research aims to explore the cost benefits of delayed payment to the client resulting in cost overruns.

## 1.5 OBJECTIVES

To enable me to achieve the research aim, the following objectives have been formulated:

- To identify the cost and time performance trends of public school projects executed from 2010 to 2018

- To compare cost trends in relation to schedule trends of the sampled projects

- To explore the cost benefits of delayed payment accruing to the client

## 1.6 SIGNIFICANCE OF THE STUDY

This research is expected to investigate extents and trends in the cost performance of projects by comparing and analysis of actual results to plans and forecasts. It also seeks to explore cost-benefit enjoyed by clients when they default in honoring payments promptly. This knowledge will help formulate policy concerning payment for construction works.

## 1.7 SCOPE OF THE STUDY

The scope of the project was restricted to School projects funded by the Ghana Education Trust Fund of the Ministry of Education between 2010 and 2018. These projects were constructed using model designs and replicated across the various schools.

## 1.5 BRIEF METHODOLOGY

Purposive sampling was used to sample secondary data on cost information of school projects finance by the Ghana Education Trust Fund constructed nationwide. Projects executed between 2010 and 2018 were considered. Using Estimated cost at contracting as independent Variable, Cost performance analysis was conducted on each project and Variance analysis conducted for the entire sample. Regression and correlation were performed to identified trends and relationships. Investment appraisal techniques were as well applied in finding the present value of absolute costs as well as compounding cost values.

## 1.6 ORGANIZATION OF CHAPTERS

The study will be organized in the following order:

Chapter one: This will be an introduction to the research. The problem statement, aims, and objectives, justification, and methodology of the research were explored in this chapter.

Chapter two: Literature review; in this chapter, existing literature on cost and time performance were reviewed to help appreciate the extent of documented knowledge on the subject.

Chapter three:  The research methodology, type and sources of data and the methods of analysis were documented

Chapter four: analysis of survey results and deductions were made and presented.

Chapter five: Finally, the research findings, conclusions, and recommendations of the study are presented in this chapter

# CHAPTER TWO

# LITERATURE REVIEW

## 2.1 INTRODUCTION

Payment is expected whenever commercial services are rendered, how else would businesses thrive? Businesses all over the world are characterized by risks of delayed payments, in some cases, non-payment and the construction industry is no exception. This usually leads to cost overruns. The construction industry is plagued with the myriad occurrence of delayed payment in spite of contractual clauses formulated in various contract forms to mitigate this canker. Catalão et al., (2019) indicated that concerns are being raised about the occurrence and the motivation of Clients for cost overruns. As indicated in the previous chapter, this research is intended to explore cost benefits accrued to the client for which reason delayed payment for construction works has proliferated the construction industry across the Globe.  Previous studies conducted on the subject of delayed payment and cost overrun will, therefore, be analyzed in this chapter to ascertain varying points of view on the subject.

## 2.2 COST OVERRUNS

Cost variation is when the final cost of a project at completion varies from the estimated cost at inception. Cost overruns occur when this variation is positive, indicating that the amount spent on the project exceeds the forecasted cost (Catalão et al., 2019). They classified the causes of cost overruns as endogenous and exogenous, according to Catalão et al., (2019) extant literature concentrates mainly on the endogenous causes which are project characteristics (scope, client, project concept, planning, projections, changes and project duration). Although exogenous determinants (economic, political and environment of governance) have been alluded to in studies, these factors have not been adequately explored. (Skamris Holm and Flyvbjerg, 1997; Creedy et al., 2010; Odeck et al., 2015). Specifically categorizing exogenous determinants makes the study by Catalão et al., (2019) distinct. However, the ‘underlining motives” behind these factors have not been examined. Cost and non-cost benefits are likely the motivation for the incessant occurrence of exogenous factors.

Flyvbjerg et al. (2018) sought to answer five fundamental questions regarding cost overruns; what cost overrun is and how it is measured, the data required to measure cost overrun, how often cost overrun occurs and its size, the root causes and measures to avoid cost overrun. This paper responds to the criticism of methods and findings of Flyvbjerg et al., (2011) by  Love and Ahiaga-Dagbui (2018). They explained cost overrun as the estimated capital costs for an investment less the actual cost. The difference can be assessed in absolute or relative terms.  For measurement in absolute terms, cost overrun equals actual cost minus estimated cost. In relative terms, however, Cost overrun is the difference between actual and estimated capital costs for investment. Several baselines could be set for measuring cost overruns, the chosen baseline for assessing cost overrun depends primarily on what an individual wishes to understand and measure. Flyvbjerg et al. (2018) wanted to appreciate whether well-informed decisions were being made by decision-makers. They intended to understand whether the cost estimates on whose basis decision-makers decided to implement a project were accurate. The accuracy of the estimates demonstrated how informed decision-makers were, the decision criteria were as follows; having accurate estimates signifies being well-informed and the contrary signifying being ill-informed. The budget at decision making was set as the baseline for measurement cost overrun Flyvbjerg et al. (2002, 2004), Cantarelli et al. (2010), Flyvbjerg et al. (2009), Flyvbjerg and Budzier (2011), Flyvbjerg (2014). The point of setting a baseline for measuring cost overrun as indicated above was disputed by Love and Ahiaga-Dagbui (2018)  who maintained that the cost estimate at the time of award of the contract is set as a baseline. However, Flyvbjerg et al. (2018) clarified that the baselines may be set according to what the individual wished to understand and measure. The position of Love and Ahiaga-Dagbui (2018) regarding the point of the baseline as well as the clarification by  Flyvbjerg et al. (2018)  sets the direction as to the decision of baseline for this research. In analyzing cost overrun using these baselines, 86% of projects representing 9 out of ten experience cost overruns (Flyvbjerg et al. 2018; Flyvbjerg et al, 2011) this conclusion failed to satisfy Love and Ahiaga-Dagbui (2018)  however no counter hypothesis was postulated in this regard.

Stakeholders of capital projects have always been aware of the causes of cost overruns enumerated in literature. These causes include; scope changes, complex interfaces, archaeology, geology, bad weather, business cycles, it is also known to project professionals that the causes enumerated above can be mitigated to a very large extent. (Flyvbjerg et al. 2018). Professionals usually underestimate the causes and ways of mitigating them due to strategic misrepresentation, overconfidence bias, the planning fallacy(Ibid). they indicated that the main root causes of cost overrun were behavioral biased and not visible. They, however, did not investigate further into the motivation behind the behavioral bias.   (Kahneman et al., 2011; Flyvbjerg, 2008, 2013a).

## 2.3 SCHEDULE DELAYS

Assaf and Al-Hejji (2006) defined the delay in construction as the time overrun that occurs when the project is not completed within the estimated or forecasted completion date specified in the contract or beyond the agreed date for which the parties require delivery of the project. Several factors account for the delay in completing a project including the contractors' delivery, Procurement of materials, conditions at the site, how the parties coordinate, finance, contractual relations, and etc. (Kim et al., 2016). About seventy percent of construction projects experienced time overrun by between 10% and 30% of the original schedule. (Assaf and Al-Hejji, 2006)

The contractor perceives time delay as additional responsibility: the construction period is extended with additional overheads and other increasing expenses as a result of the longer duration of the project, the working capital of the contractor could also be stuck in one project hence restricting the contractor to that project (Skitmore and Al-Kharashi 2009). Clients usually measure the loss of revenue associated with delays in completing a project, however, this may not be the case for all projects. In as much as the original cost may increase when the original duration is exceeded, cost-benefit could as well be accumulated to the client.

Of much research conducted on the subject of schedule overrun, late payment by clients and variances of late payment such as financial management/constraints remains one of the recurring causes of delay. The table below illustrates the causes of project delays by researchers worldwide (Venkateswaran and Murugasan 2017):

### Table 2. 1 Causes of cost and time overruns

| SN | Researchers | country | Factors identified |
| --- | --- | --- | --- |
| 1 | Le-Hoai, Lee, and Lee (2008) | Vietnam | - Delays in honoring payment for completed works - Inefficient contract management practices - Archaic or inappropriate construction methods - Unexpected conditions on site - Inefficient supervision and management of the site - Errors in Design - Changes in Design - Variations - Poorly Done Estimates - Fluctuations in The Cost Of Inputs - Financial difficulties of contractor - Financial difficulties of owner - Government obstacles - Unavailability of skilled workers |
| 2 | Fugar and Agyakwa-Baah (2010) | Ghana | - Delay in honoring certificates - Underestimation of the costs of projects - Underestimation of the complexity of projects - Difficulty in accessing bank credit - Poor supervision - Underestimation of time for completion of projects by contractors - Shortage of materials - Poor professional management - The fluctuation of prices/rising cost of materials - 10. Poor site management |
| 3 | Singh (2009) | India | - Technical and natural factors - Contractual failures - Organizational/institutional failures - Economic factors |
| 4 | Ramanathan, Narayanan, and Idrus (2012 | Malaysia | - Consultants - Contractor - Finance - Owner/client - Project attributes - Projects - Relating to design - Organization - Deviations in policies/plans - Contractually related - Contractual Relationship - Environment - External factors - Government relationship - Labor/manpower - Materials - Plant/equipment - Scheduling and controlling |
| 5 | Choudhry, Nasir, and Gabriel (2012 | Pakistan | - Additional work - Inappropriate government policies - Not having priorities - Inappropriate planning - Fluctuation in the cost of inputs - Land purchase and relocation - Unpredictable cash flows - Slow decision making by the client - Design mistakes - Imprecise estimation - Transfer of services and utilities - Delay in payments - Harsh weather conditions, law, and order (force majeure) - Contractor’s inability delivery the project - Financial problems faced by clients - planning and scheduling inefficiencies - Variation in scope - Delay in site procession by the contractor - Delays in permit acquisition |
| 6 | Kishore, Rao, and Singh (2012) | India | - Procurement of land - Reports on projects - Contract associated problems - Management of finances - Lack or inadequate Capacity |
| 7 | Wijekoon and Attanayake (2012) | Sri Lanka | - Delay in Payment - Delay associated with having to shift existing utilities - escalation in cost - Changes in design in the course of construction - land acquisition difficulties |
| 8 | Mahamid and Bruland (2012) | Palestine | - Materials price fluctuation, inadequate time for preparation of an estimate - Knowledge in contract management - The magnitude of the contract - Unfinished drawings |
| 9 | Akoa (2011) | Cameroon | - Failure to visit sites prior to, during the bidding process to ascertain unknown site conditions - Feeble and inadequate technical studies - Unavailability of planning/programming - Underestimating of cost estimates and schedules/overestimating of profits - Unavailability equipment - Procedures of bidding |

Source: (Venkateswaran and  Murugasan, 2017)

## 2.4 DELAYED PAYMENT

Payment is defined as a mandatory trade of value, discharge, or compensation given from one company to another for services or goods or to fulfill a legal judgment (Peters et al., 2019). According to a literature review conducted, “Governance gap” has been identified as the reason for delayed payments (Peters et al., 2019, Cheng et al. 2010, Lip 2006, Wu 2008, Ansah 2011 Brand and Uher 2010, Ramachandra and Rotimi 2010, and Sin 2006). Closing this governance gap according to Peters et al., (2019) is a critical challenge. Effectively closing this gab requires the ability to change the mindset of stakeholders in the construction industry. These researchers have consistently identified a gap in legislation within various jurisdictions, however, the consistency of the problem of payment delays leaves a further void in research. Although the causes and effects of delayed payment have been identified, the motive for the persistent occurrence still remains a mystery.it is this void which is benefits accrued by project players that need to be solved.

Financial management and cash-flow training improved and amended legislation, and changes in local culture and attitude have been identified as remedies to address late-payment and nonpayment (Azman et al. 2014). Cable (2013) emphasized greater transparency between parties, the use of payment charters for the construction supply chain, and increased use of technology to improve payment cycles, Abrahams (2013) as well identified the importance of promoting ethical business practices, education, and training in financial management, and legislative intervention. Uff and Thornhill (2010) suggested implementing regular audits to identify financial shortcomings and introducing specialist courts to hasten dispute resolution. Uff and Thornhill (2010) also suggested replacing interim payment systems by contractually agreed upon milestone payments with appropriation conditions governing the right to payment. Although extensive research (Wu 2008; Cheng et al. 2010; Nazir 2006; Ansah 2011) has been undertaken on issues of late payment and nonpayment on construction works, the underlying motivation for the clients has not been dealt with. In spite of previous solutions brought forth in previous research, the problem of delayed payment continues, prompting the need to investigate the possible benefits clients enjoy for holding on to payments.

Although delayed payment impacts delivery of construction works, a better understanding of the underlying reason for delayed payment is recognizing that numerous complex factors are present in the construction industry and the application of solutions to curb them. (Sin 2006).   These cost benefits are being enjoyed either intentionally or unintentionally, as such unearthing them will influence policy in curbing this age-old problem of late payment leading to cost overruns in construction works

# CHAPTER THREE

# METHODOLOGY

## 3.1 INTRODUCTION

This chapter explains how the research was done in order to achieve its aim and objectives. Section 1 of the chapter deals with the assumptions and framework implemented for the study. According to Blumberg et al. (2005), the next essential step in any research process after reviewing the literature and identifying the research question is choosing a suitable methodology. Collis and Hussey, (2003) agreed that research methodology is the general approach to the design procedure from the hypothetical fundamentals to the collection of data and analysis adapted for a study. The methodology is, therefore, the way in which we discover how to go about the task of finding out what we believe to be true (Christou et al., 2008).  The sections  in this chapter are as follows:

- Research philosophy

- framework for the Research,

- design of research instrument and research design,

- data collection and analysis.

## 3.2 RESEARCH PHILOSOPHY

Philosophical paradigms involving epistemology, axiology, ontology and methodology assumptions need to be understood clearly considering that they determine the choice of research instruments (Christou, et al., 2008), thus the appropriate methods for a context and its underlying assumptions will be determined by these paradigms. Table 3.1 and Table 3.2 below summarizes the dimensions of research philosophy:

### Table 3. 1 Research Paradigms: Terminologies, Methods, and Data Collection Techniques

Source:  Žukauskas et al. (2018)

### Table 3. 2 comparative analysis of research paradigms and philosophy

Source:  Žukauskas et al. (2018)

This study adopts epistemology, ontological and axiological. Epistemology deals with how individuals define what is right (Streubert & Carpenter, 1999). Two main methods exist for epistemology namely; positivism and interpretivism, and are associated with quantitative and qualitative research. Positivism considers the social world as if it were a real, objective reality, in a way that laws can be found that explains this reality. According to this view, this real-world can be studied only through the utilization of methods that prevent human contamination of its understanding. Interpretivist paradigm, on the other hand, views the social world as one that individuals create, modify, and interpret the environment within which they function. In essence, the understanding is that this interaction of individuals and the environment can produce knowledge of phenomena under investigation through the accumulation of verified facts; (Bryman, 1992; Osei-Hwedie, 2010).

Objectivism was adopted for this research as regards ontology. Ontology refers to enquiring about the existence of a real-world that is sovereign of our knowledge; it is a theory of living beings (Marsh & Stoker, 2002). This is because the cost benefits of delayed payment exist as external happenings that are beyond the influence of the researcher. Also, trends in the cost performance of projects are objective realities that are not put in place by the researcher. Thus, in answering the research question: what are the cost benefits of delayed payments to the client on construction projects? The objectivism ontological position was followed.

Consequently, the research strategy adopted for this study is the quantitative (positivist) research approach to data collection and the analysis of data which is also link to the empirical framework for the studies

## 3.3 FRAMEWORK OF THE RESEARCH

According to Camp (2000), the research framework refers to the philosophical foundations on which the research is conducted and creates a relationship between the theoretical aspect and the practical elements of the research performed. However, the framework is identified or developed to increase understanding of the phenomena being observed and explaining them as simply as possible. It also deals with cognitive processes of discovering or manipulating intellectual categorization between relationships that form the basis for theorizing of all research. The theoretical framework, therefore, is key to this research in order to determine and aggregate the key questions in this study for the operationalization of the study variables.

Much preeminence is given to observation and data collection without considering theory thereby using evidence to induce generalization, this is because there hasn’t been any distinct theoretical framework in project management studies and practices of which cost management is embedded (Koskela and Howell, 2002). Hence the research position stems from developing an empirical framework because the research is built on empirical understanding. (Smyth and Morris, 2007). Therefore, empiricism framework was the best approach to be in this study because the research decouples itself from the existing belief systems (Ibid)

The reasoning behind the philosophical idea is that evidence is required, unlike thought or speech, in order to make a satisfactory claim to be added to knowledge (Pathirage, et al., 2008). Therefore, the study included the collection of real-life data and the collection of relevant evidence, thus drawing the conclusions of adding new knowledge to the body of knowledge. In this sense, the framework depends on several main themes of the study, which relate to several interrelated and interrelated research questions. A variable in one attribute can influence one variable in others and vice versa. These variables were assumed separately and collectively and examined as a study, understanding, opportunities, challenges and effective strategies. The framework deals with a series of independent variables with the central focal point with key actors and independent variables.

## 3.4 DATA COLLECTION

The sampling approach adopted for the study followed a sequential process (Teddlie and Yu 2007), involving first a purposeful sampling technique for the selection for participation in the selection of construction projects, followed by an evaluation of the cost details of these projects. Using school projects financed by the Ghana Education Trust Fund (GETFund) between 2014 and 2018 as a case study, the first objective identifies trends in the cost performance of these projects. This justifies the existence of a problem requiring a solution. Using projects completed on schedule as control and comparing the cost performance of delayed projects.

Purposive sampling is defined as the strategies by which the researcher exercises his or her judgment about who will provide the best viewpoint on the subject under consideration, and then intentionally invites those specific perspectives into the study, in the context of this research, specific perspectives were the specific projects under consideration for this study: These projects were selected on the basis of availability of credible information (Flyvbjerg et al, 2011).

## 3.5 DATA ANALYSIS

The principles of the time value of money espoused by Bailey et al (2004) were followed in formulating the following relationships.

To ascertain the cost overrun of each project, the following parameter were considering:

Estimated Cost (EC): This is the originally forecasted cost of the project. The forecasted cost is expected to suffice the project implementation over the contract duration this is the same as the contract Sum.

Actual Cost (FC): This is the cost at which the project is finally completed.

Contract Duration (FD): This is the originally forecasted duration of the project.

Actual Time (AT): This is the total duration at which the project was completed.

Start Date (SD): This is the date on which the project commenced

Expected Completion Date (ECD): this is the date on which the contract duration ends

Actual Completion Date (ACD): This is the date on which the project was completed. For the purpose of this study, the ACD shall be the date of the penultimate certificate.

Value at Expected Completion (VAC): This is the value of the Actual Cost at the Expected completion date.

Net Value at Expected Completion (NVEC):  This is the Value of expected completion less the contract sum. This is the same as the net present value. This was drawn and modified from the principle of Net present value (Murdick 1973)

In order to achieve objective 1, the following steps were taken;

Step 1. evaluate the direct cost performance of the project, the following steps were followed

Cost Performance (CP) = AC – EC

CP > 1: Cost Overrun

CP < 1: Cost Underrun

CP = 0: Break Even

Step 2: Discount the value of AC to the Expected Completion date using investment appraisal.

This is to ascertain whether the Estimated cost changed as a result of schedule overrun

Thus,

VAC = Present Value factor   X   Actual Cost

NVEC = VAC – EC

NVEC > 1 = Cost Overrun

NVEC < 1 = Cost Underrun

Step 3. Comparing the trends of Step 2 and Step 3 to draw a conclusion.

For objective 2, the cost trends for projects identified to be completed on time will be compared to the cost trends of projects delayed and draw conclusions.

For Objective 3,

Step 1.

Determination of period of delayed payments.

Delayed Duration (DD) = Date of Payment – Date of issue of the certificate

Step 2.

To determine the value of the certificate after the delayed duration (DD)

Appreciated Cost (AC)= Compound amount factor X Certified Amount (CA)

Dependent Variable = Appreciated Cost

Independent Variable = Certified Amount

Constant Variable = Compound Amount Factor

To ascertain the value appreciated  (VG)to the Client,

VG = AC – CA

Please note that

VG = Opportunity Cost of payment of the certificate

Therefore, Value Gained by Client =Cost benefit of delayed payment to the client.

## 3.6 INTEREST RATE:

The interest rate to be applied to the compound factor and discount factor is the prevailing policy rate from the bank of Ghana. Not should be taken that, the base rate from the bank of Ghana is lower than the commercial lending rate of the banks.

## 3.7 COMPOUND AMOUNT FACTOR

The compound amount factor is used to calculate the result of investing a certain amount of money a period of years.

(1+i) n

(1+i) n

Where i = Interest Rate

n = Number of Months

source: (Bailey et al, 2004)

1/(1+i) n

Present Value Factor 1/(1+i)n

1/(1+i) n

Present Value Factor 1/(1+i)n

3.8 PRESENT VALUE FACTOR

Where i = Interest Rate

n = Number of Months

source: (Bailey et al, 2004)

## 3.9 TESTS

Different data were examined for corroborating shreds of evidence and contradictions. Correlation and regression tests were used to compare observed and expected frequencies objectively since it is not always possible to tell just by looking whether data is "different enough" to be considered statistically significant.

## 3.10 SUMMARY

This chapter outlined key elements that are very important in deciding a suitable research methodology to address any research problem. The research the underlying philosophical assumptions of the research methods and framework linking the variables indicates the methodology adopted for the study; The analytical techniques adopted for the study has also been explained.

# CHAPTER FOUR

# ANALYSIS AND DISCUSSION OF RESULTS

## 4.1 INTRODUCTION

This chapter provides a detailed explanation of the results of the study and relating the findings to the Ghanaian construction industry. The chapter is in three sections, which represents the various analysis and findings in relation to the specific objectives set as follows:

- Cost and schedule performance analysis of projects

- Comparison of cost trends in relation to schedule trends of the sampled projects

- Exploring cost benefits of delayed payments to the Client

The analysis for the study was carried out quantitatively and comparatively. The main tool used for analyzing the result was Microsoft Excel (Excel 2016)

The parameters of the sampled projects considered in the evaluation include:

- The estimated cost of the projects

- Actual Cost expended as at the day of analysis

- Expected completion date

- Actual Completion date

- Date of certification

- Date of payment

## 4.2 NATURE OF THE PROJECTS

A total of 81 projects were sampled for the study as illustrated in the figure below:

##### Figure 4. 1 Nature of projects

(Source: Survey)

8 no. representing 10% of the sampled projects were pre-designed administration blocks replicated in pre-tertiary institutions nationwide.

22 no.  making up 27% of the sampled projects were pre-designed classroom blocks replicated in pre-tertiary institutions nationwide

5 no. representing 6% of the sampled projects were pre-designed Dining halls with kitchen replicated in pre-tertiary institutions nationwide.

26 no. representing 32% of the sampled projects were pre-designed Dormitory Blocks replicated in pre-tertiary institutions nationwide.

2 no. representing 3% of the sampled projects were pre-designed Laboratory Blocks replicated in pre-tertiary institutions nationwide.

1 no. representing 1% of the sampled projects were pre-designed Mechanized Boreholes with storage tanks replicated in pre-tertiary institutions nationwide.

2 no. representing 3% of the sampled projects were pre-designed Perimeter fence wall replicated in pre-tertiary institutions nationwide.

1 no. representing 1% of the sampled projects was renovation works done in pre-tertiary institutions nationwide.

14 no. representing 17% of the sampled projects were pre-designed Dining halls replicated in pre-tertiary institutions nationwide.

## 4.3. COST PERFORMANCE OF PROJECTS

Data analysis on cost performance was conducted in two parts; 1. on individual projects and on the collective projects. The parameters considered in the analysis include;

- The estimated cost of the projects

- Actual Cost at Completion of the project

- Expected completion date

- Actual Completion date

Cost variance analysis was conducted for individual projects as illustrated in the table below:

### Table 4. 1Cost Performance Analysis

| No. | Estimated Cost (A) | Actual Cost (B) | Cost Variance (C=B-A) | Percentage Cost Variance |
| --- | --- | --- | --- | --- |
| 1 | 1,878,000.11 | 2,408,117.87 | 530,117.76 | 28% |
| 2 | 1,398,385.85 | 1,408,641.19 | 10,255.34 | 1% |
| 3 | 483,381.98 | 1,611,236.30 | 1,127,854.33 | 233% |
| 4 | 210,689.15 | 477,167.16 | 266,478.01 | 126% |
| 5 | 695,489.91 | 1,309,166.86 | 613,676.95 | 88% |
| 6 | 998,861.51 | 1,040,542.13 | 41,680.61 | 4% |
| 7 | 246,370.37 | 262,320.32 | 15,949.95 | 6% |
| 8 | 799,871.46 | 794,043.65 | - 5,827.81 | -1% |
| 9 | 558,740.33 | 969,058.82 | 410,318.48 | 73% |
| 10 | 488,167.35 | 495,703.84 | 7,536.49 | 2% |
| 11 | 507,781.45 | 515,776.04 | 7,994.59 | 2% |
| 12 | 1,073,819.23 | 1,152,509.06 | 78,689.83 | 7% |
| 13 | 953,514.82 | 1,152,790.75 | 199,275.93 | 21% |
| 14 | 852,864.50 | 876,478.35 | 23,613.85 | 3% |
| 15 | 1,399,214.21 | 1,772,321.24 | 373,107.03 | 27% |
| 16 | 947,518.82 | 1,141,401.03 | 193,882.21 | 20% |
| 17 | 877,185.54 | 908,573.64 | 31,388.10 | 4% |
| 18 | 733,811.86 | 784,493.89 | 50,682.03 | 7% |
| 19 | 1,396,098.85 | 1,661,451.10 | 265,352.25 | 19% |
| 20 | 941,728.32 | 1,152,450.31 | 210,721.99 | 22% |
| 21 | 730,411.54 | 782,772.34 | 52,360.80 | 7% |
| 22 | 139,826.04 | 257,976.07 | 118,150.03 | 84% |
| 23 | 519,072.96 | 743,435.04 | 224,362.08 | 43% |
| 24 | 119,884.77 | 376,423.46 | 256,538.69 | 214% |
| 25 | 560,941.02 | 1,484,021.58 | 923,080.56 | 165% |
| 26 | 976,512.38 | 938,783.16 | - 37,729.22 | -4% |
| 27 | 484,443.25 | 695,444.29 | 211,001.04 | 44% |
| 28 | 606,997.02 | 1,657,469.33 | 1,050,472.31 | 173% |
| 29 | 756,446.19 | 772,191.10 | 15,744.91 | 2% |
| 30 | 981,424.32 | 981,532.93 | 108.61 | 0% |
| 31 | 447,891.95 | 450,625.69 | 2,733.74 | 1% |
| 32 | 764,657.97 | 881,121.86 | 116,463.89 | 15% |
| 33 | 1,455,409.32 | 2,335,093.86 | 879,684.54 | 60% |
| 34 | 1,330,000.00 | 1,461,298.45 | 131,298.45 | 10% |
| 35 | 938,308.00 | 960,745.84 | 22,437.84 | 2% |
| 36 | 1,290,933.82 | 1,387,120.40 | 96,186.58 | 7% |
| 37 | 972,764.27 | 1,105,477.43 | 132,713.16 | 14% |
| 38 | 1,791,282.98 | 1,930,387.78 | 139,104.80 | 8% |
| 39 | 242,213.06 | 601,535.63 | 359,322.57 | 148% |
| 40 | 918,170.41 | 883,170.41 | - 35,000.00 | -4% |
| 41 | 1,293,420.52 | 1,500,519.23 | 207,098.71 | 16% |
| 42 | 1,293,660.93 | 1,508,370.64 | 214,709.71 | 17% |
| 43 | 999,500.00 | 1,283,686.93 | 284,186.93 | 28% |
| 44 | 1,499,692.77 | 1,671,083.69 | 171,390.92 | 11% |
| 45 | 701,645.82 | 1,353,159.32 | 651,513.50 | 93% |
| 46 | 755,188.26 | 927,529.39 | 172,341.13 | 23% |
| 47 | 519,947.19 | 1,175,283.12 | 655,335.93 | 126% |
| 48 | 1,658,495.97 | 1,734,748.98 | 76,253.01 | 5% |
| 49 | 1,190,000.00 | 2,119,858.94 | 929,858.94 | 78% |
| 50 | 199,358.43 | 508,977.83 | 309,619.40 | 155% |
| 51 | 259,080.00 | 553,421.33 | 294,341.33 | 114% |
| 52 | 550,700.64 | 597,896.45 | 47,195.81 | 9% |
| 53 | 1,101,279.85 | 1,801,111.61 | 699,831.76 | 64% |
| 54 | 989,842.92 | 1,636,683.55 | 646,840.63 | 65% |
| 55 | 609,593.64 | 950,321.22 | 340,727.58 | 56% |
| 56 | 597,223.00 | 1,041,845.69 | 444,622.69 | 74% |
| 57 | 875,325.72 | 1,066,400.06 | 191,074.34 | 22% |
| 58 | 1,483,244.61 | 1,714,254.54 | 231,009.93 | 16% |
| 59 | 799,336.02 | 799,336.02 | 0 | 0% |
| 60 | 1,489,662.85 | 1,645,047.24 | 155,384.39 | 10% |
| 61 | 650,053.58 | 650,053.58 | 0 | 0% |
| 62 | 899,800.00 | 2,009,327.16 | 1,109,527.16 | 123% |
| 63 | 443,907.13 | 677,151.93 | 233,244.80 | 53% |
| 64 | 340,000.00 | 558,196.31 | 218,196.32 | 64% |
| 65 | 146,933.45 | 604,219.53 | 457,286.08 | 311% |
| 66 | 575,413.07 | 529,150.29 | - 46,262.78 | -8% |
| 67 | 986,906.71 | 1,456,969.40 | 470,062.69 | 48% |
| 68 | 662,604.92 | 1,150,401.86 | 487,796.94 | 74% |
| 69 | 1,500,000.00 | 2,072,455.95 | 572,455.95 | 38% |
| 70 | 861,034.02 | 1,610,093.98 | 749,059.96 | 87% |
| 71 | 1,548,414.22 | 1,660,653.35 | 112,239.13 | 7% |
| 72 | 695,000.00 | 1,888,272.59 | 1,193,272.59 | 172% |
| 73 | 590,755.84 | 547,489.81 | - 43,266.03 | -7% |
| 74 | 515,075.67 | 1,286,323.09 | 771,247.42 | 150% |
| 75 | 351,383.82 | 700,078.98 | 348,695.16 | 99% |
| 76 | 544,572.90 | 1,505,980.24 | 961,407.34 | 177% |
| 77 | 989,514.65 | 1,058,590.97 | 69,076.32 | 7% |
| 78 | 466,900.47 | 528,108.79 | 61,208.32 | 13% |
| 79 | 519,432.55 | 1,113,486.95 | 594,054.40 | 114% |
| 80 | 567,553.29 | 768,137.49 | 200,584.20 | 35% |
| 81 | 360,000.00 | 589,192.50 | 229,192.50 | 64% |

(Source: Survey)

Based on the cost performance analysis performed for the individual project in table 4.1 above, collective analysis for the projects was conducted as follows;

##### Figure 4. 2 Cost Performance

(Source: Survey)

74 no. representing 91% of the sampled projects experienced cost overrun.

5no. representing 6% of the sampled projects experienced cost underrun

2no. representing 3% of the sampled projects had break-even costs.

In the observation above, 91% of the sampled projects experienced cost overrun, this is in line with the findings of  Flyvbjerg et al. 2011 and Flyvbjerg et al. 2018   who indicated that 86% of projects representing 9 out of ten experience cost overruns.

### Table 4. 2 Statistical Description of percentage of cost variance

| Mean | 0.5290 |
| --- | --- |
| Standard Error | 0.0719 |
| Median | 0.2237 |
| Mode | 0 |
| Standard Deviation | 0.6473 |

(Source: Excel Data Analysis)

Preliminary descriptive analysis such as mean scores, standard deviations and standard mean error conducted on the variables was used to describe the outcome of the survey (Table 4.2); The significance level was set at 95% in accordance with predictable risk levels (Cohen, 1992). The mean cost overrun from the projects sampled was 0.529 thus 52.90 %. The standard error is the standard deviation of sample means and it is a degree of how representative a sample is likely to be of the population (Field, 2005). A large standard error reflects a lot of variability between means of different samples and a small standard error suggests that most sample means are similar to the population mean and so the sample is likely to be an accurate reflection of the population (Ibid). From table 4.2 above, it is safe to conclude that considering a standard error of 0.0719, the mean percentage cost variance of 52.90% is a reflection of the cost performance of the population.

The standard error was very minimal suggesting that the sample chosen is an accurate reflection of the population. There is little variability in the data collected and consistency in agreement among the individual projects sampled.

## 4.4 SCHEDULE PERFORMANCE

The following table illustrates the Schedule variance analysis carried out for the sampled projects:

### Table 4. 3 Schedule Performance Analysis

| Project No. | Estimated Duration | Expected Completion Date | Actual Completion (Date of Practical Completion) | Additional Time Elapsed (T) In Months | Percentage of Time Variance |
| --- | --- | --- | --- | --- | --- |
| 1 | 12 | 23-11-17 | 03-05-19 | 17 | 141.67% |
| 2 | 12 | 26-02-17 | 08-08-19 | 29 | 241.67% |
| 3 | 10 | 22-04-12 | 07-03-17 | 58 | 580.00% |
| 4 | 8 | 01-05-15 | 15-02-16 | 9 | 112.50% |
| 5 | 12 | 22-11-12 | 15-08-16 | 44 | 366.67% |
| 6 | 12 | 20-07-16 | 17-08-16 | 0 | 0.00% |
| 7 | 8 | 21-11-12 | 24-11-16 | 48 | 600.00% |
| 8 | 12 | 29-05-16 | 14-07-17 | 13 | 108.33% |
| 9 | 12 | 15-03-12 | 15-11-15 | 44 | 366.67% |
| 10 | 8 | 26-02-17 | 12-03-19 | 24 | 300.00% |
| 11 | 8 | 26-02-17 | 15-09-19 | 30 | 375.00% |
| 12 | 12 | 30-06-17 | 01-07-17 | 0 | 0.00% |
| 13 | 12 | 03-03-15 | 14-06-18 | 39 | 325.00% |
| 14 | 12 | 28-02-15 | 14-07-17 | 28 | 233.33% |
| 15 | 12 | 20-12-15 | 22-11-18 | 35 | 291.67% |
| 16 | 12 | 20-12-15 | 23-11-18 | 35 | 291.67% |
| 17 | 12 | 20-12-15 | 22-11-18 | 35 | 291.67% |
| 18 | 12 | 20-12-15 | 22-11-18 | 35 | 291.67% |
| 19 | 12 | 20-12-15 | 22-11-18 | 35 | 291.67% |
| 20 | 12 | 20-12-15 | 22-11-18 | 35 | 291.67% |
| 21 | 12 | 20-12-15 | 22-11-18 | 35 | 291.67% |
| 22 | 8 | 19-11-11 | 08-11-16 | 59 | 737.50% |
| 23 | 12 | 06-01-12 | 07-11-16 | 58 | 483.33% |
| 24 | 8 | 19-11-11 | 11-11-16 | 59 | 737.50% |
| 25 | 12 | 13-05-12 | 06-02-19 | 80 | 666.67% |
| 26 | 12 | 26-11-16 | 28-11-16 | 0 | 0.00% |
| 27 | 10 | 25-11-15 | 01-03-16 | 3 | 30.00% |
| 28 | 12 | 04-01-12 | 16-11-16 | 58 | 483.33% |
| 29 | 12 | 25-12-14 | 04-11-16 | 22 | 183.33% |
| 30 | 10 | 31-10-16 | 20-08-19 | 33 | 330.00% |
| 31 | 8 | 30-06-16 | 20-08-19 | 37 | 462.50% |
| 32 | 8 | 03-01-16 | 22-09-17 | 20 | 250.00% |
| 33 | 12 | 18-03-16 | 07-04-17 | 12 | 100.00% |
| 34 | 12 | 25-01-17 | 01-02-17 | 0 | 0.00% |
| 35 | 12 | 01-10-16 | 06-12-17 | 14 | 116.67% |
| 36 | 12 | 26-01-16 | 30-08-19 | 43 | 358.33% |
| 37 | 12 | 11-11-16 | 18-11-16 | 0 | 0.00% |
| 38 | 12 | 11-11-16 | 14-11-16 | 0 | 0.00% |
| 39 | 8 | 17-09-12 | 18-10-16 | 49 | 612.50% |
| 40 | 12 | 12-02-13 | 27-11-15 | 33 | 275.00% |
| 41 | 12 | 10-11-16 | 29-05-17 | 6 | 50.00% |
| 42 | 12 | 12-11-16 | 11-10-17 | 10 | 83.33% |
| 43 | 12 | 30-06-17 | 19-07-18 | 12 | 100.00% |
| 44 | 18 | 15-02-17 | 05-09-17 | 6 | 33.33% |
| 45 | 12 | 20-03-13 | 20-06-16 | 39 | 325.00% |
| 46 | 12 | 01-12-15 | 19-01-16 | 1 | 8.33% |
| 47 | 12 | 29-06-12 | 05-10-16 | 51 | 425.00% |
| 48 | 18 | 06-12-17 | 20-08-19 | 20 | 111.11% |
| 49 | 12 | 15-04-17 | 23-11-18 | 19 | 158.33% |
| 50 | 8 | 22-08-14 | 22-03-17 | 31 | 387.50% |
| 51 | 8 | 01-11-12 | 12-10-17 | 59 | 737.50% |
| 52 | 12 | 24-10-12 | 09-10-18 | 71 | 591.67% |
| 53 | 12 | 26-05-16 | 28-03-17 | 10 | 83.33% |
| 54 | 12 | 20-07-15 | 23-02-17 | 19 | 158.33% |
| 55 | 12 12 | 22-01-15 | 07-03-18 | 37 | 308.33% |
| 56 | 10 | 01-06-13 | 09-05-17 | 47 | 470.00% |
| 57 | 10 | 16-10-15 | 20-02-18 | 28 | 280.00% |
| 58 | 12 | 15-03-16 | 13-06-17 | 14 | 116.67% |
| 59 | 12 | 24-03-16 | 22-09-17 | 17 | 141.67% |
| 60 | 18 | 19-03-17 | 21-06-18 | 15 | 83.33% |
| 61 | 8 | 10-04-17 | 11-06-19 | 26 | 325.00% |
| 62 | 12 | 28-03-12 | 27-02-17 | 58 | 483.33% |
| 63 | 12 | 25-06-12 | 09-03-16 | 44 | 366.67% |
| 64 | 12 | 01-04-12 | 29-01-16 | 45 | 375.00% |
| 65 | 8 | 28-03-12 | 07-11-16 | 55 | 687.50% |
| 66 | 12 | 10-06-12 | 26-09-12 | 3 | 25.00% |
| 67 | 12 | 17-06-16 | 23-10-16 | 4 | 33.33% |
| 68 | 10 | 12-05-13 | 03-05-19 | 71 | 710.00% |
| 69 | 18 | 13-10-16 | 30-10-17 | 12 | 66.67% |
| 70 | 12 | 23-07-16 | 12-03-17 | 7 | 58.33% |
| 71 | 12 | 07-10-17 | 24-01-19 | 15 | 125.00% |
| 72 | 12 | 01-10-12 | 29-06-17 | 56 | 466.67% |
| 73 | 12 | 04-06-15 | 14-12-16 | 18 | 150.00% |
| 74 | 10 | 01-04-13 | 04-09-17 | 53 | 530.00% |
| 75 | 12 | 24-06-12 | 02-11-18 | 76 | 633.33% |
| 76 | 12 | 08-03-13 | 16-08-18 | 65 | 541.67% |
| 77 | 12 | 07-10-16 | 14-07-17 | 9 | 75.00% |
| 78 | 8 | 15-10-16 | 10-11-16 | 0 | 0.00% |
| 79 | 12 | 17-02-12 | 22-08-16 | 54 | 450.00% |
| 80 | 12 | 22-06-12 | 09-05-16 | 46 | 383.33% |
| 81 | 12 | 22-06-12 | 16-12-16 | 53 | 441.67% |

(Source: Survey)

From the schedule performance analysis performed for the individual project in table 4.3 above, the summary is illustrated as follows;

##### Figure 4. 3 Schedule performance of projects

(Source: Survey)

From the Figure above, the following deductions can be made:

7no. representing 8.64% of the sampled projects were completed on schedule

74no. representing 91.36% of the sampled projects were delayed

According to Assaf and Al-Hejji, 2006,  About seventy percent of construction projects experienced time overrun by between 10% and 30% of the original schedule, hence observation of 91.36 % is in range with existing trends discovered by previous studies. However, this study recorded a mean schedule variance of 2.86129 (Table 4.4) thus 286.129%, this figure far exceeds the 10% to 30% trend in the existing literature.

### Table 4. 4 Statistical Description of percentage schedule variance

| Mean | 2.864129 |
| --- | --- |
| Standard Error | 0.237961 |
| Median | 2.916667 |
| Standard Deviation | 2.141651 |

(Source: Excel Analysis)

## 4.5 COST TRENDS AND CORRESPONDING SCHEDULE TRENDS OF THE SAMPLED PROJECTS

Cost trends in relation to corresponding scheduled trends were evaluated as follows:

##### Figure 4. 4 Cost-Time Performance graph

(Source: Survey)

The cost-time line graph of the in figure 4.4 above indicates that a rise in time translates into a slower rise in cost.  Nevertheless, there exists a possibility that these observations might not be entirely conclusive and be the correct reflection of the whole population. As such, it was necessary to conduct further examination using an appropriate statistical technique.

The coefficient of correlation as well as the goodness of fit test was conducted for the cost and time variables (Table 4.5)

### Table 4. 5 Coefficient of correlation

|  | Percentage of Cost Variance | Expected Completion Date | Actual Completion Date | Additional Time Elapsed (T) In Months |
| --- | --- | --- | --- | --- |
| Percentage of Cost Variance | 1 |  |  |  |
| Expected Completion Date | -0.64367398 | 1 |  |  |
| Actual Completion Date | -0.19692843 | 0.456846656 | 1 |  |
| Additional Time Elapsed (T) In Months | 0.578017892 | -0.795367166 | 0.175688 | 1 |
| Percentage Time Variance | 0.61790991 | -0.771099764 | 0.148920 | 0.955005933 |

(Source: Excel Analysis)

From the table above, it is observed that, the coefficient of correlation (r) between the percentage of cost variance and percentage of time variance 0.618. this implies that the correlation between the two variables is a moderate or fair positive correlation. This indicates that a rise in the percentage of cost variance tends to cause a positive rise in the percentage of time variance.

The coefficient of determination was analyzed to determine causation between the percentage of cost variance and the percentage of time variance as follows:

CD = r2

CD = (0.6179)2

Thus CD = 0.3818

Hence: 0.3818 = 38.18 %

This Therefore implies that: 38.18% of the variation in the percentage of cost variance is explained by the variation in the percentage of time variance. While 61.82% is unexplained.

It is, therefore, safe to infer that 38.18% of the variation in Cost is explained by the variation in Time. There is, therefore, a need for an investigation into the unexplained 61.82% explanation to variation in cost.

A simple linear regression analysis was conducted on the percentage of cost variance and percentage of time variance to ascertain the relationship between cost and time performance.

The data from the regression statistics (Table 4.6) performed was used to formulate a prediction model for the time variance percentage and cost variance percentage as follows:

Ŷ = a + bX

where Y = the dependent variable (that's the variable that goes on the Y-axis),

X = the independent variable (i.e. it is plotted on the X-axis)

a = the y-intercept

b = the slope of the line

This implies that:

Percentage of Cost Variance = y-intercept + slope of the line (Percentage of Time Variance)

Deducing from table 4.6 below,

Percentage of Cost Variance = -0.006 + 0.187 (Percentage of Time Variance)

### Table 4. 6 Regression Statistics

| Multiple R | 0.618 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R Square | 0.382 |  |  |  |  |  |  |
| Adjusted R Square | 0.374 |  |  |  |  |  |  |
| Standard Error | 0.512 |  |  |  |  |  |  |
| Observations | 81.000 |  |  |  |  |  |  |
| ANOVA |  |  |  |  |  |  |  |
|  | df | SS | MS | F | Significance F |  |  |
| Regression | 1.000 | 12.802 | 12.802 | 48.793 | 0.000 |  |  |
| Residual | 79.000 | 20.727 | 0.262 |  |  |  |  |
| Total | 80.000 | 33.529 |  |  |  |  |  |
|  | Coefficients | Standard Error | t Stat | P-value | Lower 95% | Upper 95% | Upper 95.0% |
| Intercept | -0.006 | 0.095 | -0.062 | 0.951 | -0.196 | 0.184 | 0.184 |
| Percentage Time Variance (X) | 0.187 | 0.027 | 6.985 | 0.000 | 0.134 | 0.240 | 0.240 |

(Source: Excel Analysis)

## 4.6 EXPLORING COST BENEFITS OF DELAYED PAYMENTS TO THE CLIENT

The cost benefits accrued to the client as a result of delayed payment was analyzed by determining the value of the certificate at the time of payment compounded monthly. The prevailing Monetary Policy Rate of 16% (BOG, 2019) was applied as the rate for the computations.

### Table 4. 7 Payment Details (1 Certificate Considered)

| Proj No. | Date of Cert | Date Honored | Amount Certified | IPC No | Period of Delay (D) in Months | Compound Amount Per D period of delay | Appreciated Cost (Cost-Benefit to the Client) | Percentage of Amount of certified Appreciation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 10-05-17 | 01-05-19 | 128,223.33 | 2 | 23 | 173,888.40 | 45,665.07 | 35.61% |
| 2 | 01-08-16 | 01-05-19 | 513,647.88 | 2 | 33 | 795,229.26 | 281,581.38 | 54.82% |
| 3 | 10-10-16 | 01-05-19 | 356,405.86 | 6 | 30 | 530,291.54 | 173,885.68 | 48.79% |
| 4 | 07-11-16 | 01-05-19 | 25,240.60 | 3 | 29 | 37,061.01 | 11,820.41 | 46.83% |
| 5 | 28-08-16 | 01-05-19 | 106,346.65 | 4 | 32 | 162,479.41 | 56,132.76 | 52.78% |
| 6 | 17-08-16 | 01-05-19 | 300,822.31 | 2 | 32 | 459,604.82 | 158,782.50 | 52.78% |
| 7 | 24-11-16 | 01-05-19 | 95,708.00 | 3 | 29 | 140,528.94 | 44,820.94 | 46.83% |
| 8 | 14-07-17 | 01-05-19 | 466,280.74 | 2 | 21 | 615,809.50 | 149,528.76 | 32.07% |
| 9 | 17-08-16 | 01-05-19 | 376,739.57 | 4 | 32 | 575,593.34 | 198,853.77 | 52.78% |
| 10 | 15-08-16 | 01-06-19 | 237,780.73 | 1 | 33 | 368,131.95 | 130,351.22 | 54.82% |
| 11 | 22-08-16 | 01-06-19 | 236,968.93 | 1 | 33 | 366,875.12 | 129,906.19 | 54.82% |
| 12 | 15-08-16 | 01-05-19 | 337,925.43 | 1 | 32 | 516,292.00 | 178,366.57 | 52.78% |
| 13 | 14-06-18 | 01-08-19 | 522,448.34 | 3 | 13 | 620,616.95 | 98,168.61 | 18.79% |
| 14 | 14-07-17 | 01-05-19 | 651,529.93 | 2 | 21 | 860,465.13 | 208,935.20 | 32.07% |
| 15 | 22-11-18 | 01-07-19 | 238,586.23 | 5 | 7 | 261,765.06 | 23,178.83 | 9.72% |
| 16 | 22-11-18 | 01-08-19 | 149,410.91 | 5 | 8 | 166,111.98 | 16,701.07 | 11.18% |
| 17 | 22-11-18 | 01-07-19 | 174,017.43 | 4 | 7 | 190,923.35 | 16,905.92 | 9.72% |
| 18 | 22-11-18 | 01-07-19 | 148,826.64 | 5 | 7 | 163,285.26 | 14,458.62 | 9.72% |
| 19 | 22-11-18 | 01-07-19 | 231,369.23 | 5 | 7 | 253,846.92 | 22,477.69 | 9.72% |
| 20 | 22-11-18 | 01-07-19 | 157,966.87 | 5 | 7 | 173,313.47 | 15,346.60 | 9.72% |
| 21 | 22-11-18 | 01-07-19 | 167,987.11 | 5 | 7 | 184,307.19 | 16,320.07 | 9.72% |
| 22 | 08-11-16 | 01-05-19 | 185,363.47 | 3 | 29 | 272,170.90 | 86,807.43 | 46.83% |
| 23 | 07-11-16 | 01-05-19 | 25,953.65 | 7 | 29 | 38,107.98 | 12,154.33 | 46.83% |
| 24 | 11-11-16 | 01-05-19 | 139,129.23 | 3 | 29 | 204,284.74 | 65,155.51 | 46.83% |
| 25 | 06-02-19 | 01-07-19 | 986,109.46 | 3 | 4 | 1,039,763.20 | 53,653.74 | 5.44% |
| 26 | 07-11-16 | 01-05-19 | 130,131.37 | 3 | 29 | 191,073.10 | 60,941.73 | 46.83% |
| 27 | 25-11-16 | 01-07-19 | 49,640.18 | 4 | 31 | 74,843.75 | 25,203.57 | 50.77% |
| 28 | 07-11-16 | 01-05-19 | 470,797.40 | 9 | 29 | 691,276.18 | 220,478.78 | 46.83% |
| 29 | 04-11-16 | 01-05-19 | 162,214.34 | 4 | 29 | 238,180.82 | 75,966.48 | 46.83% |
| 30 | 15-09-16 | 01-05-19 | 300,092.89 | 2 | 31 | 452,457.61 | 152,364.72 | 50.77% |
| 31 | 15-09-16 | 01-06-19 | 315,897.97 | 2 | 32 | 482,637.83 | 166,739.86 | 52.78% |
| 32 | 01-11-16 | 01-05-19 | 137,317.89 | 3 | 30 | 204,313.46 | 66,995.57 | 48.79% |
| 33 | 28-09-18 | 01-08-19 | 95,491.04 | Final | 10 | 109,014.91 | 13,523.87 | 14.16% |
| 34 | 18-12-16 | 01-05-19 | 601,428.73 | 3 | 28 | 871,463.86 | 270,035.13 | 44.90% |
| 35 | 06-12-17 | 01-05-19 | 474,592.10 | 3 | 16 | 586,621.22 | 112,029.12 | 23.61% |
| 36 | 07-09-15 | 01-05-19 | 605,269.57 | 1 | 43 | 1,069,791.10 | 464,521.53 | 76.75% |
| 37 | 18-08-16 | 01-05-19 | 417,028.85 | 3 | 32 | 637,148.44 | 220,119.59 | 52.78% |
| 38 | 14-11-16 | 01-05-19 | 244,298.52 | 4 | 29 | 358,705.78 | 114,407.26 | 46.83% |
| 39 | 18-10-16 | 01-05-19 | 116,222.11 | 6 | 30 | 172,925.33 | 56,703.22 | 48.79% |
| 40 | 27-11-15 | 01-07-19 | 465,751.14 | 2 | 43 | 823,197.55 | 357,446.41 | 76.75% |
| 41 | 29-05-17 | 01-05-19 | 44,609.98 | 5 | 23 | 60,497.25 | 15,887.27 | 35.61% |
| 42 | 11-10-17 | 01-05-19 | 86,703.29 | 4 | 18 | 110,046.82 | 23,343.53 | 26.92% |
| 43 | 04-03-19 | 01-07-19 | 112,209.47 | 5 | 3 | 116,757.96 | 4,548.49 | 4.05% |
| 44 | 14-09-16 | 01-05-19 | 198,260.70 | 4 | 31 | 298,922.65 | 100,661.95 | 50.77% |
| 45 | 24-04-17 | 01-05-19 | 35,082.29 | Final | 24 | 48,210.74 | 13,128.45 | 37.42% |
| 46 | 28-05-18 | 01-07-19 | 36,500.00 | Final | 13 | 43,358.39 | 6,858.39 | 18.79% |
| 47 | 14-02-17 | 01-05-19 | 37,497.80 | 6 | 26 | 52,913.48 | 15,415.68 | 41.11% |
| 48 | 19-03-18 | 01-05-19 | 102,177.29 | 6 | 13 | 121,376.51 | 19,199.22 | 18.79% |
| 49 | 11-04-17 | 01-07-19 | 458,724.13 | 4 | 26 | 647,309.73 | 188,585.60 | 41.11% |
| 50 | 22-03-17 | 01-05-19 | 280,479.31 | 3 | 25 | 390,579.15 | 110,099.84 | 39.25% |
| 51 | 16-06-17 | 01-07-19 | 129,281.91 | 3 | 24 | 177,661.63 | 48,379.72 | 37.42% |
| 52 | 09-10-18 | 01-05-19 | 37,101.90 | 4 | 6 | 40,170.77 | 3,068.87 | 8.27% |
| 53 | 28-03-17 | 01-05-19 | 55,063.99 | Final | 25 | 76,678.91 | 21,614.92 | 39.25% |
| 54 | 23-02-17 | 01-05-19 | 24,746.07 | Final | 26 | 34,919.40 | 10,173.33 | 41.11% |
| 55 | 07-03-18 | 01-07-19 | 76,534.19 | Final | 15 | 93,355.61 | 16,821.42 | 21.98% |
| 56 | 09-05-17 | 01-05-19 | 14,930.57 | Final | 23 | 20,247.91 | 5,317.33 | 35.61% |
| 57 | 14-09-16 | 01-05-19 | 136,243.26 | 4 | 31 | 205,417.39 | 69,174.14 | 50.77% |
| 58 | 17-08-16 | 01-05-19 | 581,539.88 | 5 | 32 | 888,493.03 | 306,953.15 | 52.78% |
| 59 | 22-09-16 | 01-05-19 | 153,948.15 | 3 | 31 | 232,111.51 | 78,163.36 | 50.77% |
| 60 | 15-07-17 | 01-05-19 | 334,044.61 | 3 | 21 | 441,167.36 | 107,122.75 | 32.07% |
| 61 | 24-10-16 | 01-05-19 | 508,387.12 | 1 | 30 | 756,422.44 | 248,035.32 | 48.79% |
| 62 | 10-10-16 | 01-05-19 | 658,827.00 | 5 | 30 | 980,259.94 | 321,432.94 | 48.79% |
| 63 | 11-05-18 | 01-07-19 | 68,918.28 | Final | 13 | 81,868.10 | 12,949.82 | 18.79% |
| 64 | 16-11-16 | 01-05-19 | 68,946.25 | 6 | 29 | 101,234.42 | 32,288.17 | 46.83% |
| 65 | 07-11-16 | 01-05-19 | 394,519.06 | 5 | 29 | 579,275.99 | 184,756.93 | 46.83% |
| 66 | 26-03-13 | 01-05-19 | 68,074.81 | 4 | 73 | 179,022.02 | 110,947.21 | 162.98% |
| 67 | 23-10-16 | 01-05-19 | 98,271.57 | Final | 30 | 146,216.97 | 47,945.39 | 48.79% |
| 68 | 04-01-17 | 01-05-19 | 241,867.56 | 4 | 27 | 345,852.17 | 103,984.61 | 42.99% |
| 69 | 30-10-17 | 01-05-19 | 544,488.49 | 5 | 18 | 691,083.66 | 146,595.17 | 26.92% |
| 70 | 12-03-17 | 01-05-19 | 191,621.63 | Final | 25 | 266,841.12 | 75,219.49 | 39.25% |
| 71 | 24-01-19 | 01-06-19 | 657,579.51 | 4 | 4 | 693,358.10 | 35,778.58 | 5.44% |
| 72 | 29-06-17 | 01-05-19 | 177,201.71 | 11 | 22 | 237,147.82 | 59,946.11 | 33.83% |
| 73 | 14-12-16 | 01-05-19 | 118,181.46 | 3 | 28 | 171,243.68 | 53,062.22 | 44.90% |
| 74 | 18-11-16 | 01-05-19 | 435,224.96 | 5 | 29 | 639,044.84 | 203,819.88 | 46.83% |
| 75 | 10-05-18 | 01-05-19 | 173,676.00 | 7 | 11 | 200,916.42 | 27,240.42 | 15.68% |
| 76 | 18-04-17 | 01-05-19 | 27,228.64 | Final | 24 | 37,418.11 | 10,189.47 | 37.42% |
| 77 | 14-12-16 | 01-05-19 | 196,276.06 | 3 | 28 | 284,401.94 | 88,125.87 | 44.90% |
| 78 | 10-11-16 | 01-07-19 | 251,950.37 | 2 | 31 | 379,871.92 | 127,921.55 | 50.77% |
| 79 | 10-08-16 | 01-05-19 | 443,191.40 | 2 | 32 | 677,120.32 | 233,928.92 | 52.78% |
| 80 | 09-05-16 | 01-05-19 | 73,934.36 | 3 | 35 | 117,537.87 | 43,603.51 | 58.98% |
| 81 | 06-12-16 | 01-05-19 | 31,065.00 | 5 | 28 | 45,012.86 | 13,947.86 | 44.90% |

(Source: Secondary Survey)

The Interim Payment Certificates sampled were as presented in the figure below:

##### Figure 4. 5 Interim payment Certificates considered

(Source: Survey)

Table 4.8 below illustrates the descriptive statistics of the period of payment analyzed

### Table 4. 8 Descriptive statistics of the period of delays

| Mean | 24.54320988 |
| --- | --- |
| Standard Error | 1.212594579 |
| Median | 28 |
| Mode | 29 |
| Standard Deviation | 10.91335121 |

(Source: Excel Analysis)

The mean period of delay of the sampled projects was 24.54 months. Thus approximately 2 calendar years.

### Table 4. 9 Descriptive statistics of  percentage period of delays in payment

| Mean | 0.398943956 |
| --- | --- |
| Standard Error | 0.023991718 |
| Median | 0.448989402 |
| Standard Deviation | 0.215925465 |
| Sample Variance | 0.046623806 |

(Source: Excel Analysis)

From table 4.9  above, the mean percentage of appreciation in value was 0.3989 thus 39.89%.

A correlation test was conducted for the variables as follows:

From the table 4.10 below, it is observed that the coefficient of correlation (r) between the percentage of the value appreciated and Period of delay is 0.9835, this implies that the correlation between the two variables is a strong positive correlation. This indicates that an increase in the Period of delay causes a positive rise in the percentage of Value appreciation. Percentage of value appreciation is the appreciation of the cost-benefit accrued to the client resulting from delayed payment.

A coefficient of determination was analyzed to determine causation between the period of delay and the percentage of value appreciation as follows:

CD = r2

CD = (0.9835)2

Thus CD = 0.9673

Hence: 0.9673 = 96.73 %

This Therefore implies that: 96.73 % of variation period of delay is explained by the variation in percentage value appreciation.  3.27% is however unexplained. It is, therefore, safe to infer that 96.73% variation in percentage value appreciation is explained by variation in the period of delay.

Although appreciated value of the certificate may be momentary gains to the client, payment of fluactuations in the cost of imput on the proceeding cetificates may absorb these gains. The above notwithstanding, appreciated value resulting from delays in final certificates may be the ultimate cost-benefit to the Clients.

In reference to figure 4.5, the total number of final certificates from the sampled projects was 11 no. The mean percentage of value appreciation was found to be 0.3205 thus 32.05%. From the data analyzed, no further certificates were issued beyond the final payment certificate, hence value accrued from delays in honoring final certificates is not transferred to the contractor. Drawing from above, it could be realistic to infer that the cost-benefit accrued to the clients resulting from delayed payment is 32.05% of certified final certificates.

From the table 4.10 below, it is observed that the coefficient of correlation (r) between Period of Delay in Payment and final duration is -0.17387, this implies that the correlation between the two variables is a negative insignificant correlation, hence statistically insignificant for any conclusions. This, however, does not imply that there is no causation between the two variables. Table 2.1 summarises the causes and effects of cost and time overruns.in this table, several types of research identify delay in payment the causes of cost and time overruns. A further examination is therefore required to determine the extent of causation between delays in payment and final duration as well as the final cost of a project.

### Table 4. 10 Coefficient of correlation for variables

|  | Percentage of Cost Variance | Time Variance (T) In Months | Final Duration | Percentage Time Variance | Amount Certified | Compounded Amount Per D | Appreciated Value | Percentage of Value Appreciated | Period of Delay (D) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Percentage of Cost Variance | 1 |  |  |  |  |  |  |  |  |
| Time Variance (T) In Months | 0.57801 | 1 |  |  |  |  |  |  |  |
| Final Duration | 0.56040 | 0.99505 | 1 |  |  |  |  |  |  |
| Percentage Time Variance | 0.61790 | 0.95500 | 0.92851 | 1 |  |  |  |  |  |
| Amount Certified | 0.03545 | 0.05755 | 0.06783 | 0.02860 | 1 |  |  |  |  |
| Compounded Amount Per D | 0.01922 | 0.02932 | 0.03513 | 0.01497 | 0.9721 | 1 |  |  |  |
| Appreciated Value | -0.01841 | -0.03536 | -0.03998 | -0.01640 | 0.7311 | 0.87077 | 1 |  |  |
| Percentage of Appreciated | -0.01712 | -0.15468 | -0.17773 | -0.07704 | -0.0029 | 0.15809 | 0.46593 | 1 |  |
| Period of Delay in Payment (D) | 0.01824 | -0.14764 | -0.17387 | -0.05851 | 0.0020 | 0.17446 | 0.50309 | 0.98352 | 1 |

(Source: Excel Analysis)

## 4.7 TIME VALUE ANALYSIS

At estimated completion, the estimated cost (Contract sum) is expected to have been exhausted. But for the time value of money, the estimated cost of the project would remain unchanged even beyond the completion date (all other factors remaining constant). Therefore, the present value of actual cost at completion is expected to be equal to the estimated cost at the estimated completion date. A variation in this figure indicates additional expenditure or less expenditure.

The decision criteria are as follows:

Positive NPV at Estimated Completion = Additional Expenditure (Loss to the Client)

Negative NPV at Estimated Completion = Reduced Expenditure (Savings to the Client)

The Savings made are gains accrued to the client which are considered cost benefits.

Table 4.12, is explained as follows; the estimated cost of project no.1  is  Gh¢1,878,000.11 and actual cost Gh¢ 2,408,117.87 the project was however completed 17 months beyond the expected completion date. All other factors held constant, the variation in cost was as a result of the time value of money, hence discounting the actual cost over the period of delay should be equal to the estimated cost. However, Gh¢ 2,408,117.87 discounted monthly over a period of 17 months equals Gh¢ 1,922,596.51. which is greater than Gh¢1,878,000.11 by Gh¢ 44,596.40. This Gh¢ 44,596.40 is a loss to the Client. On the other hand, a negative variance as indicated by projects no. 2 implies savings made by the client. This savings is referred to as the cost-benefit to the client.

From the table, 35no. representing 43.21% recorded positive NVP at expected completion while 46no. representing 56.79% recorded negative NVP at expected completion. It could be intimated therefore that for 56.79% of the projects sampled, the client made saving while for 43.21% the Client made losses.

### Table 4. 11 Descriptive statistics for Percentage of  Nvp Over Estimated Cost

| Mean | -0.01 |
| --- | --- |
| Standard Error | 0.03 |
| Median | -0.05 |
| Standard Deviation | 0.31 |
| Sample Variance | 0.10 |

(Source: Excel Analysis)

From table 4.11  above, the mean percentage of appreciation in value was -0.01 thus  -1 %. The mean percentage of the NVP which is the amount accrued to the client as cost-benefit is 1% of the estimated cost. This is usually as a result of schedule overrun as well as cost overruns resulting from delayed payment.

### Table 4. 12 Time  Value of Money Analysis

| Project No. | Estimated Cost (A) | Actual Cost (B) | Cost Variance (C=B-A) | Percentage of Cost Variance | Discount Amount Factor 11+r12^tx12 | Present Value of B at T | NPV at expected Completion | Percentage of NVP Over Estimated Cost | Time Variance (ending at T) In Months |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 1,878,000.11 | 2,408,117.87 | 530,117.76 | 28% | 0.7984 | 1,922,596.51 | 44,596.40 | 2% | 17 |
| 2 | 1,398,385.85 | 1,408,641.19 | 10,255.34 | 1% | 0.6811 | 959,362.74 | -439,023.11 | -31% | 29 |
| 3 | 483,381.98 | 1,611,236.30 | 1,127,854.33 | 233% | 0.4638 | 747,350.21 | 263,968.24 | 55% | 58 |
| 4 | 210,689.15 | 477,167.16 | 266,478.01 | 126% | 0.8876 | 423,545.03 | 212,855.88 | 101% | 9 |
| 5 | 695,489.91 | 1,309,166.86 | 613,676.95 | 88% | 0.5583 | 730,958.18 | 35,468.27 | 5% | 44 |
| 6 | 998,861.51 | 1,040,542.13 | 41,680.61 | 4% | 1.0000 | 1,040,542.13 | 41,680.61 | 4% | 0 |
| 7 | 246,370.37 | 262,320.32 | 15,949.95 | 6% | 0.5295 | 138,905.73 | -107,464.64 | -44% | 48 |
| 8 | 799,871.46 | 794,043.65 | - 5,827.81 | -1% | 0.8418 | 668,442.57 | -131,428.89 | -16% | 13 |
| 9 | 558,740.33 | 969,058.82 | 410,318.48 | 73% | 0.5583 | 541,062.79 | -17,677.54 | -3% | 44 |
| 10 | 488,167.35 | 495,703.84 | 7,536.49 | 2% | 0.7277 | 360,716.82 | -127,450.53 | -26% | 24 |
| 11 | 507,781.45 | 515,776.04 | 7,994.59 | 2% | 0.6721 | 346,650.08 | -161,131.37 | -32% | 30 |
| 12 | 1,073,819.23 | 1,152,509.06 | 78,689.83 | 7% | 1.0000 | 1,152,509.06 | 78,689.83 | 7% | 0 |
| 13 | 953,514.82 | 1,152,790.75 | 199,275.93 | 21% | 0.5966 | 687,716.84 | -265,797.98 | -28% | 39 |
| 14 | 852,864.50 | 876,478.35 | 23,613.85 | 3% | 0.6901 | 604,889.42 | -247,975.08 | -29% | 28 |
| 15 | 1,399,214.21 | 1,772,321.24 | 373,107.03 | 27% | 0.6290 | 1,114,835.86 | -284,378.35 | -20% | 35 |
| 16 | 947,518.82 | 1,141,401.03 | 193,882.21 | 20% | 0.6290 | 717,970.75 | -229,548.07 | -24% | 35 |
| 17 | 877,185.54 | 908,573.64 | 31,388.10 | 4% | 0.6290 | 571,516.30 | -305,669.24 | -35% | 35 |
| 18 | 733,811.86 | 784,493.89 | 50,682.03 | 7% | 0.6290 | 493,466.93 | -240,344.93 | -33% | 35 |
| 19 | 1,396,098.85 | 1,661,451.10 | 265,352.25 | 19% | 0.6290 | 1,045,095.68 | -351,003.17 | -25% | 35 |
| 20 | 941,728.32 | 1,152,450.31 | 210,721.99 | 22% | 0.6290 | 724,921.03 | -216,807.29 | -23% | 35 |
| 21 | 730,411.54 | 782,772.34 | 52,360.80 | 7% | 0.6290 | 492,384.03 | -238,027.51 | -33% | 35 |
| 22 | 139,826.04 | 257,976.07 | 118,150.03 | 84% | 0.4577 | 118,084.26 | -21,741.78 | -16% | 59 |
| 23 | 519,072.96 | 743,435.04 | 224,362.08 | 43% | 0.4638 | 344,832.31 | -174,240.65 | -34% | 58 |
| 24 | 119,884.77 | 376,423.46 | 256,538.69 | 214% | 0.4577 | 172,301.59 | 52,416.82 | 44% | 59 |
| 25 | 560,941.02 | 1,484,021.58 | 923,080.56 | 165% | 0.3466 | 514,344.27 | -46,596.75 | -8% | 80 |
| 26 | 976,512.38 | 938,783.16 | - 37,729.22 | -4% | 1.0000 | 938,783.16 | -37,729.22 | -4% | 0 |
| 27 | 484,443.25 | 695,444.29 | 211,001.04 | 44% | 0.9610 | 668,352.16 | 183,908.91 | 38% | 3 |
| 28 | 606,997.02 | 1,657,469.33 | 1,050,472.31 | 173% | 0.4638 | 768,794.78 | 161,797.76 | 27% | 58 |
| 29 | 756,446.19 | 772,191.10 | 15,744.91 | 2% | 0.7472 | 576,997.00 | -179,449.19 | -24% | 22 |
| 30 | 981,424.32 | 981,532.93 | 108.61 | 0% | 0.6459 | 633,983.60 | -347,440.72 | -35% | 33 |
| 31 | 447,891.95 | 450,625.69 | 2,733.74 | 1% | 0.6126 | 276,044.93 | -171,847.02 | -38% | 37 |
| 32 | 764,657.97 | 881,121.86 | 116,463.89 | 15% | 0.7673 | 676,066.47 | -88,591.50 | -12% | 20 |
| 33 | 1,455,409.32 | 2,335,093.86 | 879,684.54 | 60% | 0.8530 | 1,991,940.65 | 536,531.33 | 37% | 12 |
| 34 | 1,330,000.00 | 1,461,298.45 | 131,298.45 | 10% | 1.0000 | 1,461,298.45 | 131,298.45 | 10% | 0 |
| 35 | 938,308.00 | 960,745.84 | 22,437.84 | 2% | 0.8307 | 798,134.18 | -140,173.82 | -15% | 14 |
| 36 | 1,290,933.82 | 1,387,120.40 | 96,186.58 | 7% | 0.5658 | 784,809.07 | -506,124.75 | -39% | 43 |
| 37 | 972,764.27 | 1,105,477.43 | 132,713.16 | 14% | 1.0000 | 1,105,477.43 | 132,713.16 | 14% | 0 |
| 38 | 1,791,282.98 | 1,930,387.78 | 139,104.80 | 8% | 1.0000 | 1,930,387.78 | 139,104.80 | 8% | 0 |
| 39 | 242,213.06 | 601,535.63 | 359,322.57 | 148% | 0.5226 | 314,338.26 | 72,125.20 | 30% | 49 |
| 40 | 918,170.41 | 883,170.41 | - 35,000.00 | -4% | 0.6459 | 570,450.10 | -347,720.31 | -38% | 33 |
| 41 | 1,293,420.52 | 1,500,519.23 | 207,098.71 | 16% | 0.9236 | 1,385,886.27 | 92,465.75 | 7% | 6 |
| 42 | 1,293,660.93 | 1,508,370.64 | 214,709.71 | 17% | 0.8759 | 1,321,249.33 | 27,588.40 | 2% | 10 |
| 43 | 999,500.00 | 1,283,686.93 | 284,186.93 | 28% | 0.8530 | 1,095,043.00 | 95,543.00 | 10% | 12 |
| 44 | 1,499,692.77 | 1,671,083.69 | 171,390.92 | 11% | 0.9236 | 1,543,420.37 | 43,727.60 | 3% | 6 |
| 45 | 701,645.82 | 1,353,159.32 | 651,513.50 | 93% | 0.5966 | 807,250.10 | 105,604.28 | 15% | 39 |
| 46 | 755,188.26 | 927,529.39 | 172,341.13 | 23% | 0.9868 | 915,325.06 | 160,136.80 | 21% | 1 |
| 47 | 519,947.19 | 1,175,283.12 | 655,335.93 | 126% | 0.5089 | 598,099.89 | 78,152.71 | 15% | 51 |
| 48 | 1,658,495.97 | 1,734,748.98 | 76,253.01 | 5% | 0.7673 | 1,331,036.80 | -327,459.17 | -20% | 20 |
| 49 | 1,190,000.00 | 2,119,858.94 | 929,858.94 | 78% | 0.7775 | 1,648,210.64 | 458,210.64 | 39% | 19 |
| 50 | 199,358.43 | 508,977.83 | 309,619.40 | 155% | 0.6633 | 337,579.97 | 138,221.54 | 69% | 31 |
| 51 | 259,080.00 | 553,421.33 | 294,341.33 | 114% | 0.4577 | 253,319.42 | -5,760.58 | -2% | 59 |
| 52 | 550,700.64 | 597,896.45 | 47,195.81 | 9% | 0.3905 | 233,459.00 | -317,241.64 | -58% | 71 |
| 53 | 1,101,279.85 | 1,801,111.61 | 699,831.76 | 64% | 0.8759 | 1,577,674.25 | 476,394.40 | 43% | 10 |
| 54 | 989,842.92 | 1,636,683.55 | 646,840.63 | 65% | 0.7775 | 1,272,537.14 | 282,694.22 | 29% | 19 |
| 55 | 609,593.64 | 950,321.22 | 340,727.58 | 56% | 0.6126 | 582,149.14 | -27,444.50 | -5% | 37 |
| 56 | 597,223.00 | 1,041,845.69 | 444,622.69 | 74% | 0.5366 | 559,041.36 | -38,181.64 | -6% | 47 |
| 57 | 875,325.72 | 1,066,400.06 | 191,074.34 | 22% | 0.6901 | 735,961.25 | -139,364.46 | -16% | 28 |
| 58 | 1,483,244.61 | 1,714,254.54 | 231,009.93 | 16% | 0.8307 | 1,424,107.27 | -59,137.34 | -4% | 14 |
| 59 | 799,336.02 | 799,336.02 | - | 0% | 0.7984 | 638,175.01 | -161,161.01 | -20% | 17 |
| 60 | 1,489,662.85 | 1,645,047.24 | 155,384.39 | 10% | 0.8198 | 1,348,631.94 | -141,030.91 | -9% | 15 |
| 61 | 650,053.58 | 650,053.58 | - | 0% | 0.7087 | 460,668.59 | -189,384.99 | -29% | 26 |
| 62 | 899,800.00 | 2,009,327.16 | 1,109,527.16 | 123% | 0.4638 | 931,999.28 | 32,199.29 | 4% | 58 |
| 63 | 443,907.13 | 677,151.93 | 233,244.80 | 53% | 0.5583 | 378,079.95 | -65,827.18 | -15% | 44 |
| 64 | 340,000.00 | 558,196.31 | 218,196.32 | 64% | 0.5510 | 307,561.64 | -32,438.36 | -10% | 45 |
| 65 | 146,933.45 | 604,219.53 | 457,286.08 | 311% | 0.4826 | 291,619.57 | 144,686.12 | 98% | 55 |
| 66 | 575,413.07 | 529,150.29 | - 46,262.78 | -8% | 0.9610 | 508,536.41 | -66,876.66 | -12% | 3 |
| 67 | 986,906.71 | 1,456,969.40 | 470,062.69 | 48% | 0.9484 | 1,381,787.04 | 394,880.33 | 40% | 4 |
| 68 | 662,604.92 | 1,150,401.86 | 487,796.94 | 74% | 0.3905 | 449,194.29 | -213,410.63 | -32% | 71 |
| 69 | 1,500,000.00 | 2,072,455.95 | 572,455.95 | 38% | 0.8530 | 1,767,898.64 | 267,898.64 | 18% | 12 |
| 70 | 861,034.02 | 1,610,093.98 | 749,059.96 | 87% | 0.9115 | 1,467,523.03 | 606,489.01 | 70% | 7 |
| 71 | 1,548,414.22 | 1,660,653.35 | 112,239.13 | 7% | 0.8198 | 1,361,426.04 | -186,988.18 | -12% | 15 |
| 72 | 695,000.00 | 1,888,272.59 | 1,193,272.59 | 172% | 0.4763 | 899,361.46 | 204,361.45 | 29% | 56 |
| 73 | 590,755.84 | 547,489.81 | - 43,266.03 | -7% | 0.7879 | 431,354.29 | -159,401.55 | -27% | 18 |
| 74 | 515,075.67 | 1,286,323.09 | 771,247.42 | 150% | 0.4956 | 637,494.78 | 122,419.11 | 24% | 53 |
| 75 | 351,383.82 | 700,078.98 | 348,695.16 | 99% | 0.3654 | 255,840.94 | -95,542.88 | -27% | 76 |
| 76 | 544,572.90 | 1,505,980.24 | 961,407.34 | 177% | 0.4228 | 636,675.14 | 92,102.25 | 17% | 65 |
| 77 | 989,514.65 | 1,058,590.97 | 69,076.32 | 7% | 0.8876 | 939,630.76 | -49,883.89 | -5% | 9 |
| 78 | 466,900.47 | 528,108.79 | 61,208.32 | 13% | 1.0000 | 528,108.79 | 61,208.32 | 13% | 0 |
| 79 | 519,432.55 | 1,113,486.95 | 594,054.40 | 114% | 0.4891 | 544,577.10 | 25,144.54 | 5% | 54 |
| 80 | 567553.29 | 768,137.49 | 200,584.20 | 35% | 0.5437 | 417,668.61 | -149,884.68 | -26% | 46 |
| 81 | 360,000.00 | 589,192.50 | 229,192.50 | 64% | 0.4956 | 292,000.62 | -67,999.38 | -19% | 53 |

(Source: Secondary Survey)

# CHAPTER FIVE

# SUMMARY OF FINDINGS, CONCLUSION, AND RECOMMENDATIONS

## 5.1 INTRODUCTION

This chapter focuses on summarizing the research findings, concluding the research and also making recommendations. The study was conducted to satisfy the aim of exploring cost benefits of delayed payment to the client resulting in cost overruns. The following objectives were set to enable the researcher to meet the aim:

- To identify the cost performance trends of public school projects executed from 2010 to 2018

- To compare cost trends in relation to schedule trends of the sampled projects

- To explore the cost benefits of delayed payment accruing to the client

The chapter is presented in the following sequence

- Summary of research procedure;

- Summary of the research findings;

- Conclusions based on objectives;

- Limitations and delimitations

- Recommendations; and

- Areas for further studies.

## 5.2 SUMMARY OF RESEARCH PROCEDURE

The study is summarized as follows

- The study was designed to cover School projects executed by the government of Ghana and financed by the Ghana education trust fund. A total of 81 projects were sampled for the study. The sampling procedure adopted in sampling the projects was purposive sampling. The data was collected from the payment certificates of the projects sampled and presented and analyzed with Microsoft excel. The data collected from the payment certificates consisted of the following:

- The estimated cost of the projects,

- Actual Cost expended

- Expected completion date

- Actual Completion date

- Date of certification

- Date of payment

## 5.3 SUMMARY OF RESEARCH FINDINGS

As regards objective 1, it was found that 91 % of the projects in the sample experienced cost overruns by an average of 52.90 %. It was as well found out that 91.36 % of projects experienced schedule overruns by as much as 286.13%.

Objective 2 involved the evaluation of cost trends in relation to schedule trends. It was found that a positive correlation exists between cost trends and schedule trends. A rise in the schedule (time) resulted in a rise in cost. Further studies found that 38.18% of the variation in Cost is explained by the variation in Time, whereas 61.82 % is unexplained.

A regression module was therefore formulated to illustrate the relationship between cost and time trends: Percentage of Cost Variance = -0.006 + 0.187 (Percentage of Time Variance)

Objective 3 sought to explore cost-benefit accrued to the client when payments are delayed. It was found that the average period of delay in honoring certificates was 24.54 months approximately two calendar years. the study also revealed that the client enjoyed cost-benefit of averagely 39.89% of the certified amount also 32.05% of the Final Certificate. Overall the cost-benefit due the client on the was 1% of the contract sum. Finally, it was found that 96.73% variation in appreciation in value explained by variation in the period of delay in payment.

## 5.3 CONCLUSION

Following the above findings, the following conclusions can be drawn:

- An increase in the construction schedule results in an increase in the cost of the project.

- 91 % of the projects in the population experienced cost overruns by an average of 52.90 %

- 91.36 % of projects experienced schedule overruns by as much as 286.13%.

- Payment of certificates is delayed by an average of 24 months

- Cost benefits of an average of 39.89% of the certified amount are accrued to clients as a result of delayed payment. Also, the mean cost-benefit accrued to the clients resulting from delayed payment is 32.05% of certified final certificates. Overall the cost-benefit due the client resulting from delayed payment leading to cost overruns was revealed as 1% of the contract sum.

- 96.73% variation in the percentage of variation in certified amount is explained by variation in the period of delay in payment.

## 5.3 LIMITATIONS AND DELIMITAIONS

Bearing in mind the sensitive and confidential nature of contract details and payment information, there were difficulties in accessing data for the study, hence projects for which information was available were those considered in the analysis.

The sample was limited to completed projects for which at least one payment certificate was honored between May and August 2019.

The certification analysis was also limited to only one payment certificate thus certificate honored between May and June 2019.

## 5.4 RECOMMENDATIONS

The following recommendations are worth considering following the conclusions drawn for efficient delivery of projects;

- Care should be taken through prudent management practices to prevent schedule overruns and hence preventing cost overruns.

- Policy on payment for a construction project should be structured such that, detailed payments are discouraged. Note should be taken that value accruing to the client indicates value lost by the contractor.

- A continues analysis of cost and time performance of projects should be conducted frequently to discover trends and make appropriate recommendations.

## 5.5 RECOMMENDATIONS FOR FURTHER STUDIES

The following are further research  that could be taken up from this study:

- 38.18% of the variation in Cost is explained by the variation in Time, whereas 61.82 % is unexplained. This unexplained 61.82 % should be further researched and explained.

- Only 1no. payment certificate was considered per project in the analysis regarding delayed payment. A further study should be conducted considering all payment certificates issued per project.

- No significant correlation was recorded between delayed payment and cost and time overruns, however, the research identifies the delayed payment as a cause of time and cost overrun. The causation between delayed payment and cost and time overruns needs to be researched.

# REFERENCES

Akoa, B.B. (2011). Cost overruns and time delays in highway and bridge projects in developing countries - experiences from Cameroon. MS diss., Michigan State University.

Ammar, M., Zayed, T., Asce, M. and Moselhi, O. (2013), ‘Fuzzy-Based Life-Cycle Cost Model for Decision Making under Subjectivity’, Journal of Construction Engineering and Management, vol. 139, no. 5, pp. 556–63.

Ansah, S. (2011). “Causes and effects of delayed payments by clients on construction projects in Ghana.” J. Constr. Project Manage. Innovation 1 (1): 27–45.

Assaf, S.A. and Al-Hejji, S. (2006), ‘Causes of delay in large construction projects’, International Journal of Project Management, vol. 24, no. 4, pp. 349–57.

Azman, M. N. A., N. Dzulkalnine, Z. A. Hamid, and K. W. Bing. (2014). “Payment issue in Malaysian construction industry: Contractors’ perspective.” J. Teknologi 70 (1): 57–63. https://doi.org/10.11113/jt.v70 .2804.

Bailey, F. and Chandra, Prasanna (2004), ‘Basic Concept of Time Value of Money’, Financial Management–Theory and Practice, vol. 21, no. 3, pp. 286–8.

Blumberg B., Cooper D.R. and Schindler P.S. (2005) Business Research Methods.8th Ed. Berkshire: McGraw-Hill Education

Brand, M. C., and T. Uher. (2010). “Follow-up empirical study of the performance of the New South Wales construction industry security of payment legislation.” Int. J. Law Built Environ. 2 (1): 7–25. https://doi.org/10.1108/17561451011036496.

Bryman, A., (2007). Barriers to integrating quantitative and qualitative research. Journal of mixed methods research, 1(1), pp.8-22.

Cable, V. (2013). Building a responsible payment culture: Discussion paper. London: Dept. of Business Innovation and Skills.

Cantarelli, C.C., Flyvbjerg, B., van Wee, B. and Molin, E.J., (2010). Lock-in and its influence on the project performance of large-scale transportation infrastructure projects: investigating the way in which lock-in can emerge and affect cost overruns. Environment and Planning B: Planning and Design, 37(5), pp.792-807.

Catalão, F.P., Cruz, C.O. and Sarmento, J.M. (2019), ‘The determinants of cost deviations and overruns in transport projects, an endogenous models approach’, Transport Policy, vol. 74, no. December 2018, pp. 224–38.

Cheng, T., G. Soo, M. Kumaraswamy, and W. Jin. (2010). “Security of payment for Hong Kong construction industry.” Manage. Procurement Law 163 (1): 17–28. https://doi.org/10.1680/mpal.2010.163.1.17.

Choudhry, R.M., Nasir, A.R. and Gabriel, H.F. (2012). Cost and time overruns in highway projects in Pakistan. Pakistan Engineering Congress, Centenary Celebration, Paper No 726, 353–369.

Choudhry, R.M., Nasir, A.R. and Gabriel, H.F. (2012). Cost and time overruns in highway projects in Pakistan. Pakistan Engineering Congress, Centenary Celebration, Paper No 726, 353–369.

Christou, E., Valachis, I. and Anastasiadou, C. (2008) Research Methodology in Hospitality Industry: The role of the Inquiry Paradigm

Cohen, J., (1992). A power primer. Psychological bulletin, 112(1), p.155.

Collis, J. and Hussey, R. (2003) Business Research: A Practical Guide for Undergraduate and Postgraduate Students 2nd Ed, New York: Palgrave Macmillan

Creedy, G.D., Skitmore, M., Wong, J.K.W., (2010). Evaluation of Risk Factors Leading to Cost Overrun in Delivery of Highway Construction Projects. J. Construct. Eng. Manag. 136 (5), 528–537. https://doi.org/10.1061/(ASCE)CO.1943-7862.0000160.

DBIS (Department for Business Innovation and Skills). (2015). Late payment: Challenging grossly unfair terms and practices. Accessed December 5, 2017. https://www.gov.uk/government/uploads/system /uploads/attachment_data/file/400351/bis-15-68-late-payment-challenging -grossly-unfair-terms-and-practices.pdf.

Enshassi, A.A.-N.J.; M.K. (2009), ‘Delays and cost overruns in the construction projects in the Gaza Strip’, journal of Financial Management of property and construction, pp. 126–51.

Flyvbjerg, B. and Budzier, A., (2013). Why your IT project might be riskier than you think. arXiv preprint arXiv:1304.0265.

Flyvbjerg, B., (2009). Survival of the unfittest: why the worst infrastructure gets built—and what we can do about it. Oxford review of economic policy, 25(3), pp.344-367.

Flyvbjerg, B., (2014) What you should know about megaprojects and why: An overview. Project management journal, 45(2), pp.6-19.

Flyvbjerg, B., Ansar, A., Budzier, A., Buhl, S., Cantarelli, C., Garbuio, M., Glenting, C., Holm, M.S., Lovallo, D., Lunn, D., Molin, E., Rønnest, A., Stewart, A. and van Wee, B. (2018), ‘Five things you should know about cost overrun’, Transportation Research Part A: Policy and Practice, vol. 118, no. September, pp. 174–90.

Flyvbjerg, B., Holm, M.K.S. & Buhl, S.L. (2011) Transport Reviews: A Transnational What Causes Cost Overrun in Transport Infrastructure Projects, no. June 2014, pp. 37–41.

Flyvbjerg, B., Holm, M.S. and Buhl, S., (2002). Underestimating costs in public works projects: Error or lie? Journal of the American planning association, 68(3), pp.279-295.

Frimpong, Y., Oluwoye, J. and Crawford, L. (2003) ‘Causes of delay and cost overruns in construction of groundwater projects in developing countries; Ghana as a case study’, International Journal of Project Management, vol. 21, no. 5, pp. 321–6.

Fugar, F.D. and Agyakwah-Baah, A.B. (2010) ‘Delays in Building Construction Projects in Ghana’, Construction Economics and Building, vol. 10, no. 1–2, pp. 103–16.

Kahneman, D., Lovallo, D. and Sibony, O., 2011. Before you make that big decision. Harvard business review, 89(6), pp.50-60.

Kim, S., Nguyen, V.T. and Luu, V.T. 2016, Delay Factors Affecting the Completion of the Government Construction Projects in Vietnam, no. October 2015.

Kishore, M., Rao, C.H. and Singh, L. (2012). Time and cost overrun analysis on national highway development projects. Journal of the Indian Roads Congress, 73(3): 299–321.

Kishore, M., Rao, C.H. and Singh, L. (2012). Time and cost overrun analysis on national highway development projects. Journal of the Indian Roads Congress, 73(3): 299–321.

Koskela, L. and Howell, G., (2002), The Underlying Theory of Project Management is Obsolete. Proceedings of the PMI Research Conference, pp. 293-302

Le-Hoai, L., Lee, Y.D. and Lee, J.Y. (2008). Delay and cost overruns in Vietnam large construction projects: A comparison with other selected countries. KSCE Journal of Civil Engineering, 12(6): 367–377. https://doi.org/10.1007/s12205- 008-0367-7

Lip, E. (2006). “Curing the ills of non-payment in the construction industry—The Singapore experience.” In Proc., 8th Surveyors’ Congress. Kuala Lumpur, Malaysia: ISM.

Love, P.E.D. and Ahiaga-Dagbui, D.D. (2018) ‘Debunking fake news in a post-truth era: The plausible untruths of cost underestimation in transport infrastructure projects’, Transportation Research Part A: Policy and Practice, vol. 113, no. August 2017, pp. 357–68.

Mahamid, I. and Bruland, A. (2012). Cost deviation in road construction projects: The case of Palestine. Australian Journal of Construction Economics and Building, 12(1): 58–71. https://doi.org/10.5130/ajceb.v12i1.2427

Mahamid, I. and Bruland, A. (2012). Cost deviation in road construction projects: The case of Palestine. Australian Journal of Construction Economics and Building, 12(1): 58–71. https://doi.org/10.5130/ajceb.v12i1.2427

Marsh D. and Stoker G. (2002) Theories and Methods in Political Science, 2nd Ed. Houndmills, UK: Palgrave, Macmillan

Murdick, R.G. (1973) ‘Time Value of Money’, IEEE Engineering Management Review, pp. 51–60.

Nazir, N. Z. (2006). “Late payment problems among contractors in Malaysia.” Master’s dissertation, Dept. of Civil Engineering, Universiti Teknologi Malaysia

Odeck, J., Welde, M., Volden, G.H., (2015). The impact of external quality assurance of costs estimates on cost overruns: Empirical evidence from the norwegian road sector. Eur. J. Transp. Infrastruct. Res. 15 (3), 286–303.

Osei-Hwedie, M. (2010) Strategic Issues of Innovative Financing of Infrastructure Project Delivery, Unpublished Thesis (MSc), Kwame Nkrumah University of Science and Technology, Kumasi- Ghana

Peters, E., Subar, K. and Martin, H. (2019) ‘Late Payment and Nonpayment within the Construction Industry: Causes, Effects, and Solutions’, Journal of Legal Affairs and Dispute Resolution in Engineering and Construction, vol. 11, no. 3, p. 04519013.

Priemus, H., Flyvbjerg, B. and van Wee, B. eds., (2008). Decision-making on mega-projects: cost-benefit analysis, planning and innovation. Edward Elgar Publishing.

Ramachandra, T., and J. O. Rotimi. (2010). “Review of methods for mitigat- ing payment risks in construction: The case of New Zealand.” In Proc., Int. Research Conf. on Sustainability in Built Environment, 198–207. Moratuwa, Sri Lanka: Dept. of Building Economics, Univ. of Moratuwa.

Ramanathan, C., Narayanan, S.P. and Idrus, A. (2012). Construction delays causing risks on time and cost – a critical review. Australian Journal of Construction Economics and Building, 12(1): 37–57. https://doi.org/10.5130/ajceb. v12i1.2330

Sin, T. A. S. (2006). Payment issues–The present dilemmas of Malaysian construction industry. Master’s thesis, Faculty of Civil Engineering, Universiti Teknologi.

Singh, R. (2009). Delays and cost overruns in infrastructure projects: An enquiry into extents, causes and remedies, working paper no. 181. Delhi: Centre for Development Economics, Department of Economics, Delhi School of Economics.

Skamris Holm, M.K., Flyvbjerg, B., (1997). Inaccuracy of traffic forecasts and cost estimates on large transport projects. Transport Pol. 4 (3), 141–146. https://doi.org/10.1016/ S0967-070X(97)00007-3

Skitmore, M. and Al-Kharashi, A.(2009) ‘Causes of delays in Saudi Arabian public sector construction projects’, Construction Management and Economics, vol. 27, no. 1, pp. 3–23.

Smyth, H. J and Morris, P. W.G. (2007) An Epistemological Evaluation of Research into Projects and Their Management: Methodological Issues,

Streubert, H.J. and Carpenter, R.D. (1999) Qualitative Research in Nursing: Advancing the Humanistic Imperative. 2nd Ed. Philadelphia: Lippincott Williams & Williams

Teddlie, C. and Yu, F. (2007). Mixed Methods Sampling: A Typology with Example The Standish Group (2015), CHAOS REPORT 2015.

Uff, J., and D. Thornhill. (2010). Report ofthe commission ofenquiry into the construction sector of Trinidad and Tobago. Port of Spain, Trinidad: Ministry of Finance.

Venkateswaran, C.B. and Murugasan, R. (2017) ‘Time delay and cost overrun of road over bridge (ROB) construction projects in India’, Journal of Construction in Developing Countries, vol. 22, no. November, pp. 79–96.

Wijekoon, S.B. and Attanayake, A.M.C.T.K. (2012). Study on the cost overruns in road construction projects in Sri Lanka. International Conference on Sustainable Built Environment, Sri Lanka, Paper No 69. The Earls Regency Hotel, Kandy, 14–16 December 2012. Sri Lanka: University of Peradeniya

Wu, J. (2008). “Payment problems and regulatory responses in the construc- tion industry: Mainland China perspective.” J. Prof. Issues Eng. Educ. Pract. 134 (4): 399–407. https://doi.org/10.1061/(ASCE)1052-3928 (2008) 134:4(399).

Žukauskas, P., Vveinhardt, J., & Andriukaitienė, R. (2018). Philosophy and Paradigm of Scientific Research. Open access peer-reviewed chapter. Retrieved from DOI: 10.5772/intechopen.70628

# APPENDIX

Photos of some of the projects consided in the study