EFFECTIVE MANAGEMENT OF RISK FACTORS ASSOCIATED WITH PUBLIC INVESTMENT PROJECTS IN GHANA

By

Eric Larbie Marmah

(BSc. Construction Technology and Management)

A thesis submitted to the Department of Construction Technology and Management, Kwame Nkrumah University of Science and Technology, Kumasi in partial fulfilment of the requirement for the award degree of

MASTER OF SCIENCE IN PROJECT MANAGEMENT

November, 2019

# DECLARATION

I hereby declare that this submission is my own work and that, to the best of my knowledge and belief, it contains no material previously published or written by another person nor material which to a substantial extent has been accepted for the award of any other degree or diploma at Kwame Nkrumah University of Science and technology, Kumasi or any other educational institution, except where due acknowledgement is made in the thesis.

Eric Larbie Marmah (PG1150017)    …………………….          ……………………

Student                                                    Signature                           Date

Certified by:

Prof. Theophilus Adjei-Kumi            …………………….           …………………….

Supervisor                                             Signature                            Date

Certified by:

Prof. Bernard Kofi Baiden               …………………….            …………………….

Head of Department                             Signature                             Date

# ABSTRACT

Risk management is an important part of the decision-making process in construction project management particularly regarding the project’s integration, scope, time, cost, quality, human resources, communications, and procurement. Effective risk management in public investment projects requires a comparison between the potential risk and the possible return or future profits on the project.  This study explored the effective management of risk factors in public investment projects in Ghana. The study was carried out along the tenets of a preliminary literature review and followed by a survey using a structured questionnaire. Fifty-nine (59) questionnaire were distributed by purposive sampling, and 50 completed questionnaires representing 85% were considered valid for the analysis. The data collected were analysed using Relative Importance Index (RII) and standard deviation. The study reveals that, change of government, changes in management ways, lower quality of work, change of government policy, new governmental acts or legislation, poor communication between parties involved, resource management, Ambiguous planning due to project complexity, changes in design, legal disputes during the construction phase among the partners, gaps between the Implementation and the specifications due to a misunderstanding of drawings, delayed disputes resolutions, undocumented change orders are the major risk factors that affect public investments projects in Ghana. Considering the mitigation techniques, planning for alternative methods as stand-by, transfer or share risk to/with other parties, referring to previous and ongoing similar projects for accurate, utilize quantitative risk analyses techniques for accurate time, consciously adjust for bias risk premium to time estimation, depend on subjective judgment to produce a proper program and Produce a proper schedule by getting updated project information are the major risk mitigation techniques. Finally, it was recommended that investors working in the public sector have to be aware of the fact that, change of government and change of government policies have a major risk on public investment and as such they should always bear in mind and also have alternatives as a stand-by

Keywords: Risk, management, preliminary, mitigation, investment, communication.

# TABLE OF CONTENT

DECLARATION	i

ABSTRACT	ii

TABLE OF CONTENT	iii

ACKNOWLEDGEMENTS	viii

DEDICATION	ix

CHAPTER ONE	1

INTRODUCTION	1

1.1 Background to the Study	1

1.2 Problem Statement	2

1.3 Aim and Objectives	3

1.3.1 Aim	3

1.3.2 Objectives	3

1.4 Research Questions	3

1.5 Scope of the Study	3

1.6 Research Methodology	4

1.7 Significance of the Study	5

1.8 Organisation of the Chapters	6

LITERATURE REVIEW	8

2.1 Introduction	8

2.2 What is Risk?	8

2.2.1 Sources of Risk	11

2.3 Review of Empirical Studies on Project Risk Management	12

2.4 Definitions of Risk Factors	18

2.5 Risk Classification in Investment Projects	19

2.5.1 Strategic Risk	20

2.5.2 Change Risk	20

2.5.3 Operational Risk	20

2.5.4 Unforeseeable Risk	21

2.6 The Risk Management Process	21

2.6.1 Risk Identification	22

2.6.2 Risk Analysis	22

2.6.3 Risk Mitigation	23

2.6.4 Risk Monitoring and Follow Up	23

2.7 Chapter Summary	24

CHAPTER THREE	25

RESEARCH METHODOLOGY	25

3.1 Introduction	25

3.2 Research Methodology	25

3.3 Research Philosophy	25

3.4 Research Strategy	27

3.5 Research Approach	28

3.6 Research Design	29

3.7 Study Population	30

3.8 Sampling and Sampling Technique	30

3.8.1 Sample Size	30

3.9 Research Instrument	32

3.10 Data Analysis	33

3.11 Test of Validity and Reliability	34

CHAPTER FOUR	35

DATA ANALYSIS AND DISCUSSION OF RESULTS	35

4.1 Introduction	35

4.2 Data Analysis	35

4.3 Presentation of Results and Discussions	36

4.3.1 Organizational Role	36

4.3.2. Educational level of respondent	37

4.3.3 Working Experience of Respondents in the Construction Industry	38

4.4 Analysis and Discussion of Main Objectives	39

4.4.1 Risk factors that typically affect public investments projects	39

CHAPTER FIVE	44

SUMMARY OF FINDINGS, CONCLUSION AND RECOMMENDATION	44

5.1 Introduction	44

5.2.1 Risk factors that typically affect public investments projects	44

5.2.2 Risk mitigation techniques	45

5.3 Conclusion	45

5.4 Recommendation	46

5.5 Recommendation for Further Studies	47

REFERENCES	48

APPENDIX - SURVEY QUESTIONNAIRE	55

LIST OF TABLES

Table 2.1: Probability Impact risk Rating Matrix	23

Table 3.1: Cronbach's Alpha	34

Table 4.1: Role in the Organisation	37

Table 4.2: Educational Level of Respondent	38

Table 4.3: Working Experience of Respondent	39

Table 4.4: Risk Factors that Typically Affect Public Investment Projects	41

Table 4.5: Risk Mitigation Techniques	43

LIST OF FIGURES

Figure 1.1: Research Disposition Diagram	7

Figure 2.1: A Map of Knowledge Illustrating the Sources of Risk Affecting the Objectives of a Project	12

Figure 2.2: The risk Management Process	22

# ACKNOWLEDGEMENTS

My first appreciation goes to Almighty God for the opportunity, guidance and wisdom to go through this programme. I owe a great deal of appreciation to my supervisor, Prof. Theophilus Adjei-Kumi for his precious contribution and guidance. I also recognize with gratitude, the support of the rest of the staff of the Department of Construction Technology and management, KNUST, Kumasi. I am most grateful to my wife Mrs. Frederica Manso-Howard and my Children, who have gone a very long way to support me in diverse ways.

Finally, I thank my colleagues for their constructive criticisms and to everyone who helped made this a success.

# DEDICATION

I dedicate this work firstly to the Almighty God for the gift of life and how far he has brought me. In addition, I dedicate this work to my wife Mrs. Frederica Manso-Howard and my Children.

# CHAPTER ONE

# INTRODUCTION

# 1.1 Background to the Study

Risk management forms part of our everyday life.  From Babylonian times until the Age of Enlightenment, the risk was not managed systematically, but was more or less based on ‘gut feeling.’ However, a more systematic methodology was seen after statisticians and theorists developed quantified techniques for assessing risk (Douglas , 2009). Risk management is an important part of the decision-making process in construction project management (Tang, Qiang, Duffield, Young, & Lu, 2007), particularly regarding the project’s integration, scope, time, cost, quality, human resources, communications, and procurement. Effective risk management in public investment projects requires a comparison between the potential risk and the possible return or future profits on the project (Flanagan, 1993).

In public investment projects, risk and uncertainty could have either a positive or an adverse outcome. The threat is a result of an adverse risk and opportunity is an outcome of positive risk. Therefore, risk does not indicate a bad thing. However, it means things are uncertain (Cretu, Steward, and Berends, 2011). Since public investment project is very capital intensive, effective risk management is a must. In Ghana, we have seen a lack of effective risk management in very high capital-intensive projects resulting in high judgment debts. Risk management (RM) is a form of decision making within project management (PM), and it is an essential part of the project management plan (PMP); it describes the types, sources, and impacts of potential risks in the project, in addition to which, tools and techniques will be used in risk identification and assessment. Furthermore, Lester defines risk as ‘the combination of the probability of an event and its consequences’ (Lester, 2007).

# 1.2 Problem Statement

Several studies have been conducted on public investment projects, but all these studies do not look at the subject matter holistically. Effective management of risk factors is not studied in details. There is still a research gap in this area. What is common to most of the studies is that they are mainly concerned with cataloging the factors. Only a few have gone beyond and tried to proffer mitigation techniques to some of the factors. They have accessed the factors either at the national level in comparison with other countries or individual company or project levels (Appiah-Kusi, 2003); (Conrad-Mulherin, 2012). There is insufficiently published literature on a more comprehensive evaluation of the effective management of risk factors in public investment projects in Ghana.

This thesis proposes to fill that gap by finding out the most dominant risk factors that affect the management of public investment projects. For that purpose, broad risk categories such as legal, commercial/economic/financial, technical, and political will be the focus of the thesis. These risk categories are adopted and modified after (Hoffman, 2007) who found out that, developing countries, among which Ghana cannot be ruled out, exhibit differences in four major aspects of the business environment including political security; economic security; general infrastructure systems and regulatory and legal systems. Public investment projects (PIP) are plagued with so many issues ranging from procurements to payment of contractor. The extant study will look at the PIP in the construction industry/infrastructural projects where vast sums of money are injected.

# 1.3 Aim and Objectives

# 1.3.1 Aim

This thesis aims to establish the effective management of risk factors in public investment projects in Ghana.

# Objectives

The following specific objectives will be pursued to fulfil the above stated aim:

- To identify risk factors that typically affect public investments projects in Ghana.

- To identify the techniques that are employed in public projects in effective management of risk.

# 1.4 Research Questions

Following research questions will guide the study:

1. What are the risks that affect Public Investment Projects in Ghana?

2. What are the risk management techniques and practices being used to control the identified risks?

# 1.5 Scope of the Study

Even though this study is in the interest of all the participants in the Ghanaian Public Investments Projects, the construction industry was given a priority. Attention was concentrated on crucial personnel of first-class construction firms who had ongoing projects at the time of the study and also filed with the Ministry of Water Resources, Works, and Housing. The study was limited to the current on-going infrastructure projects in the Sekondi-Takoradi metropolis. The study is confined to the application of risk management practices and techniques to control the severity of identified project risk

# 1.6 Research Methodology

In other to be abreast with the current information on the chosen topic, a review of relevant literature was carried out. The purpose of the review was to distinguish what has been done and what is needed to be done in the field, discover the essential variables to the topic and to identify the methodologies and research techniques that have been used (Hart, 2003). A quantitative research method was conducted amongst leading professionals and practitioners in public investment projects in Ghana. Based on the data collected from the interviews, a questionnaire will be developed to be distributed amongst a representative sample of the professionals and practitioners in public investment projects in Ghana. The data tools would consist of close and open questions and would be based on the research objectives. Data collected will be analysed. Data collected was analysed using Statistical Package for Social Sciences (SPSS, version 23). Both Descriptive, Correlational Statistics and Content Thematic Analysis was used to present the data. Quantitative analysis of completed responses has been used. The results of the survey will be presented in the diagrammatical and textual form. According to Kombo and Delno (2009), a research study that raises questions that require interviewing and questionnaires for data collection should use a survey design. The same author further explained and quoted Orodho (2003) as defining descriptive survey as a method of collecting information by interviewing or administering questionnaires to a sample of individuals. Indeed, this is what the questions of my study require and therefore will guide my choice of the research design. Quantitative data for the study would be obtained from both primary and secondary sources such as journals, trusted internet site, books, etc. The study would make use of purposive sampling technique in the selection of respondents for questionnaire administration and interviews.

# 1.7 Significance of the Study

Risk Management Practices have been critical issue encountered by construction professionals in their works. A risk-averse investor will do everything possible to avoid risk. There is the need to provide an outlook of the various risk management practices as it is being carried out on projects. The first and essential step in risk management is the identification of the risk factors that an organization is exposed to. This is followed by the measure of the impacts of each risk factor. Therefore, as this thesis investigates the various country risk factors and ways to mitigates them, it will be very beneficial to the multiple stakeholders in the industry. This research is timely as it seeks to give knowledge on construction firms and how to effectively manage risk on the project. It will help project managers and other professionals find the best way of planning and executing projects through the appropriate risk management tools. This research work will also provide the Ghanaian construction firms with guidelines for best risk management practices. To the other players in the infrastructural, and construction industry such as the client, consultants, sub-contractors, etc., it will provide them with the essential ideas with regards to the risk management of construction firms. This will help to understand how the risk management practices of construction firms lead to the execution of projects. This piece of work will also be of immense benefit to individuals in the academia because it will add up to the already existing body of knowledge in this field. This will include Lecturers and students of various tertiary institutions, where it can be used as a teaching and learning tool. For the government, the findings will be instrumental in that; the government can take the needed policy, legal, economic measures or reforms necessary to make the industry more attractive so that Ghana would continue to be one of the most secure destinations for public investment in Africa and the world at large. Country risk is one essential factors upon which financial institutions base their lending decisions (Simonsen & Perry, 1999). The thesis would also contribute to the existing knowledge on Ghana country risk in general.  Lastly, this work will serve as a direction for further research into the subject area of risk and provides more insight into the risk management practices of construction firms.

# 1.8 Organisation of the Chapters

The study consists of five sections and is organized as follows:

Chapter One: In this chapter, a brief discussion is presented, which is based on the research topic that is ‘Effective Management of the risk factors associated with Public Investment Projects in Ghana’’. This chapter is helpful to offer an overview of the research study including the structure of the research study. This chapter includes research background, research aim, research objectives, and research questions, the rationale of the research study, the significance of the research study and the limitations of the research study.

Chapter Two: This chapter explains the theories as well as the models that are relevant to the research topic. Through library research using appropriate databases and finding out current journals and papers that are relevant to the research topic was conducted. The concepts, theories, and models discussed in this chapter are taken from the previous research studies; henceforth, this chapter is well cited with appropriate references.

Chapter Three: Provides information on how this study was conducted. Beginning with the study methodology, population and sample size, data collection procedures, instrumentation, data analysis procedures, limitation of the research and ethical issues.

Chapter Four: Provides findings and the discussion of the results of the study.

Chapter Five: Provides a summary of the findings, conclusion, and recommendation and suggestions for future work.

Figure 1.1: Research Disposition Diagram

CHAPTER TWO

# LITERATURE REVIEW

# 2.1 Introduction

This section reviews prior studies on the subject being researched. A literature review is “a useful methodology to gain an in-depth understanding of a research topic. A systematic examination of existing publications can help researchers in identifying the current body of knowledge and stimulating inspirations for future research” (Mok et al., 2015, p.447). This serves as a guide for the development of a theoretical framework and hypotheses for this study. This will enable the researcher to apply them to the research findings to arrive at justifiable recommendations and conclusions. Risks are usually inevitable and inherent parts of individuals’ public and business life. There is always a probability that things will go contrary to laid down plans. Many tragedies, incidents, and disasters occur on projects because people did not know about; underestimated or never knew how to respond to the risk events and uncertainties surrounding the job functions they carry out. Risks are prominent in all aspects and at all levels of a project’s or organization’s activities. (Tchankova, 2002). Effective management of risk factors associated with public investment projects in Ghana is essential to ensure timely delivery of projects.

# 2.2 What is Risk?

According to Aven (2014), the word risk is, probably, derived from the early Italian “risicare” which means “to dare” and is commonly used to express a certain probability that, an unwanted event will occur. So, from prehistoric times up to modern times, risk (either physical or economical) has always been part of human’s daily activities and has therefore been incorporated into so many disciplines from insurance to engineering to portfolio theory, etc. According to Bijl and Hamann (2002), this raises some questions: How big is that probability? What are the consequences and what degree of influence do they have on their environment? They argued that the answers to these questions are very subjective and depend on each’s background, experiences, and roles. The subjectivity of risk can be demonstrated by identifying such areas of application as economics, health, safety and environment, information technology and information security, insurance, business and management, services, high-reliability organizations, finance, security and many more. These differences in perception on the issue of risk lead to various definitions and identifications.

(Cervone, 2006) Defines risk, as a problem which has not yet happened. This simple definition somehow really gets to the foundation of the issues which project managers face while performing their functions on projects. They deliberate on these issues and try to develop methods or techniques on how they can avoid them. Even bearing in mind the critical nature of risks and the probability of their occurrence on projects, project managers do not give issues related to risks the attention it requires, they rather than often perform superficial assessments of the risk issues and then add a margin for the risk. Hence Hall (2002), defined risk as an undesired probability that can be measured calculated or estimated and this probability is likely to affect the attainment of project objectives adversely. The quantification can be done by multiplying the probability of failure by the severity of the consequences (Hall, 2002). In almost the same line the European Symposium on Aerothermodynamics/European Space Research and Technology Centre and European Cooperation on Space Standardization (ESA/ESTEC and ECSS. 2000), considered risk as an undesirable situation or circumstance that has both a likelihood of occurring and a potential negative consequence on the project. Browning et al., (2000), Pennock and Haimes (2002), also mentioned the concept of technical or performance risk. To them risk, as such, is “uncertainty that a product design will satisfy technical requirements and the consequences thereof” or the risk that a project will fail to meet its performance criteria.

Defining the concept of risk regarding dimension, Holton (2004) argued that risk “entails two essential components: exposure and uncertainty. Risk, then, is exposure to a proposition of which one is uncertain. In the same school of taught Bijl and Hamann (2002) describe risk as two-dimensional phenomena. For them, an example of this two-dimensional view of risk is the belief that risk equals probability time’s severity. Another view is expressed by Yellmann (2000) who considers risk as multi-dimensional phenomena instead of two dimensions and identified three dimensions of risk which are “Expected Loss, Variability of Loss Values and Uncertainty about the Mental Models used.” Therefore, risk is either a condition of or a multi-dimensional measure of, exposure to unpredictable loss or losses.

A careful examination of the definitions mentioned above and views about risk shows that risk is always viewed as something negative. Van Scoy (1992) expresses a different point of view. According to him, “risk in itself is not bad; risk is essential to progress, and failure is often a key part of learning. But we must learn to balance the possible negative consequences of risk against the potential benefits of its associated opportunity”. This statement implies that there is a certain level of risk that is acceptable. In the same school of thought, the European Cooperation on Space Standardization (ECSS, 2000) argues that risk is acceptable when its magnitude is less than a given threshold which is defined in the risk management policy. Having given this brief definition of risk, highlighting it’s subjective and negative nature one question that someone may ask is: how can risk be dealt with in a business venture? In other words, how can risk be managed? Answer to this question will be provided in the next section.

# 2.2.1 Sources of Risk

Risks in project management can come from different sources. Education and Learning Wales, (2001) indicated the following as sources of risks: Environmental risks, Political risks, Social risks, Financial risk, Legal risks, Technological risks, Commercial risk, Communications risks, Geographical risks, Management risks, Geotechnical risks, Construction risks, Operational risks, and Demand/product risks.  The sources of risk are unique to individual projects and as well related generally to all projects. The related risk in the two domain needs to be reviewed in the process of project risk identification. Figure 2.1 shows map of knowledge illustrating the sources of risk affecting the objectives of a project. Figure 2.1 grouped the risk factors under Engineering risk which can be predicted and Non-engineering risk factors which cannot be predicted. It is appropriate that the forecast of the engineering factors be made at the initial stages of the project since they are predictable. Whereas the non-engineering factors which affect the budgeted cost, estimated time and desired quality of the project, and mainly involve uncertainties should be analyzed and estimated to achieve project objectives.

Figure 2.1: A Map of Knowledge Illustrating the Sources of Risk affecting the Objectives of a Project

Source: Renuka et al., (2014)

# 2.3 Review of Empirical Studies on Project Risk Management

Yarab (2007), In this research conducted in Jordan, there has been the development of risk matrix and the expected yield which can be identified on the organization's position in the environment in which it operates and identify what are the most important factors which could occur in the performance of the organization and get an ongoing assessment of the risks and how those risks affect performance in general through the study of joint relationship between risk and yield. Enshassi et al. (2008), the researcher found in Palestine that, the most essential legal risks are legal disputes during the construction between the parties of the project. According to him, they are of medium importance of risk because the probability of occurrence average is close to low because they understand the importance of solving problems between the parties before it reaches the judiciary. The consequences of their arrival at the judiciary have excess costs and takes time to be resolved judicially. Political risks that cannot be controlled such as bribery and corruption are at the forefront of political risk. But it is important medium, and the results showed that the probability of occurrence of these risks are medium and has a medium impact. Therefore, it is necessary to address them and not to be neglected. The rest of the political risks are the risks of low importance such as the political risk all of which have a low probability of occurrence due to the stability of the country's politics and security.

Namara (2008), Revealed in a study conducted in Malaysia that, risk management is an attempt to identify potential threats to the project and the probability of risk occurrence must take appropriate actions to address these threats and verify the probability of their occurrence. This must include risk management process definition and identify risks, mitigate and reduce risks, and follow-up risk.

Oday (2009), Identified reasons for the delay of project construction in Jordan. Seven main groups were related to the owner and each group included the following reasons such as late payment certificates, intervention of the owner in the work, slow in adoption of decision, wrong estimate for implementation of the project, factors related to contractor in the management of the work site, construction methods , planning unsuitable for the project and the mistakes in the implementation period, lack of experience of the contractor, and included factors related to consultant quality control, and the time of waiting for the results of materials tests.

Suad (2009), Studied in Saudi Arabia that the cost and risk assessment during the implementation phase of the project is a critical factor for success and control of cash flows through that stage.  The things affecting increased cost of risks are the impact the creation of designs, drawings and methods of contracting and other factors and their impact for the formulation of cash flows and avoid disputes that often occur due to lack of understanding or confusion regarding cash flows or Payment Certificates. The research showed that there are a lot of factors that have an impact in increasing the cost of risk. Design requirements is one of the most important factors that influence (80%) the cost overrun of the project, followed by other factors with less impact.

Badri et al. (2012), Observed in Iraq that, project risk management process helps project owners and project teams make decisions regarding alternative plans to achieve their objectives and the risk involved in each item. In order to increase the likelihood of success of meeting the most important objectives is the time. Sometimes at the expense of other objectives, risk management encourages the project team to take appropriate measures to reduce adverse effects to the project such as cost, schedule, and quality to maximize opportunities to improve the project’s goals with lower cost, shorter schedules, enhanced scope and higher quality and minimize management crisis.

El-Sayegh (2010), This study carried out in Kuwait identified that designers generate risks such as defective design, deficiency in drawings, changes in design and documents not issued on time. Design risk arises when there are design errors and omissions as well as design change. This source of risk includes defective or incomplete design documents, inconsistencies, and flaws among the plans and specifications. Design errors could be due to defective design, and unavailable or inappropriate design detail. These happen due to incomplete design scope; incomplete or erroneous geological and geotechnical exploration; and inadequate interaction of design with methods of construction. Salem (2010), Identified cash flow and financial difficulties and transfer to lower bidding work form the most important reasons for the delaying construction projects in Iraq. The contractor is primarily responsible for the delay, followed by the owner and consultant. Compensation claims resulting from causing delay, change orders and additional work are the most important causes of conflicts. Fouzi (2011), found that valuation of companies in Libya is a key factor for the success of the project by making sure the financial, technical and administrative ability and its expertise in the construction. The field study created a form to test construction companies before contracting with them. This form aims to ensure the ability of financial, technical and administrative capacity of companies. Companies that don’t possess the conditions in the form cannot be contracted.

Herroelen (2014), Observed in Ireland that, risk management is generally a part of other management systems such as quality, environmental or work environmental management systems. Some of the core values are environmental management systems, the pledge of all employees, customer concentration, management commitment, focus, continuous improvement, and fact-based decisions. These basic values are closely connected and could easily be found in the theoretical framework of risk management. Haneef et al. (2012), Observed in Iraq that more awareness is required about risk management concerning insurance, organizational policy planning and implementation, project management and general management skills, finance, economics, law, and accounting. Construction organizations need to define well-organized responsibilities and authorities for all stakeholders, by which risk management processes can be established for senior engineers working in construction projects.

Mohammed (2012), Identified that in Syria, people must know the degree of risk before the start of any project to achieve goals. The project manager must know what will happen and what should be done in the event of any change to find support for the project plans such as transferring resources from inside the project. He must know the likelihood of changes because he must continue the project without delay and have justification for that. Other costs or extra time or slow performance would weaken the project, and these are exposed to costs He should develop a plan for the unexpected and speculate time and budget.

Jaser (2013), Reported that the contractors and owners still depend on traditional approaches to managing risk factors and their consequences in Kuwait. The use of right judgment to control risk factors was the most applied method used to control risk events, and these results assure the need to develop the used methods for managing risk factors. Use of quantitative methods, computer systems or sensitivity analyses were not practiced by respondents, they also depend on right judgment and comparing analysis to analyse risk consequences. El-Sayegh (2015), Concluded that the construction sector is facing two main reasons relating to production, and information infrastructure and that the construction sector in Dubai, is one of the basic employments and income growth in the emirates. The sector faces five major challenges which need immediate attention to help the construction sector to face the economic crisis and recession. The study revealed that the first of those risks, i.e. the supply of inputs and inflate costs, which impacts on the profitability levels, as the lack of infrastructure to provide that information leads to the risks, due to a significant imbalance between supply and demand. The global financial crisis has caused a slowdown in the construction sector, but a correction that has occurred in this sector succeeded compared to the economies of other countries with large contracting sectors.

Iqbal (2015), Observed in Tunisia that contractors want owners to accept and share more risks with them. This can be attributed to two factors; first, owners have some control over some of the risks, for example, the payment on contract, changes in work, and scope limitations and work definition. Second, because the high competition in the market has slowed the economy in recent years, the surveyed risks have the highest impact on the schedule of a project while the same risks affect the safety of the project. Most of the risk categories affect schedule and budget more than other project parameters. Heba (2014), This recent study in the Emirates, Dubai, showed that a lot of insurance companies in the Arab region and the Arab Gulf face some challenges when they are submitted to insurance services associated with some significant projects in the world. This has spread dramatically recently and has become so much representing distinctive landmarks in the cities and the Gulfian states.  The study included a survey of the views of officials in the local insurance industry to know if the local insurance companies suffer from these challenges, and whether they are capable and qualified as required to ensure this type of project as well as various mega significant financial value in state projects. Most insurance companies at the moment do not have the qualifications and no possibilities to deal with this significant development projects, and to be able to do so, it must combine the efforts of local insurance companies to work together with each other as joint coordination will increase the financial capacity and the exchange of experiences and competencies through work joint committees between these companies. In addition to bringing in expertise from abroad to assist in the work on such projects.

Alexander (2015), this study carried out in Egypt revealed that risk management is a complicated process that interrelates with many other processes in the construction industry. Investigating project risks includes studying potential events that may affect the scope, cost, time, or performance of the project's objectives. Investigating potential risks requires the collaboration of all disciplines contributing to the project. Technical, managerial, financial, and administrative departments of the participating firms. Organization’s risk management policy should set out its approach to risk management. The policy should also set out responsibilities for risk management throughout the organization.

MacKenzie (2010), In Sweden, the construction sector at some time suffered from poor performance and lack of control in most steps of the execution process due to the sector’s problems with many faults and increasing buildings costs.  The government initiated and assigned a commission whose assignment was to concentrate on where the problems are and how to increase the effectiveness instead of the costs. They found amongst other things the cost and the construction faults, risks and other uncertainties can cause losses leading to increased costs, delay in construction period and lack of quality during the implementation of the projects. Gunhan (2015), Observed that in the Philippines, international projects are generally more difficult to manage due to conditions such as multiple ownership, elaborate financial provisions, and different political ideologies.

# 2.4 Definitions of Risk Factors

Project Management Institute, (2004) defines risk as “uncertain event or condition that, if it occurs, has positive or negative effects on at least one project objective, such as time, cost, revenues and profits” and in the mining industry, the uncertainties include social and environmental, political, engineering, long lead and capital-intensive venture, economical, exhaustibility and some of these are briefly defined below.

Political risk is defined as uncertainty over the actions not only of governments and political institutions but also of minority groups and separatist movements (MIGA, 2011).

Economic/financial/commercial risks are broadly defined as currency instability, and exchange rate, transfer, and convertibility, inflation, input cost escalation, changes in demand or price for the product (Conrad-Mulherin, 2012) and legal risks are described by Conrad-Mulherin, (2012) as changes to the judicial, regulatory or legal framework in the jurisdiction the project is being developed. While some of these risks are industry-specific and cut across country boarders, others and especially the severity of their impacts are country-specific. In other words, the existence and the effects of these risks vary from one country to the other country and, for that matter, will be referred to as country risks. Definition of country risk as well as its factors are very subjective and depend on the purpose for which individuals evaluate them. For this thesis, a more comprehensive description of the component’s factors of each of these risk categories, their mitigation measures as well as their application to the Ghanaian capital-intensive projects is presented.

# 2.5 Risk Classification in Investment Projects

The risk classification concerning respect to investment projects are:

- Strategic Risks;

- Change risks;

- Operational risks;

- Unforeseeable risks

# 2.5.1 Strategic Risk

This is the type of risk that evolves at the corporate level of an organization or management level of a project and affects the development of a project’s strategy. (Broyd, 2001) Reveals that the construction industry has developed both flexibility and excellent skills in problem-solving but lacks the capability of ‘planning for the future.’ Also, risks due to poor forecasting or assessment of the market conditions or economic characteristics of the country or the countries in which an oil company will carry out its operations is a vital strategic risk which should be given due consideration through feasibility studies of prices of materials, economic policies and stakeholders (business partners, local communities and suppliers).

# 2.5.2 Change Risk

These are the types of risks that relates to imposed or planned changes which occur on projects. A planned change arises when new strategies are formed while an imposed change arises due to external and internal forces. A typical example is; during the design process for oil and gas structures in Ghana, any shortcomings with respect to materials, product geometry, functional specifications, etc., expose projects to change risks which results to excesses of materials being used; extra incurred costs due to project delays; resource reallocations, additional operations and rework (Ahmed et al., 2007).

# 2.5.3 Operational Risk

Operational risks are the risks coming from failed or inadequate internal production processes, systems and people as well as coming from external factors or events. These are the types of risks that relates to the production processes involved on a project and involves the working techniques used by project team members; the asset base of the project; the stakeholder relationships (human resources and staff development) within the project team and legal risks (contractual issues, statutory obligations and liability (internal processes).

# 2.5.4 Unforeseeable Risk

Unforeseeable risks are the risks that occur because they cannot be accurately forecasted before they occur.  No matter how great a project’s planning processes could be, there is always something that goes wrong somewhere. There have been several accidents on projects due to ground conditions, fire outbreaks and air pollution. Therefore, companies cater for this by building in contingencies for these risks into the overall strategic plan concerning time, cost and quality objectives for their projects. In cases where the company cannot contain the impacts, like cases of flood, fire or any natural disaster; companies pay very high premiums to insurance companies to transfer liability for such events to the insurance companies because of the hazardous nature of the oil and gas operations. Variation in interest rates for bank loans, inflation and increases in government taxes are so prevalent in Ghana.

# 2.6 The Risk Management Process

Overall risk management is the process of identifying and evaluating the risks and developing strategies to manage it. These strategies include the transfer of risks to other parties and to avoid and minimize the negative effects and to accept some or all of its consequences. Traditional risk management focuses on the risks arising from physical or legal reasons (example: natural disasters, fires, accidents, death, and lawsuits) on the other hand, financial risk management focus on those risks that can be managed using financial barter. Regardless of the type of risk management, all the big companies and small businesses have a dedicated team of risk management. The risk management process should include the definition of risk identification, risk analysis, risk mitigation, monitoring and control of risk as show in Figure 2.2

Figure 2.2: The risk Management Process

RISK IDENTIFICATION

RISK ANALYSIS

RISK MITIGATION

RISK MONITORING

# 2.6.1 Risk Identification

This phase aims to identify all the potential risks that may face the project and threaten its goals, and this requires methods to identify risks such as questionnaire, interviews with project managers or officials in companies, checklists, brainstorming, or Delphi Technique. Risk identification can depend on goals; any risk impedes the achievement of project goals considered risk.

# 2.6.2 Risk Analysis

Qualitative analysis of risks is most common in the risk analysis process. On part, uses qualitative risk analysis to prioritize risks that affect the goals of the project, and must be done on qualitative analysis of the risks at the beginning of the project and reviewed during the implementation to keep pace with changes in the level of risk.

The ranking of risks: Each project has different risks associated with its processes, risk implementation, all of which affect the activities of the project. A technique used in risk arrangement is Probability Impact Risk Rating Matrix (Ward, 1999) as shown in Table 2.1, which expresses the value of all the risk in numbers 1,5,10 to signal risk arrangement (low, Medium, High). Risk = Possibility x impact.

Table 2.1: Probability Impact risk Rating Matrix

| Impact |  | Probability |  |
| --- | --- | --- | --- |
|  | Low (1) | Medium (5) | High (10) |
| Low (1) | 1 | 5 | 10 |
| Medium (5) | 5 | 25 | 50 |
| High (10) | 10 | 50 | 100 |

Source: Ward (1999)

# 2.6.3 Risk Mitigation

The goal of this strategy is to mitigate the consequences of the risk to an acceptable level. Taking some of the actions that mitigate the risks for the best to take action to address the consequences of that risk. Examples of actions taken before the start of implementation of the projects during implementation, or the engineering or seismic tests or the selection of suitable suppliers, these procedures may include changing the conditions to mitigate the potential for danger, such as adding resources or time to the activities of the project.

# 2.6.4 Risk Monitoring and Follow Up

It is monitor and follow up of the effectiveness of the actions taken, or any other deviations can occur in the project.

# 2.7 Chapter Summary

Investment projects are always associated with risk and uncertainty because of the length of the implementation period that change the conditions making it contain multiple risks. The most important risk facing the projects in Ghana are the presence of companies/contractors not able to implement projects on time and in the required quality and the approved budget and specifications agreed upon. Valuation of companies is a key factor in the success of the project by making sure the financial, technical and administrative capabilities and expertise in the implementation of previous projects. Therefore, this field study was to determine effective risk management techniques in investment projects, and the purpose of this model is to ensure the ability of companies/contractors financial, technical and administrative capabilities and expertise in the implementation of projects. The definition of criteria that must be available in these companies in the suggested form to be invited to the auction. These companies in the project and these standards are (financial situation, material resources file, years of experience of the company, technical file, human resource file, planning and Follow-up, safety and Insurance). Using this suggested form to evaluate companies before contracting with them is recommended. The preparation checklist contains the risk of the projects to be a reference point for any owner or implementer of projects to be taken into account when hiring or implementation of projects. These risks have the greatest impact on the time, cost, and quality.

# CHAPTER THREE

# RESEARCH METHODOLOGY

# 3.1 Introduction

The chapter gives the procedure which was used in collecting data for the study. Information regarding the strategy, design, target population and sample size are also described. A detailed methodology and tools used are described. Two methods were used in achieving the aim and objectives of this study. First of all, relevant information relating to the thesis topic was gathered through the literature review and the second, was through questionnaires survey by sending structured questionnaires to targeted respondents in order to obtain feedback. Once the data was available, analyses were made and the yielded results discussed, and finally, recommendations made.

# 3.2 Research Methodology

Research methodology refers to the underlying theory of how research is conducted. It provides the theoretical and philosophical assumptions of the study and its consequence on the method or methods adopted for the study (Saunders et al., 2009). It is subsequently used to probe the research problem, collect, analyze and interpret the data (Dainty, 2007).

# 3.3 Research Philosophy

This research has adopted the positivist approach to research due to the empirical and quantitative nature of the study.  Another reason for the choice of this philosophy is the fact that the study has used statistical models and descriptive statistics in explaining the variables. The scientific nature of the study, however, ensures that the research is positioned towards the value-free end of the axiological context of research philosophy. Davison and Martinsons (2011) refers to research philosophy as the belief about the way in which data of a phenomenon should be gathered, analyzed and used. The term epistemology (what is known to be true), as opposed to doxology (what is believed to be true), encompasses the various philosophies of research approach (Davison and Martinsons, 2011). Galliers (1991) has indicated that the purpose of science then, involves the process of transforming things believed into things known, i.e., from doxa to episteme. According to Galliers (1991), two major research philosophies have been identified in the Western tradition of science, i.e., positivist, which is also sometimes called scientific, and interpretivist, which is also known as antipositivist. Positivists believe that reality is stable and can be observed and described from an objective viewpoint (Levin, 1988), i.e., without interfering with the phenomena being studied. The proponents of this view contend that phenomena should be isolated and that observations should be repeatable. This often involves manipulation of reality with variations in only a single independent variable so as to identify regularities in, and to form relationships between, some of the constituent elements of the social world (Davison and Martinsons, 2011). According to them, predictions can be made on the basis of the previously observed and explained realities and their inter-relationships. Hirschheim (1985, p.33) has said that "positivism has a long and rich historical tradition. It is so embedded in our society that knowledge claims not grounded in positivist thought are simply dismissed as a scientific and therefore invalid" This view is indirectly supported by Alavi and Carlson (1992) who, in a review of 902 MIS research articles, found that all the empirical studies were positivist in approach. Positivism has also had a particularly successful association with the physical and natural sciences. On the other hand, the Interpretivists contend that only through the subjective interpretation of an intervention, in reality, can that reality be fully understood. The study of phenomena in their natural environment is key to the interpretivist philosophy, together with the acknowledgment that scientists cannot avoid affecting those phenomena they study. They admit that there may be many interpretations of reality, but maintain that these interpretations are in themselves a part of the scientific knowledge they are pursuing. Interpretivism has a tradition that is no less glorious than that of positivism, nor is it shorter.

# 3.4 Research Strategy

Research strategy has been defined by Saunders, Lewis, and Thornhill (2009) as the general plan of how the researcher goes about answering the research questions. Bryman (2008) similarly define it as a general orientation to the conduct of research. Research strategy, according to Remenyi and Williams (2003), provides the overall direction of the research including the process by which the research is conducted. Saunders et al. (2009) mentioned that appropriate research strategy has to be selected based on research questions and objectives, the extent of existing knowledge on the subject area to be researched, the amount of time and resources available, and the philosophical underpinnings of the researcher. Easterby-Smith et al. (2008), Collis and Hussey (2009) and Saunders et al (2009) have identified some of the standard research strategies used in business and management as experiment, survey, case study, action research, grounded theory, ethnography, archival research, cross-sectional studies, longitudinal studies and participative enquiry. From these various strategies, this research sought to adopt the case study research strategy as the appropriate strategy for research. The case study as a strategy has been defined by Yin (2003) as an “empirical inquiry that investigates a contemporary phenomenon within its real-life context, especially when the boundaries between phenomenon and context are not clearly evident”. The definition put forward by Collis and Hussey (2013), also identified some of the observable characteristics of case study strategy. They defined the case study as “a methodology that is used to explore a single phenomenon in a natural setting using a variety of methods to obtain in-depth knowledge.” Therefore, it can be seen that case study research is capable of accommodating different research techniques and is usually used when it is required to obtain in-depth knowledge with regard to a particular phenomenon.

# 3.5 Research Approach

This research has applied the inductive approach to research. Bryman and Bell (2015) and Saunders et al. (2012) have indicated that in inductive inference, known premises are used to generate an untested conclusion. In terms of generalizability, the inductive inference generalizes from the specific to the general. Three major approaches to research have been identified. These according to Kathori (2004) are qualitative, quantitative and the mixed approach. However, these approaches are suitable for specific types of researches. Snape and Spencer (2003) defined qualitative research as an interpretative method based on comprehending the explanation given by individuals to occurrences within their environment. According to Denzin and Lincoln (1998), the qualitative research focuses on understanding how social meaning is obtained and emphasizes on the relationship between researchers and the topic. Quantitative research, on the other hand, focuses on the measurement and analysis of relationship between variables (Denzin and Lincoln, 1998). This research approach collects numerical data in order to explain, predict and/or control phenomena of interest. With respect to the mixed approach, Creswell et al. (2003) defined the approach as the adoption of both the quantitative and qualitative analysis in a particular study. This study is most preferred when the integration of both the qualitative and quantitative approach in the study gives a much better understanding of the study than using just one of the approaches. Descombe (2003) established that in order for research to obtain accurate results, the researcher must adopt an approach that is appropriate, rational and unambiguous. Bryman et al. (1988) further explains that the decision to choose either approach should be made in accordance with the appropriateness of the approach to answer the research question. This study has adopted the descriptive and quantitative research design. This design is deemed appropriate in the sense that it has allowed the researcher to familiarize herself with the concepts studied and consequently helped to generate testable hypotheses. Also, this study collected quantifiable data, used mathematical data analysis and the expression of the final result in statistical terms.

# 3.6 Research Design

The research design is a combination of the research strategies of inquiries (e.g., surveys and cases studies), research choices (mono-method or mixed methods) and time horizon (Saunders et al., 2009) and thus relates to the method of enquiry which provides specific direction for procedures necessary for achieving the research objectives (Creswell, 2014). Dainty (2007), emphasized that the research design in consonance with the underlying philosophies provides a broader structure for conducting the research and effectively plays the role of positioning the investigator in the empirical world and links the research questions to the relevant data. The study has adopted the descriptive survey design which determines and reports the way things are (Gay, 1992). According to Polit et al. (1995), the descriptive survey aims at primarily describing, observing and documenting an aspect of a situation as it naturally occurs rather than explaining it. The descriptive sample survey has been recommended by Babbie (1990) for the purpose of generalizing from a sample to a population so that inferences can be made about some characteristics, attributes, or behavior of the population.

# 3.7 Study Population

Statistically, Population is explained to be units that have the chance to be involved in the survey sample. The units could be people, employee or members of a particular set (Groves et al., 2009). For the purposes of this study, attention was concentrated on crucial personnel of first-class (D1K1) construction firms who had ongoing projects at the time of the study and also filed with the Ministry of Water Resources, Works, and Housing. The study was limited to the current on-going infrastructure projects in the Sekondi-Takoradi metropolis. A total number of Seventy (70) professionals form the study population. The choice of first-class building contractors for this study is based on the consideration of their strong organizational nature coupled with their financial and technical capacity in the execution of large demanding projects.

# 3.8 Sampling and Sampling Technique

Sampling serves to provide practical ways of ensuring that data collection and processing aspects of research are done whilst making sure that the sample is an accurate reflection of the population (Fellows and Liu, 2003). Purposive sampling was employed to represent the total sample size since the study is concerned with Contractors having on-going building projects in the Sekondi-Takoradi Metropolis. A list of contractors was compiled from the identification of on-going projects being executed by D1K1 Contractors and the samples were selected from the stratum of the target population of these on-going projects.

# 3.8.1 Sample Size

Wood and Haber (1998) defined the sampling as the process used in choosing representative units of a population for the study in a research investigation. Scientific knowledge is derived from samples. Sampling procedures help in solving problems in scientific research works (Wood and Haber, 1998).  Burns and Grove (1987), posited that historically a minimum of 30 subjects as a sample size can be used but describes 30 subjects as inadequate as a sample size for most research works (Burns and Grove, 1987).  The sample size for the study was arrived at using statistical calculation. The formula as shown below derived by Creative Research Systems (2005) was used to determine the sample size of unlimited population:

SS = Z2×P×(1-P)C2………………………... (1)

Where SS = Sample Size.

Z = Z Value (e.g. 1.96 for 95% confidence interval).

P = Percentage picking a choice, expressed as a decimal, (0.50 used for sample size needed).

C = Confidence interval (0.05)

SS = 1.962×0.5×(1-0.5)0.052

SS = 0.96040.0025

SS= 384

Correction for finite population

SSnew= SS1+SS-1pop……………………………………. (2)

Where pop is the population = 70 identified D1K1 Contractors having on-going projects within the Sekondi-Takoradi Metropolis, SSnew= 3841+384-170

SSnew= 59

59 questionnaires are to be administered to contracting firms.

# 3.9 Research Instrument

The study used both the primary and the secondary sources of data in gathering data for the study. The secondary data were desktop information. The primary data was collected from the various firms using the questionnaire as the research instrument. Wilkinson and Birmingham (2003) described research instruments as tools that are employed in the collection, translation, and organization of data into valuable information through a systematic and strenuous survey to help in the interpretation of the data. Gray (2004) asserted that the choice of research instrument adopted for a study is dependent on the sort of questions the researcher intends asking and the purpose of the study. Also, other factors such as time and resource also influence the researcher’s decision.

The empirical nature of this study dictated that primary data was collected by administering survey questionnaires which were designed after extensively consulting literature (Barako and Gatere, 2008; Gomez-Conde, 2015). The consultation of literature for the development of the questionnaire follows the view of Miller and Yang (2008) that the survey questionnaire can either be developed entirely by the researcher or by adopting and/or adapting questions and statements from earlier studies in similar works. Punch (2003), emphasized the merits of using existing questions, indicating that it enables the comparison of past and present results in related research. The researcher in the development of the questionnaire must ensure that personal biases which could offend respondents are not exhibited in the process. In this regard, most of the constructs and the relevant measures in the study were generated and modified to suit the current context from previous. The survey questionnaire was deliberately divided into four (4) parts to capture topical issues effectively reflecting three of the objectives of the study. Section one of the questionnaire featured problems directed at obtaining background information about respondents and their institutions. The other three sections of the questionnaire covered issues on identified risk factors and their severity, Relative usage of risk preventive methods on projects and Relative usage of risk mitigation methods on an investment project in Ghana. The questionnaires were administered by hand to 59 respondents who are made of representatives from the identified target population.

# 3.10 Data Analysis

The results were analyzed in percentages and figures using descriptive statistics and presented in the form of bar charts and tables with the help of SPSS. The Importance Index was also used to assess the severity of identified risk factors, a relative to the various risk management practices and techniques. It was also used to rank the identified risk factors and the risk management practices being used by contracting firms. In order to generate the result, the researcher used the Statistical Package for Social Sciences (SPSS) version 16.0. The Relative Importance Index (RII) helped in determining the severity of risk factors and the usage of the relativity of management practices. The Index is computed in Adnan et al. (2007) as:

Importance Index = Ʃ (1n1 + 2n2 + 3n3 + 4n4 + 5n5)

5(n1 + n2 + n3 + n4 + n5)

Where:

n1 - the number of respondents who answered “very insignificant.”

n2 - the number of respondents who answered “insignificant.”

n3 - the number of respondents who answered “neutral.”

n4- the number of respondents who answered “significant.”

n5- the number of respondents who answered “very significant.”

# 3.11 Test of Validity and Reliability

Reliability of the constructs was tested by calculating the Cronbach’s α coefficient which is a measure of internal consistency, that is, how closely related a set of items are as a group.    It is considered to be a measure of scale reliability. A "high" value for alpha does not imply that the measure is unidimensional.  Cronbach’s alpha can be written as a function of the number of test items and the average inter-correlation among the items.  Below is the formula for the standardized Cronbach’s alpha:

Table 3.1 shows Cronbach alpha and internal consistency.

Table 3.1: Cronbach's Alpha

| Cronbach’s alpha | Internal Consistency |
| --- | --- |
| α ≥ 0.9 | Excellent |
| 0.9 > α ≥0.8 | Good |
| 0.8 > α ≥ 0.7 | Acceptable |
| 0.7 > α ≥ 0.6 | Questionable |
| 0.6 > α ≥ 0.5 | Poor |
| 0.5 > α | Unacceptable |

Source: Bland and Altman (1997).

# CHAPTER FOUR

# DATA ANALYSIS AND DISCUSSION OF RESULTS

# 4.1 Introduction

This chapter focuses on organization, structuring and characteristics of the data collected from the field as well as the analysis and interpretations drawn from it to address the key research objectives and questions captioned in chapter one. The results obtained are compared with the relevant literatures and the researcher comments are added. This chapter deals with the analysis and discussion of the data collected to identify effective management of risk factors in public investment projects in Ghana. This chapter also presents the results of the analysis and discussions in the form of texts and Tables. The chapter is organized as follows; Background information of Respondents and analysis of dependent variable. Out of the fifty-nine (59) questionnaires administered, fifty (50) were completed and returned representing 85%. The analyses are based on the 85% questionnaires completed and returned. The high response rate can be attributed to the fact that questionnaires were administered in person and successive follow-ups thereafter. When the questionnaires were issued to the respondents in person, the respondents were encouraged to fill it right away.

# 4.2 Data Analysis

The data analysis was carried out in two parts. The first part concentrated on the background of the respondents which was based on information carried in the section A, general information of the questionnaire, section B comprises risk factors that typically affect public investments projects in Ghana, the causes of the risk on infrastructural projects in Ghana and risk mitigation techniques that are being practiced in the Ghanaian construction industry.

# 4.3 Presentation of Results and Discussions

To give weight to the results of the study the researcher deems it relevant to probe the background of his respondent. On the first part of the analysis, descriptive statistics were obtained on the responses given on the variables in the section A. This involved the frequency and percentage of responses to each of the variables. The questions centred on their position in their firm, experience and level of education. This helped to assess and increase the validity, reliability and precision of the responses and result of the main research. The result is summarized in Table 4.1, 4.2 and 4.3

# 4.3.1 Organizational Role

Table 4.1 below shows that Majority of the respondents of the survey were either holding the position of Project Manager, Architect, Project Team Member, Project Consultant and Site Engineer. Nearly, 18% were Project Managers (N = 9), 16% were Architects (N = 8), 32% were Project Team members (N = 16), 14% were project consultants (N = 7) and 20% were Engineers (N= 10). The respondent position is vital to ensure some degree of reliability of the data. Since they are all working in the maintenance department of the firm, this makes them credible and reliable source of information which is needed for this study.

Table 4.1 role in the organization

| Item | Frequency | Percentage (%) |
| --- | --- | --- |
| Project Manager | 9 | 18% |
| Architect | 8 | 16% |
| Project Team Member | 16 | 32% |
| Project Consultant | 7 | 14% |
| Site Engineer | 10 | 20% |
| Total | 50 | 100 |

Source: Field Survey, 2018

# 4.3.2. Educational level of respondent

Table 4.4 below shows that Majority of the respondents of the survey were either Holders of PhD, Master’s Degree (MSc, MPhil, and MBA), Bachelor of Science or Higher National Diploma. 2% of the Respondents were holders PhD, 28% are holders of a Master Degree, 52% holds a Bachelor’s Degree, and whiles 18% were holders of Higher National Diploma. The results indicate that majority of the respondents are highly educated and well qualified. The respondents work for well-established firms that have a lot of experience. They also fall within the targeted group the researcher intended to study.

Table 4.2: Educational Level of Respondent

| Item | Frequency | Percentage (%) |
| --- | --- | --- |
| Higher National Diploma (HND) | 9 | 18% |
| Bachelor Degree | 26 | 52% |
| MBA/MSc/MPhil | 14 | 28% |
| PhD | 1 | 2% |
| Total | 50 | 100 |

Source: Field Survey, 2018

# 4.3.3 Working Experience of Respondents in the Construction Industry

The intention of this question was to identify the level of experience of the respondents in the construction industry since how long they have been in the construction industry will affect the quality of the response given. From the table, bulk of the respondents have been in the building industry for more than 6 years representing 88% (N=13+19+12). Approximately, 12% indicated level of less than 5 years’ practice in the building industry. Accordingly, it can be deducted that, they have had a lot of experience in the Ghanaian construction industry and for that matter are capable of giving in-depth information on the issues under discussion. And the balances of a variety of levels of experience will therefore enable a generalized and realistic view as far as this research is concerned.

Table 4.3: Working Experience of Respondents

| Item | Frequency | Percentage (%) |
| --- | --- | --- |
| Less than 5 years | 6 | 12% |
| 6 to 10 years | 13 | 26% |
| 11 to 15 years | 19 | 38% |
| Above 16 years | 12 | 24% |
| Total | 50 | 100 |

Source: Field Survey, 2018

# 4.4 Analysis and Discussion of Main Objectives

# 4.4.1 Risk factors that typically affect public investments projects

From Table 4.4 below, using mean score ranking to determine the risk factors that typically affect public investments projects, change of government was ranked first with a mean of 4.6667 and a standard deviation of .48305. Changes in management ways, Lower quality of work, change of government policy, new governmental acts or legislation, Poor communication between parties involved, Resource management, Ambiguous planning due to project complexity and Changes in design were also ranked in order of 2nd to 10th respectively. The least ranked Risk factors that typically affect public investments projects are Legal disputes during the construction phase among the partners, Gaps between the Implementation and the specifications due to a misunderstanding of drawings, Delayed disputes resolutions, Undocumented change orders among others as shown in table 4.4. They all had a mean and a standard deviation value greater than 3.0571 and .43644 respectively indicating their high-risk factor to public investment projects. These responses conform to literature. Wales (2001) indicated the following as sources of risks: Environmental risks, Political risks, Social risks, Financial risk, Legal risks, Technological risks, Commercial risk, Communications risks, Geographical risks, Management risks, Geotechnical risks, Construction risks, Operational risks, and Demand/product risks. Oday (2009), Identified reasons for the delay of project construction in Jordan. Seven main groups were related to the owner and each group included the following reasons such as late payment certificates, intervention of the owner in the work, slow in adoption of decision, wrong estimate for implementation of the project, factors related to contractor in the management of the work site, construction methods , planning unsuitable for the project and the mistakes in the implementation period, lack of experience of the contractor, and included factors related to consultant quality control, and the time of waiting for the results of materials tests.

Table 4.4 Risk Factors that Typically Affect Public Investments Projects

| Factors | Mean | Std. Deviation | Ranking |
| --- | --- | --- | --- |
| Political | 4.5714 |  |  |
| Change of government | 4.6667 | .48305 | 1th |
| Change of government policy | 4.5238 | .60159 | 4th |
| New governmental acts or legislation | 4.5238 | .67964 | 5th |
| Management | 4.3143 |  |  |
| Ambiguous planning due to project complexity | 4.3810 | .80475 | 8th |
| Resource management | 4.3810 | .74001 | 7th |
| Changes in management ways | 4.6190 | .58959 | 2nd |
| Information unavailability |  |  |  |
| (include uncertainty) | 3.7143 | .46291 | 15th |
| Poor communication between parties | 4.4762 | .60159 | 6th |
| Legal | 4.0317 |  |  |
| Legal disputes during the construction phase among the partners | 4.2381 | .88909 | 10th |
| Delayed disputes resolutions | 4.0952 | .70034 | 12th |
| No specialized arbitrators to help settle fast | 3.7619 | .43644 | 14th |
| construction | 3.95675 |  |  |
| Rush bidding | 3.0571 | .96362 | 16th |
| Gaps between the Implementation and the specifications due to a misunderstanding of drawings | 4.1905 | .51177 | 11th |
| Undocumented change orders | 3.9341 | .45075 | 13th |
| Lower quality of work | 4.6190 | .49761 | 3rd |
| Changes in design | 4.2857 | .56061 | 9nd |
| The difference in actual and contract executed quantities | 3.6541 | .45192 | 17th |

Source: Field Survey, 2018

4.4.2 Risk Mitigation Techniques

In determining the risk mitigation technique, a list of factors (seven factors) were identified from literature and respondents were asked to rate those according to their level of influence of each technique on a five-point Likert scale items. The adopted scale read as follows,

5= Always; 4= often; 3=Sometimes; 2= rarely; 1= Never. In analysing the results of the risk mitigation techniques, relative importance index was used. from table 4.6 below, it is interesting to note that all the seven (7) factors seems influential as they had a mean score and an RII value greater than 3.50 and 0.700 respectively. However, considering the risk mitigation techniques in order of ranking, respondents indicated that, planning for alternative methods as stand-by was rated first with a mean score and RII value 4.38 and 0.912 respectively. This was followed by Transfer or share risk to/with other parties, Refer to previous and ongoing similar projects for accurate, Utilize quantitative risk analyses techniques for accurate time, consciously adjust for bias risk premium to time estimation, Depend on subjective judgment to produce a proper program and Produce a proper schedule by getting updated project information. They all had a mean score and an RII value greater than 4.00 and 0.700 respectively. The goal of this strategy is to mitigate the consequences of the risk to an acceptable level. Taking some of the actions that mitigate the risks for the best to take action to address the consequences of that risk. Examples of actions taken before the start of implementation of the projects during implementation, or the engineering or seismic tests or the selection of suitable suppliers, these procedures may include changing the conditions to mitigate the potential for danger, such as adding resources or time to the activities of the project.

Table 4.5 Risk Mitigation Techniques

| No. | Challenges | Mean | RII | Ranking |
| --- | --- | --- | --- | --- |
| 1 | Plan alternative methods as stand-by | 4.38 | 0.912 | 1st |
| 2 | Transfer or share risk to/with other parties | 4.31 | 0.882 | 2nd |
| 3 | Refer to previous and ongoing similar projects for accurate | 4.29 | 0.901 | 3rd |
| 4 | Utilize quantitative risk analyses techniques for accurate time | 4.25 | 0.872 | 4th |
| 5 | Consciously adjust for bias risk premium to time estimation | 4.21 | 0.885 | 5th |
| 6 | Depend on subjective judgment to produce a proper program. | 4.33 | 0.854 | 6th |
| 7 | Produce a proper schedule by getting updated project information | 4.24 | 0.865 | 7th |

Source: Field Survey, 2018

# CHAPTER FIVE

# SUMMARY OF FINDINGS, CONCLUSION AND RECOMMENDATION

# 5.1 Introduction

The summary of the key research findings tailored to the proposed research aim and objectives are presented in this chapter. The conclusion, relevance and contributions of this study are also underlined in this chapter. Further, limitations of the research and suggestions for future research directions are provided as well.

5.2 Summary of Findings

This research was instigated with the primary aim of finding out effective management of risk factors in public investment projects in Ghana. In pursuing this aim, two objectives were set out. The achievement of each of these research objectives is set out in the following subsections.

# 5.2.1 Risk factors that typically affect public investments projects

The study reveals that, change of government, changes in management ways, lower quality of work, change of government policy, new governmental acts or legislation, poor communication between parties involved, resource management, ambiguous planning due to project complexity, changes in design, legal disputes during the construction phase among the partners, gaps between the implementation and the specifications due to a misunderstanding of drawings, delayed disputes resolutions, undocumented change orders are the major risk factors that affect public investments projects in Ghana. These were supported by Wales (2001) and Oday (2009).

# 5.2.2 Risk mitigation techniques

From the study it is interesting to find out that, planning for alternative methods as stand-by, transfer or share risk to/with other parties, referring to previous and ongoing similar projects for accurate, utilize quantitative risk analyses techniques for accurate time, consciously adjust for bias risk premium to time estimation, depend on subjective judgment to produce a proper program and produce a proper schedule by getting updated project information are the major risk mitigation techniques. The goal of these techniques is to mitigate the consequences of the risk to an acceptable level. Taking some of the actions that mitigate the risks for the best to take action to address the consequences of that risk. Examples of actions taken before the start of implementation of the projects during implementation, or the engineering or seismic tests or the selection of suitable suppliers, these procedures may include changing the conditions to mitigate the potential for danger, such as adding resources or time to the activities of the project.

# 5.3 Conclusion

This study explored the effective management of risk factors in public investment projects in Ghana. In attempt to achieve this aim, two objectives were set which includes, identifying risk factors that typically affect public investments projects in Ghana and to identify the risk mitigation techniques that are being practiced in the Ghanaian construction industry. The study reveals that, Change of government, Changes in management ways, Lower quality of work, Change of government policy, new governmental acts or legislation, Poor communication between parties involved, Resource management, Ambiguous planning due to project complexity, Changes in design, Legal disputes during the construction phase among the partners, Gaps between the Implementation and the specifications due to a misunderstanding of drawings, Delayed disputes resolutions, Undocumented change orders are the major risk factors that affect public investments projects in Ghana. Considering the mitigation technique planning for alternative methods as stand-by, Transfer or share risk to/with other parties, Referring to previous and ongoing similar projects for accurate, Utilize quantitative risk analyses techniques for accurate time, consciously adjust for bias risk premium to time estimation, Depend on subjective judgment to produce a proper program and Produce a proper schedule by getting updated project information are the major risk mitigation techniques.

# 5.4 Recommendation

In view of the findings of this research, the following recommendations are therefore prescribed.

- Investors working in the public sector have to be aware of the fact that, change of government and change of government policies have a major risk on public investment and as such they should always bear in mind and also have alternatives as a stand-by.

- It is also recommended that investors find means to Transfer or share risk to/with other parties through insurance from a third party.

- Investors should document their change orders and also ensure effective communication between parties involved in an investment contract.

- It is again recommended that whenever there is misunderstanding between parties, referring to previous and ongoing similar projects for accuracy will help resolve disputes.

## 5.5 Recommendation for Further Studies

It is recommended that, a study is conducted to establish the influence of risk factors on project investment and its link to project success.

# REFERENCES

Ahmed, A., Kayis, B., and Amornsawadwantana, S. (2007). A review of techniques for risk management in projects. Benchmarking: An International Journal, 14(1), pp. 22-36.

Management.28p. (Unpubl.).

Alavi, M., and Carlson, P. (1992). A review of MIS research and disciplinary development. Journal of Management Information Systems, Vol. 8, No.4, pp. 45- 62.

Alexander, N., (2015). Quantitative Risk Management: Concepts, Techniques, and Tools:

Appiah-Kusi, A. S. (2003). Risks and Crises Management in the Ghana Mining Industry: a case study. Kumasi: KNUST Series. Retrieved from http://ir.knust.edu.gh/handle

Aven, T. (2014). Risk, Surprises and Black Swans: Fundamental Ideas and Concepts in Risk

Babbie, E. (1990), Survey Research Methods, Wadsworth, Belmont, CA.

Badri, A., Nadeau, S. and Gbodossou, A., (2012). Proposal of a risk-factor-based analytical approach for integrating occupational health and safety into project risk evaluation. Accident Analysis & Prevention, 48, pp.223-234.

Barako, D. G., and Gatere, P. K. (2008). Outsourcing Practices of the Kenyan Banking Sector (SSRN Scholarly Paper No. ID 1534158). Rochester, NY: Social Science Research Network. Retrieved from http://papers.ssrn.com/abstract=1534158

Bijl, M.G.H, and Hamann, R.J. (2002). Risk Management Literature Survey: An overview of Approach, Procedia - Social and Behavioral Sciences 119, pp. 653-662. Assessment and Risk

Bland, J.M. and Altman, D.G., (1997). Statistics notes: Cronbach's alpha. Bmj, 314(7080), p.572.

Browning, T.R., Eppinger, S.D., Deyst Jr, J.J. and Whitney, D.E., (2000, July). 7.4. 4 Complex System Product Development: Adding Value by creating Information and reducing risk. In INCOSE International Symposium (Vol. 10, No. 1, pp. 548-556).

Broyd, T. (2001). Constructing the future, Foresight: making the future work for you. London:

Bryman A. and Bell, E. (2015) “Business Research Methods” 4th edition, Oxford University Press.

Bryman, A., Bresnen, M., Beardsworth, A. and Keil, T., 1988. Qualitative research and the study of leadership. Human relations, 41(1), pp.13-29.

Bryman, A., 2008. Social Research Methods., (Oxford University Press: Oxford, UK.).

Burns N., and Grove, S., (1987). The practice of nursing research; conduct, critique and utilization, W. B. Saunders Company.

Cervone, H. F. (2006). Project Risk Management, OCLC. Systems and Services: International

Cervone, H.F., (2006). Project risk management. OCLC Systems and Services: International digital library perspectives, 22(4), pp.256-262.

Collis, J., and Hussey, R. (2013). Business research: A practical guide for undergraduate and postgraduate students. Palgrave MacMillan.	Concepts, Techniques, and Tools, Princeton University Press, 2010.

Conrad-Mulherin, J. W. (2012). An analysis of base and precious metal project finance risks in sub-Saharan Africa: Perspectives on political, commercial, technical and legal risks from an international bank. University College London School of Energy and Resources,. University College London School of Energy and Resources, Australia.

Conrad-Mulherin, J.W., (2012). An analysis of base and precious metal project finance risks in sub-Saharan Africa: Perspectives on political, commercial, technical and legal risks

Cooper, D. and Schindler, P. 2003. 8 ed. Business research methods. Boston: McGraw-Hill, USA.

Creswell, J. W. (2003). Research Design: Qualitative, Quantitative and Mixed Methods Approaches, 2nd edition, London: SAGE Publications.

Cretu, O., Steward, R., and Berends, T. ( 2011). Risk Management for Design and Construction. New Jersey: John and Wiley and Sons, Inc.

Dainty, A. R.  (2007). A call for methodology pluralism in Built Environment research. In Proceedings of 3rd Scottish Conference for Postgraduate Researchers in the Built and Natural Environment (PRoBE), 20-22 November (pp. 1–10). Glasgow: Glasgow Caledonian University.

Davison, R.M. and Martinsons M.G. (2011) Methodological Practice and Policy for Organisationally and Socially Relevant IS Research: An Inclusive-Exclusive Perspective, Journal of Information Technology, Vol. 26, No. 4, pp. 288-293.

Denzin, N.K. and Lincoln, Y.S., 2008. The landscape of qualitative research (Vol. 1). Sage.

Descombe, M., 2003. The good research guides. For Small-scale Research Projects.

Douglas , H. W. (2009). The Failure of Risk Management: Why It's Broken and How to Fix It. John Wiley and Sons.

Easterby‐Smith, M., Lyles, M. A., and Tsang, E. W. (2008). Inter‐organizational knowledge transfer: Current themes and future prospects. Journal of management studies, Vol. 45, No. 4, pp. 677-690.

El-Sayegh (2010). Risk Management in Construction Projects: A Knowledge-base. European Space Research and Technology Centre (2000). Space Project Management: Risk Assessment, standard ECSS-M-00-03A. 56p.

El-Sayegh, S.M. and Mansour, M.H., (2015). Risk assessment and allocation in highway construction projects in the UAE. Journal of Management in Engineering, 31(6), p.04015004.

Enshassi, A., Mohamed, S. and Abu Mosa, J., (2008). Risk management in building projects in Palestine: Contractors’ perspective. Risk management in building projects in Palestine: Contractors’ perspective, 13(1).

Fellows, R. and Liu, A., (2003). Research methods for construction, Blackwell Science

Flanagan, R. (1993). Risk Managment and Construction . Oxford: Blackwell Science Ltd.

Fouzi, H., (2012).  Analyze and manage the risks faced by construction projects, Faculty of 	Engineering, University of Omar Mukhtar, Libya.

from an international bank. University College London School of Energy and

Galliers, R. (1991). Choosing appropriate information systems research approaches A revised taxonomy. R. Galliers, ed. Information Systems Research: Issues, Methods, and Practical Guidelines. Blackwell, Oxford, U.K., 144–162.

Gay, L. R. (1992). Educational research: Competencies for analysis and application (4th Ed). New York: Macmillan Publishing Company.

Gomez-Conde, J. (2015). Examining the Link between Outsourcing and Performance: The Leverage Effect of the Interactive Use of Management Accounting and Control Systems (SSRN Scholarly Paper No. ID 2595279). Rochester, NY: Social Science Research Network. Retrieved from http://papers.ssrn.com/abstract=2595279

Gray, D. E. (2004). Doing Research in the Real World. London: SAGE Publications.

Gunhan, A., (2015). Risk Management Principles and Governance, looming the modus. digital library perspectives, 22(4), pp. 256-262.

Hair, J. F., Black, W. C., Babin, B. J., and Anderson, R. E. (2010). Multivariate data analysis (7th ed.). Pearson Prentice Hall.

Hall, D.C. (2002). What is “Risk"? Risk Management Working Group INCOSE. Online from www.citeseerx.ist.psu.edu/ 12p.

Haneef, S., Riaz, T., Ramzan, M., Rana, M.A., Hafiz, M.I. and Karim, Y., (2012). Impact of risk management on non-performing loans and profitability of banking sector of Pakistan. International Journal of Business and Social Science, 3(7).

Hart, C. (2003). Doing a Literature Review. London: SAGE Publications Ltd.

Heba, E., (2014). Risk Management Practices and Financial Performance in Jordan, Business Administration, Economics and Political Science, The British University in Egypt, Cairo, Egypt.

Herroelen, W., (2014). A risk integrated methodology for project planning under uncertainty. In Essays in Production, Project Planning and Scheduling (pp. 203-217). Springer, Boston, MA.

Hirschheim, R. (1985). Information systems epistemology: An historical perspective. Research methods in information systems, Vol. 9, No. 3, pp. 13- 35.

Hoffman, S. L. (2007). The Law and Business of International Project Finance: A Resource for Governments, Sponsors, Lenders, Lawyers and Project Participants (3 ed.). New York: Cambridge University Press.

Holton, G. A. (2004). Defining Risk. Financial Analysts Journal 60(6). pp19-25.

Iqbal, S., Choudhry, R.M., Holschemacher, K., Ali, A. and Tamošaitienė, J., (2015). Risk management in construction projects. Technological and Economic Development of Economy, 21(1), pp.65-78.

Kombo, D. K. and Tromp, D. L. A. (2006). Proposal and Thesis Writing: An Introduction. 	Pauline’s Publications‟ Africa, Nairobi.

Kothari, C. R. (2004). Research methodology. Methods and techniques (second revised 	edition), New Delhi, New Age International Publisher

Lester, A. (2007). Project management, planning and control : managing engineering, construction and manufacturing projects to PMI, APM and BSI standards (5 ed.). Amsterdam ; Boston: Elsevier/Butterworth-Heinemann.

Lindner, J. R., Murphy, T. H., and Briers, G. E. (2001). Handling nonresponse in social science research. Journal of Agricultural Education, 42(4), 43-53. Management, 3 (5).

MacKenzie, R., Forde, C., Robinson, A., Cook, H., Eriksson, B., Larsson, P. and Bergman, A., (2010). Contingent work in the UK and Sweden: evidence from the construction industry. Industrial Relations Journal, 41(6), pp.603-621.

Mason, A. L., Lau, J. Y., Hoang, N., Qian, K., Alexander, G. J., Xu, L. and Everhart, J. E. (1999). Association of diabetes mellitus and chronic hepatitis C virus infection. Hepatology, Vol. 29, No. 2, pp. 328 – 333.

Miller, G. J., and Yang, K. (Eds.). (2008). Handbook of research methods in public administration (2nd ed.). Boca Raton: CRC Press.

Mok, K. Y., Shen, G. Q. and Yang, J. 2015. Stakeholder management studies in mega construction projects: A review and future directions. International Journal of Project Management, Vol.33, No.2; pp.446-457. operandi among construction contractors in Malaysia, International Journal of Construction

Orodho A. J. (2004). Technologies of writing Research proposals and report in Education and 	Social Science, Masola publishers, Reata Prince.S. Nairobi

Pennock, M.J and Haimes, Y.Y., (2002). Principles and guidelines for project risk 	management. Systems Engineering, 5(2). pp89-108. Virginia.

Polit, DT, Beck, C.T. and Hungler, B.P. (2001). Essentials of nursing research - Methods, appraisal, and utilization. 5th edition. Philadelphia: Lippincott.

Project Management Institute (2004). A Guide to the Project Management Body of Knowledge, 	3rd Edition. Project Management Institute, Four Campus Boulevard, Newtown Square, 	Pennsylvania USA. 405p.

Punch, K. (2003). Survey research: The basics. California: Sage Publications.

Remenyi, D., and Williams, B. (2003). Doing research in business and management: an introduction to process and method. Sage.

Renuka, S. M., Umarani, C., Kamal, S. (2004). “A Review on Critical Risk Factors in the Life 	Cycle of Construction Projects”. Journal of Civil Engineering Research, 4(2A): pp. 31-	36, Resources, Australia, 95p (Unpubl.).

Saunders, M., Lewis, P. and Thornhill, A. (2009) Research methods for business students, 5th ed., Harlow, Pearson Education.

Shenila, M., (2010). Project Management Risk Sensitivity Analysis, Journal of Information and 	Communication Technology,4 (1), pp 38-48.

Simonsen, H., and Perry, J. (1999). Risk Identification, Assessment and Management in the Mining and Metallurgical Industries. The Journal of the South African Institute of Mining and Metallurgy, 99.

Suad, A., (2009). Risk Management Mediates the Influence of Good Corporate Governance, 	Managerial Shareholder, and Leverage on Firm Value, IOSR Journal of Business and Management 18 (11), pp. 62-70.

Snape, D. and Spencer, L., 2003. Qualitative research practice: A guide for social science students and researchers.

Tang, W., Qiang, M., Duffield, C., Young, D., and Lu, Y. (2007). 2007. Risk Management in the Chinese Construction Industry. Journal of Construction Engineering and Management, ASCE, 12, 944-956

Tchankova, L. (2002). Risk identification – basic stage in risk management. Environmental 	Management and Health, 13(3), pp. 290-297.

the process, tools used and their outcomes. 82p. Delft University of Technology,

Thurairajah, N., Haigh, R., and Amaratunga, R. D. (2006). Leadership in Construction Partnering Projects: Research Methodological Perspectives (pp. 35–48). Research Institute for Built and Human Environment: University of Salford M7 1NU.

Van Scoy, R.L., (1992). Software Development Risk: Opportunity Not Problem. Technical Report CMU/SEI-92-TR-030. Carnegie Mellon University. Pittsburgh, Pennsylvania. 	22p.

Wilkinson, D., and Birmingham, P. (2003). Using research instruments: A guide for researchers. Psychology Press.

Wood, G., and Haber, J., (1998). Nursing research; methods, critical appraisal and utilization, 4th ed., Mosby-Year Book.

Yellman, T.W. (2000). Three Facets of Risk. SAE Technical Paper 2000-01-5594. World 	Aviation Conference. 16p.(unpubl.).

Yin, R. 2009. Case study research: Design and methods. Thousand Oaks, CA: Sage 	Publications

# APPENDIX - SURVEY QUESTIONNAIRE

KWAME NKRUMAH UNIVERSITY OF SCIENCE AND TECHNOLOGY

COLLEGE OF ART AND BUILT ENVIRONMENT

DEPARTMENT OF BUILDING TECHNOLOGY

SURVEY QUESTIONNAIRE

“EFFECTIVE MANAGEMENT OF RISK FACTORS ASSOCIATED WITH PUBLIC INVESTMENT PROJECTS IN GHANA”

Dear Sir/ Madam,

I am an MSc. student at Kwame Nkrumah University of Science and Technology, Department of Building Technology currently undertaking an “Effective Management of Risk Factors Associated with Public Investment Projects in Ghana.”

The research is ongoing under the supervision of Prof. Theophilus Adjei-Kumi and requires a questionnaire survey to be undertaken to collect data from professionals in public investment projects in Ghana. Your experience and knowledge in the area of the research is essential and much appreciated. Information on the identification of risk factors that typically affect public investments projects in Ghana, the severity of the identified risks on infrastructural projects and risk mitigation techniques that are being practiced in the Ghanaian construction industry will be obtained from the research. The information you shall provide shall be STRICTLY CONFIDENTIAL and for academic purposes only and findings from this research will be made available to you on request.

I know you have a very busy schedule and this will take some time off you, I will plead that you help me with your knowledge as it means so much to the achievement of this research. I appreciate your effort and time very much in advance, kindly contact me on 0243187941 if you have any questions or clarification.

Sincerely yours,

Eric Larbie Marmah, MSc. Student, KNUST

Dr. Theophilus Adjei-Kumi, Project Supervisor, KNUST

Section A: Background Information

1. Please what is your role in your organization?

[      ] Project Manager

[      ] Architect

[      ] Project Team Member

[      ] Project Consultant

[      ] Site Engineer

Others (please specify) ………………………………………..

2. Please what is your educational level?

[       ] Higher National Diploma (HND)

[       ] Bachelor Degree

[       ] MBA/MSc/MPhil

[       ] PhD

Other (please specify) ………………………………………..….…

3. Please indicate your level of experience in the industry

[       ] Less than 5 years

[       ] 6 to 10 years

[       ] 11 to 15 years

[       ] Above 16 years

SECTION B: RISK FACTOR

Below is the table which contains the risk factors, please indicate by ranking the risk factors in order of low risk, medium risk and high risk.

1= low risk;              2= medium risk       3= high risk

|  | Risk category | Factors | Level of influence |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | 1 | 2 | 3 |
| RF1 | Legal | Legal disputes during the construction phase among the partners |  |  |  |
|  |  | Delayed disputes resolutions |  |  |  |
| RF28 |  | No specialized arbitrators to help settle fast |  |  |  |
| RF29 | Construction | Rush bidding |  |  |  |
| RF30 |  | Gaps between the Implementation and the specifications due to a misunderstanding of drawings and |  |  |  |
| RF31 |  | Undocumented change orders |  |  |  |
| RF32 |  | Lower quality of work. |  |  |  |
| RF33 |  | Changes in design |  |  |  |
| RF34 |  | The difference in actual and contract executed quantities |  |  |  |
| RF35 | Political | Change of government |  |  |  |
| RF36 |  | Change of government policy |  |  |  |
| RF37 |  | New governmental acts or legislation |  |  |  |
| RF38 | Management | Ambiguous planning due to project complexity |  |  |  |
| RF39 |  | Resource management |  |  |  |
| RF40 |  | Changes in management ways |  |  |  |
| RF41 |  | Information unavailability (include uncertainty) |  |  |  |
| RF42 |  | Poor communication between parties involved |  |  |  |

SECTION C: RISK MITIGATION TECHNIQUES

In the table shown below, please determine the relative use of each preventive method by ticking (√) the appropriate box for each item in the table:

|  |  | Never | Rarely | Sometime | Often | Always |
| --- | --- | --- | --- | --- | --- | --- |
|  | Preventive Method | 1 | 2 | 3 | 4 | 5 |
| RM1 | Utilize quantitative risk analyses techniques for accurate time | ☐ | ☐ | ☐ | ☐ | ☐ |
| RM2 | Depend on subjective judgment to produce a proper program. | ☐ | ☐ | ☐ | ☐ | ☐ |
| RM3 | Produce a proper schedule by getting updated project information | ☐ | ☐ | ☐ | ☐ | ☐ |
| RM4 | Plan alternative methods as stand-by. | ☐ | ☐ | ☐ | ☐ | ☐ |
| RM5 | Consciously adjust for bias risk premium to time estimation | ☐ | ☐ | ☐ | ☐ | ☐ |
| RM6 | Transfer or share risk to/with other parties | ☐ | ☐ | ☐ | ☐ | ☐ |
|  | Refer to previous and ongoing similar projects for accurate | ☐ | ☐ | ☐ | ☐ | ☐ |