KWAME NKRUMAH UNIVERSITY OF SCIENCE AND TECHNOLOGY, KUMASI,

GHANA

A COMPARATIVE ANALYSIS OF PROJECT MANAGEMENT DELIVERY IN THE FINANCIAL SECTOR: THE ROLE OF STAKEHOLDERS

By

ROSE KALU

(BA Information Studies)

A Thesis submitted to the Department of Construction Technology and Management, in partial fulfillment of the requirement for the award of

Master of Science Degree in Project Management.

MASTER OF SCIENCE

NOVEMBER, 2018

DECLARATION

I hereby declare that this submission is my own work towards the MSc. Project Management and that to the best of my knowledge, it contains no material previously published by another person nor material which has been accepted for the award of any other degree of the university or any other university, except where due acknowledgement has been made in the text.

ROSE KALU (PG8915717)

Student

............................................

Signature

.............................................

Date

Certified by

DR. BARBARA SIMONS

Supervisor

...........................................

Signature

............................................

Date

Certified by

PROFESSOR B. K. BAIDEN

Department of Construction and Technology

...................................................

Signature

...................................................

Date

ABSTRACT

The objective of this study is to examine the role stakeholders play in the delivery of financial products and service packages. To achieve this objective, the study focused on identifying the stakeholders of the financial services industry, and they included employees and management, customers and clients, competing financial institutions, regulatory agencies, contractors and consultants, civil society groups and community leadership, and the general public. The study also focused on establishing the roles performed by the various constituents towards the development and delivery of financial products and services.  Another area explored was the critical success factors for effective management of stakeholders within the financial services industry. Lastly, challenges inherent in the management of stakeholders towards project delivery were examined. The study targeted employees within five (5) financial institutions in the Sunyani Municipality of the Brong Ahafo region of Ghana, and comprised 50 employees. A structured survey was used to collect data from respondents and information gathered on their views was analyzed and the results attained revealed that regulatory agencies, customers and clients, and employees and management were considered to be the most important stakeholder groups. The study also established the need to appreciate certain factors that are critical for the successful management of stakeholder. It further exposed the challenges inherent in managing stakeholders, with respondents agreeing that unplanned changes in project scope and design as well as poor stakeholder representation in decision making were the major challenges faced in product and service design and delivery. The study concluded with recommendations for improving stakeholder engagement practices and suggestions for future studies in the study area.

TABLE OF CONTENT

DECLARATION.................................................................................................................i

ABSTRACT.......................................................................................................................ii

TABLE OF CONTENT....................................................................................................iii

LIST OF TABLES............................................................................................................vi

LIST OF FIGURES..........................................................................................................vii

ACKNOWLEDGEMENT..............................................................................................viii

DEDICATION..................................................................................................................ix

CHAPTER 1: INTRODUCTION.......................................................................................1

  - Background of the Study............................................................................1

  - Problem Statement......................................................................................3

  - Aim of the Study........................................................................................4

  - Research Questions....................................................................................4

  - Objectives of the Study..............................................................................4

  - Research Methodology...............................................................................5

  - Significance of the Study............................................................................5

  - Scope of the Study......................................................................................6

  - Limitations of the Study.............................................................................7

  - Organization of the Study...........................................................................7

CHAPTER 2: LITERATURE REVIEW............................................................................9

2.1	Introduction................................................................................................9

2.2	The Concept “Project”................................................................................9

2.3	Product and Service Packages as Projects................................................11

2.4	Conceptual Review of Stakeholder..........................................................12

2.5	Stakeholder Categorization......................................................................15

2.6	Project Stakeholder Management.............................................................17

2.7	Stakeholders in the Financial Services Industry: Roles, Interest, and

Influences.................................................................................................18

2.8	Stakeholder Management Processes.........................................................22

2.9	Critical Success Factors for Effective Stakeholder..................................24

2.10	Challenges of Project Stakeholder Management......................................27

2.11	Benefits of Effective Stakeholder Management.......................................28

CHAPTER 3: RESEARCH METHODOLOGY..............................................................29

3.1	Introduction..............................................................................................29

3.2	Research Design.......................................................................................29

3.3	Research Strategy.....................................................................................29

3.4	Target Population.....................................................................................30

3.4.1 Study Area.......................................................................................30

3.4.2 Study Population.............................................................................30

3.4.3 Sampling Technique........................................................................31

3.5	Data Collection Instrument.......................................................................31

3.6	Validity of Research Instrument...............................................................32

3.7	Reliability of Research Instrument...........................................................32

3.8	Data Analysis............................................................................................32

3.9	Chapter Summary.....................................................................................33

CHAPTER 4: DATA ANALYSIS AND DISCUSSION OF FINDINGS.......................34

4.1	Introduction..............................................................................................34

4.2	Respondents’ Profile................................................................................34

4.2.1 Age of Respondents.........................................................................35

4.2.2 Gender of Respondents....................................................................35

4.2.3 Educational Qualification of Respondents......................................36

4.2.4 Number of Years in Current Employer Institution..........................37

4.2.5 Job Position of Respondents............................................................38

4.2.6 Level of Involvement in Product/Service Design and Delivery......39

4.3	Descriptive Results...................................................................................40

4.3.1 Identification of Stakeholders..........................................................40

4.3.2 Role of Stakeholders in the Financial Services Sector....................41

4.3.3 Critical Success Factors for Stakeholder Management...................45

4.3.4 Stakeholder Management Challenges.............................................47

4.4	Measurement Assessment........................................................................49

4.5	Discussions...............................................................................................49

4.6	Chapter Conclusion..................................................................................53

CHAPTER 5: SUMMARY OF FINDINGS, CONCLUSIONS AND RECOMMENDATIONS.................................................................................................54

5.1	Introduction..............................................................................................54

5.2	Summary of Findings...............................................................................54

5.3	Conclusion................................................................................................56

5.4	Recommendations....................................................................................56

5.5	Future Research Recommendations.........................................................56

REFERENCES.................................................................................................................58

APPENDICES..................................................................................................................67

Questionnaire........................................................................................................67

LIST OF TABLES

Table 2.1	Project Types and Characteristics............................................................11

Table 2.2	Stakeholders, their Roles and Responsibilities, Expectations and

Potential Impact........................................................................................20

Table 2.3	Critical Success Factors for Effective Stakeholder Management............25

Table 4.1	Age Distribution of Respondents.............................................................35

Table 4.2	Gender Distribution of Respondents........................................................36

Table 4.3	Respondents’ Number of Years in Current Jobs......................................38

Table 4.4	Respondents’ Level of Involvement in Product/Service Development...40

Table 4.5	Responses on Identification of Stakeholders............................................41

Table 4.6	Extent of the Role of Stakeholders in the Financial Sector......................42

Table 4.7	Extent of Critical Success Factors for Stakeholder Management............46

Table 4.8	Extent of Stakeholder Management Challenges.......................................48

LIST OF FIGURES

Figure 2.1	Stakeholder Model of the Firm.................................................................14

Figure 2.2	Stakeholder Mapping and Classification..................................................19

Figure 2.3	Stakeholder Management Processes.........................................................24

Figure 4.1	Educational Qualifications of Respondents..............................................37

Figure 4.2	Job Positions of Respondents...................................................................39

ACKNOWLEDGEMENT

My sincerest gratitude goes to God Almighty for granting me the wisdom and strength to complete this thesis and achieve the results herein. My heartfelt gratitude also goes to my supervisor, Dr. Barbara Simons for her immense patience, scholarly guidance and direction. Her prompt responses, unbiased criticisms, and valuable comments helped bring this work to a successful completion.

Again, I wish to thank the staff and management of the Sunyani branches of the following financial institutions; Bank of Ghana, GCB Bank Limited, Databank Ghana Limited, Legacy Capital Investment Limited, and Unique Insurance Limited, for availing themselves as respondents of this study and their prompt responses to the survey questions which facilitated the completion of this work.

Finally, special thanks go to my family and friends for their immense support and encouragement throughout the process of completing this work.

God richly bless you all.

DEDICATION

I dedicate this thesis to Almighty God, my family Janet and Richard Kalu, and dearest friend Ruthie Dzidzor Sewornoo, for their consistent support and encouragement. I also dedicate this work to Mr. Bismark Amponsah for his immense support and advice during the initial stages of my work. I could not have gotten this far without you.

My gratitude knows no bounds.

CHAPTER ONE

INTRODUCTION

1.1 Background of the Study

The financial services sector is experiencing rapid changes, trends and the emergence of innovative ideas, services, products and technological advancement (Alva, 2018). The increasing demands of customers for higher returns on their investments has given rise to aggressive competition in the financial services sector comprising of banks, savings and loans companies, microfinance institutions, finance houses, insurance companies among others (Bank of Ghana, 2017). This growing competition, both globally and on the local front, has led to a massive paradigm shift in the financial services sector from its original traditional function of merely providing savings avenues for customers, to the development and delivery of attractive products and service offerings (Indrajit, 2002). As noted by Tapestry Networks (2016), there has been a rapid shift in the financial services sector, especially banks, from their original functional orientation to a matrix organizational structure. In managing projects in the financial service sector, the principal interest of financial institutions lies in the successful delivery of project deliverables that are inextricably linked to and further the achievement of their organizational strategic objectives. These interests are generally maximization of profits and increase in market share (Vrecko et al., 2015).

Stakeholders play an integral role in the successful development and delivery of projects, services, and products, so much so that a comprehensive body of knowledge has been developed and packaged as “Project Stakeholder Management” to harness the benefits of managing stakeholders for the efficient and effective delivery of projects across all sectors (Association for Project Management, n.d.). The Project Management Institute [PMI] (2017) examines stakeholder management from three dimensions: identifying the people, groups or organizations that could impact or be impacted by a project; analyzing their expectations and potential impact on the project; and developing and implementing appropriate strategies for effectively engaging them towards the achievement of project goals. In this regard, PMI suggests that effective project stakeholder management cannot be achieved without following a series of coordinated steps and processes. Stakeholder management takes into account understanding the attitudes of stakeholders throughout a project’s lifecycle with the objective of executing strategies in consonant with the expectations of stakeholders (Beringer et al., 2013). It concentrates on uninterrupted communication with stakeholders to translate their anticipations and needs, manage their problems and conflicting interests, and deploy appropriate engagement strategies to meet project goals (PMI, 2017).

Roeder (2013) argues that any individual or entity that can impact or be impacted by the inputs, processes or outputs of a project, both negatively and positively is a stakeholder. Beringer et al. (2013) assert that stakeholders possess a double relationship with the performance of the project in the sense that their actions affect the project and the project results in turn affect their interests. For every project therefore, there exist different categories of stakeholders with diverse levels of interests, influences, needs, expectations, and roles and responsibilities, and these individuals are the driving-force behind successful completion and attainment of project goals (Nalewaik & Mills, 2015). Singh and Khan (2012) stressed on the importance of customers to businesses whilst other researchers (Chandler, 1967; Yener, 2002; Cooray, 2011) focused on different stakeholder groups.

Carrying out effective stakeholder management entails identifying the parties whose influence and interests are important in the project environment as well as understanding the indicators that encourage them to generate mutual benefits (Purvis et al., 2014). Proper management of stakeholders is a critical success factor for any project and while numerous studies (Liang et al., 2017; Tammer, 2009; Bourne, 2013) have sought to examine this phenomenon generally and in specific settings and sectors, this study seeks to focus on project management delivery in the context of the financial services sector.

1.2 Problem Statement

According to Bank of Ghana (2017), the financial sector contributes significantly to Ghana’s Gross Domestic Product and overall economic performance. Banks and other financial institutions in Ghana have been increasingly engaged in customer-oriented projects in their quest to capture more of the market share, improve their customer experience, and grow their productivity and profitability levels (Simons, 2016). To successfully attain this, there is the need to identify the various stakeholders groups including customers, industry competitors, employees, management, and external contractors, understand their roles and impact on project management delivery, and the challenges inherent in their management.

This intricate blend of stakeholders with possibly contradicting interests, needs, attitudes, perceptions, and backgrounds pose a major challenge in the efficiency and effectiveness of the overall project management efforts. While there is a vast collection of research works on project stakeholders and their management, it is skewed towards traditionally recognized project-oriented sectors like construction, education, health, NGO and social intervention initiatives, leaving a vacuum in the financial services sector.

This study therefore seeks to fill this gap by identify the various stakeholder groups in the financial services industry, exploring their roles, and examining the critical success factors of effective stakeholder management. It goes further to identify project stakeholder management challenges and suggest relevant solutions to these challenges.

1.3 Aim of the Study

The aim of this research is to examine stakeholders’ role in the project management delivery of financial service products and services in the financial services sector.

1.4 Research Questions

The study seeks to answer the following questions:

- What are the roles of the stakeholders of the financial services sector in the delivery of financial services and products?

- What are the success factors of stakeholder management in financial service delivery?

- What are the stakeholder management challenges inherent in the financial sector?

1.5 Objectives of the Study

The specific objectives of the study are:

- To examine the roles of the stakeholders in the delivery of projects in the financial services sector.

- To explore the critical success factors for effective stakeholder management in the financial sector.

- To identify stakeholder management challenges in the financial services sector.

1.6 Research Methodology

To achieve the objectives of this study, a combination of both primary and secondary sources will be explored. The target population of this study is financial service providers in Sunyani, five of which have been selected. Purposive sampling technique will be used to select personnel within these institutions who have been involved in at least one phase of the project management lifecycle of a newfangled service or product package. This non-probabilistic technique has been adopted to ensure that the research sample is relevant to the studies.

The study will also adopt the quantitative approach using survey design. The survey method is selected because of its ability to facilitate the collection of structured responses from a diverse group of respondents. The analysis of data collected will be based on quantitative methodology, specifically the application of statistical analysis including mean (composite) scoring and standard deviation. The data collected will be modified to remove mistakes, coded, and entered into SPSS for analysis.

1.7 Significance of the Study

For the successful delivery of any product, project or service, it is critical to understand the needs and wants of the target users of the deliverables, how the project outcomes will influence them, and how the stakeholders can contribute to an effective and efficient development process. Regarding the extant literature in the field of stakeholder management, the outcome of this study will serve as a useful literature for other researchers who want to conduct similar studies.

For the financial service sector, this thesis will provide a better understanding and appreciation of the role of stakeholders in their product and services development and delivery processes. It will also expose the challenges inherent in stakeholder management as encountered by financial service providers. Furthermore, the findings of this study will contribute to research efforts in stakeholder management, bringing to light the peculiarities in the financial services sector. While stakeholder management has been explored in recent studies, focus has been biased towards traditional projects sectors like construction (Yang et al., 2009a), health services (Semali, 2003), Non-Profit initiatives, and social interventions (Ayatah, 2012). Very limited studies have been undertaken in this regard in the financial services sector and therefore, this study will serve as a reference material for further research efforts in stakeholder management. Ultimately, this study will contribute to the body of knowledge in project management.

1.8 Scope of the Study

This thesis covers five (5) selected financial service providers in the Sunyani Municipality, Ghana. While it has been severally recognized that other project management processes are key for successful project delivery, this study is limited to stakeholders and their role in successful project delivery in the financial sector in Sunyani Municipality. Within the selected institutions, data collection efforts will be directed at members of staff and management who have had direct involvement in at least one phase of a project in the delivery of a newfangled service or product package. Stakeholder management concepts to be discussed are processes, interests, influences, and power.

1.9 Limitations of the Study

This study on the role of stakeholders and stakeholder management in the delivery of projects is limited to financial services and product packages. It is also skewed towards customer-oriented projects like Internet banking, Stored Value Facilities, Fast and Secure Transfer (FAST) facilities among others, rather than a holistic examination of all genres of projects undertaken in the financial services sector of which there is a vast majority. The study also covers personnel of five (5) financial institutions in Sunyani, representing a single stakeholder group in the industry.

1.10 Organization of the Study

The study is organized into the five chapters. The first chapter outlines the background to the study, problem statement, research questions, research objectives, a brief overview of research methods, scope of study, and the significance of study.

Chapter Two (2) is a review of literature on previously undertaken research on stakeholder management. The chapter takes into consideration the contextual review, stakeholder interest, influence and power, stakeholder management processes, successful project delivery, theoretical and empirical literature review, and conceptual framework as well as hypothesis.

Chapter Three (3) contains the research methodology and design used in undertaking the study, including the data collection and sampling method as well as the sample population, while Chapter Four (4) elaborates on the data analysis and presentation of the findings in the form of tables, charts, and summary details for easy understanding.

The concluding chapter, Chapter Five (5) discusses the conclusions of the findings of the study, its contributions to the body of knowledge, recommendations proposed, limitations, as well as suggestions for the direction of future research in the area.

CHAPTER TWO

LITERATURE REVIEW

2.1 Introduction

In this chapter, a review of existing literature on the role of stakeholders in the delivery of projects will be provided. To begin, this chapter will explore historical antecedents and current issues in project stakeholder management. Another focus of this review will be on the theoretical and conceptual frameworks and hypothesis surrounding stakeholder management, stakeholder categorization, and success factors for effective stakeholder management. Major concepts and theories of this study as well as the context within which these concepts will be used throughout this work will be defined and established. This chapter will also provide an analysis of who a Stakeholder is, the Categories of Stakeholders, Stakeholders in the Financial Services Sector, their roles and influence, the challenges encountered in their management, and the benefits to be derived from their effective management. This chapter will conclude with a summary of empirical studies undertaken on Project Stakeholder Management and capture key issues in stakeholder management for successful project delivery.

2.2 The Concept “Project”

Long before the establishment of an organized body of knowledge, principles, manuals or guides, there existed organized efforts, both simple and complex, directed towards the achievement of tangible endeavors (Seymour & Hussein, 2014). The Great Wall of China, Pyramids of Giza and Coliseum are some great examples of successful projects undertaken in the past. Projects have therefore been in a way of life for as long as human existence on earth. Over time however, the definition has grown and evolved alongside humans and organizations. PMI defines a project as “a temporary endeavor undertaken to create a unique product, service or result” (PMI, 2017, p. 2). While brief and simple, this definition encompasses a wide variety of initiatives, both tangible and intangible, and although the concept has become common so much so that it has been adopted in everyday parlance to refer to a vast collection of tasks and ventures, its integral meaning remains unchanged.

Over the years, there has been a significant paradigm shift in the adoption of project management practices and its widespread application in traditionally functional organizations as organizations are increasingly organizing their activities as projects (Albrecht & Spang, 2014). This has led to an evolution in the definition of the concept, “Project”. For the purpose of this study, the explanation provided by Kerzner (2009) in his book ‘Project Management: A System Approach to Planning, Scheduling and Controlling’, has been adopted. Rather than define it, Kerzner sought to establish the characteristics of a project as “series of activities and tasks that have a specific objective, with a focus on the creation of business value, to be completed within certain specifications; have defined start and end dates; have funding limits (if applicable); consume human and nonhuman resources (ie. money, people, equipment); and are multifunctional (ie. cuts across several functional lines)” (Kerzner, 2009, p.2).

While each project is inherently unique, either as a result of the complexity, size, target consumers, stakeholders or industry, several key characteristics cut across all of them, each of which has been captured by Kerzner. Moreover, the key processes inherent in the design and delivery of products and services across all sectors and business organizations fit the above definition.

2.3. Product and Service Packages as Projects

In order to establish products and services as project, it is prudent to understand the features and characteristics of these two concepts and how they fit into the broad spectrum and categorization of projects as posited by numerous authors and project management experts.  This makes for easier acceptability under the broad categorization of projects.

According to Youker (2017), projects can be grouped under ten categories, based on their deliverables. As shown in Table 2.1 below, he sought to establish taxonomy of the different types of projects based on the degree of uncertainty, level of worker sophistication, level of detail in planning, degree of innovation employed and finally, the degree of time constraints.

Table 2.1: Project Types and Characteristics (adapted from Youker, 2017).

|  | Type of Project | Type of Worker | Degree of Uncertainty | Time Pressure | Stability of Scope | Level of Innovation | Importance of Cost |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Administrative | White | Low | Low | High | Low | Low |
| 2 | Construction | Blue | Low | Low | High | Low | High |
| 3 | Software | High Tech | High | Medium | Low | High | Low |
| 4 | Design | White | Medium | Medium | Medium | High | Medium |
| 5 | Maintenance | Blue | High | High | Low | Low | Low |
| 6 | Event | White | Low | Medium | High | Medium | Medium |
| 7 | Equipment | Blue | Low | Low | High | Low | Low |
| 8 | New Product | White | High | High | Low | High | Low |
| 9 | Research | High Tech | High | Low | Low | High | Low |
|  | Others? |  |  |  |  |  |  |

Claessens (2015) sees products as tangible or intangible goods that can be offered to a group of consumers to satisfy their needs and wants. He went further to distinguish between products and services and described the latter as a subset of a product, intangible in nature, and made up of benefits, activities, or satisfaction which when purchased will not result in the ownership of anything.

2.4 Conceptual Review of Stakeholder

Stakeholder approach as a management strategy began in the mid-1980s. A notable figure in this movement was Richard Edward Freeman. He viewed stakeholder approach from the perspective of the organization and is generally credited with the concept of strategic management later re-conceptualized as Stakeholder Approach in 1984 (Freeman, 1999). Stakeholder approach was intended to widen the vision, responsibilities and roles of management beyond maximizing benefits (Mitchell et al., 1997). The history of stakeholder management approach also emanated from earlier works put forth by the Stanford Research Institute (SRI) in the 1960s, particularly in 1963, within which it asserted that stakeholders are groups or individuals whose support are integral to the survival of an organization and without which an organization cannot function.

The definition espoused by the Stanford Institute was criticized on the basis that it limited stakeholders to individuals and groups who have only economic interests in an organization. Clarkson (1994) sought to define stakeholders through the lenses of risk ownership. Distinguishing them as voluntary and involuntary, he posited that voluntary stakeholders bear some level of risk due to their intentional human and capital investment in the organization while individuals exposed to certain risks via the organization’s processes, activities, and outputs are the involuntary stakeholders. His theory revolved around the notion that there is no “stake” without an element of risk. Implicitly, involuntary stakeholder-ship infers that stakeholders need not always be real but can sometimes be potential. With this reasoning, a stakeholder can influence, be influenced, or perceive themselves likely to influence or be influenced by an organization, and vice versa (Clarkson, 1994). Freeman (1984) held the same view, describing stakeholders as people with the potential to affect or be affected by an organization’s actions towards achieving its strategic goals.

In seeking to establish who the key players of a project are for effective coordination of engagement efforts, Mitchell et al. (1997) conceptualized stakeholders with the word “legitimacy”. He argued that stakeholders have some level of legitimate power and relationship that cannot be trivialized; and that such relationships are seen as exchanging transactions, impacting actions, and possessing moral responsibilities.

Dodd (1932) asserts that there are four main groups of an organization’s stakeholders - shareholders, employees, customers, and the general public. In 1947, the company Johnson and Johnson outlined their stakeholders to include their employees, managers, customers, and shareholders. In a similar fashion, several other companies announced diverse categories of individuals and groups as their stakeholders (Preston & Sapienza, 1990). Donaldson and Preston (1995) posit that stakeholders consist of all groups or persons with legitimate interests not conflicting with others interest who take part in an enterprise to obtain benefits. In this regard, the argument of stakeholder theory takes into account external constituencies that include environmental groups, communities, governmental bodies, potential employees, community groups, trade unions, trade, associations, partner institutions, potential customers and the general public (Donaldson & Preston, 1995).

Freeman (1984) sought to present a more comprehensive categorization of stakeholder groups that cut across all sectors and industries, and Figure 2.1 below is a graphical representation of his categorization. Within most sectors and industries, internal stakeholders comprise of employees and owners while external stakeholders are made up of customers, Special Interest Groups (SIGs), competitors, consumer advocates, government, and suppliers among others.

Suppliers

Local community organizations

Government

Owners

Consumer advocates

Firm or organization

Environmentalists

Customers

SIG

Competitors

Media

Employees

Figure 2.1: Stakeholder Model of the Firm: Adopted from Freeman, (1984)

Both narrow and broad definitions have been ascribed to the relationships between stakeholders and firms. Some definitions of stakeholder are narrow in the sense that stakeholders are seen as those who participate in exchange relationships (Hill & Jones, 1992). The fact that all profit-oriented companies have limited time and resources which are spent on numerous activities is given due consideration in these observations. Proper identification and granting due attention to stakeholders is therefore key for management in their quest to achieve the company’s strategic and financial objectives. Upchurch (1998) also argues that stakeholders are people who have informal moral claims and relationships towards an organization.

While there is no universally accepted definition, the description of a stakeholder by Bourne and Walker (2005) which encompasses all individuals and groups with interests, rights or shares in a project, who concurrently possess the ability to contribute to a project as well as be affected by the project’s deliverables, fit the context within which this concept will be used throughout this work.

2.5 Stakeholder Categorization

Stakeholders can be characterized as either claimants or influencers (Savage et al., 1991). Savage et al. (1991) further explored the propensity and likelihood of both actual and potential stakeholders to either support or oppose an organization in the achievement of its goals. Freeman (1984) also classified stakeholders as “internal” and “external”. He espoused that in a typical business organization, internal stakeholders are customers, shareholders, employees and management while external stakeholders include contractors and suppliers, the media, community activists, advocacy groups, regulatory bodies and government agencies, and the community at large. Another classification of stakeholders as posited by Clarkson (1995) is “primary” and “secondary”. Secondary stakeholders have no direct relations with the organization in that these stakeholders have limited legitimate hold or formal contractual relationship over the organization (Eesley & Lenox, 2006). On the other hand, primary stakeholders like customers and employees have direct relations with the firm because they engage in direct business transactions and have direct legal authority over the firm.

Clarkson (1995) and Savage et al. (1991) argue that though secondary stakeholders do not involve themselves directly, they nonetheless affect an organization. Langtry (1994) contends that secondary stakeholders possess legitimate and moral claims in that the organization is significantly responsible for their well-being. Freeman (1984) classified stakeholders as “moral” and “strategic”, arguing that strategic stakeholders affect the firm and taking due consideration in the managing their needs, expectations, and concerns is key to the survival of the institution.  On the other hand, moral stakeholders are viewed to be those who provide resources for, depend on the firm, and bear the brunt of the firm operations and outputs, both positive and negative (Frooman, 1999).

Fassin (2009) criticizes previous stakeholder categorizations, arguing that there must be a clear distinction between stake keepers, stake watchers and stakeholders. He respectively defines stakeholders as people having concrete and actual stake in an organization, stake watchers as community pressure groups and organized unions who have no real stake but rather protect the interests of real stakeholders, and finally stake keepers as the independent regulators such as regulatory agencies, certification organizations and government agencies having no stake in the firm but rather possessing control and influence. A widely used categorization sees stakeholder groupings on the basis of their contractual ties to the project, magnitude of involvement, and status on the project (Nalewaik & Mills, 2015).

2.6 Project Stakeholder Management

A project stakeholder is an organization or individual whose anticipations, needs, position or influence can negatively or positively impact or be impacted by how project activities are carried out and the deliverables attained at project completion (PMI, 2017). Project stakeholders possess diverse and conflicting interests, influences, needs, expectations, roles, and responsibilities. These contradictory positions especially on key project issues may result in severe obstructions and affect overall project success. An organization must therefore identify and appreciate its stakeholder mix, manage their interests and demands, and promote proactive communication to successfully attain project deliverables (PMI, 2017). Donaldson and Preston (1995) contends that stakeholder management and project performance have a positive correlation. Freeman et al. (2007) also posit that from a sustainability and ethical perspective, stakeholders must not be disengaged from the project because their interests affect the outcome of the project and vice versa.

Specifically, due attention must be directed at identifying relevant stakeholders of the project in order to meet their respective needs for the survival of the organization (Baron, 2009). Evaluating stakeholder’s demands and influence must also be treated as crucial in the planning, execution and closing of projects (Olander & Landin, 2005). To reduce uncertainty, stakeholder analysis should be carried out by the project management team to give the project organization insight into the project environment (Aaltonen, 2011). A widely held view on stakeholder management is that the value realized from stakeholders and their relationship with the project team ultimately determines the success or failure of a project. In light of this, effective management of stakeholder relationships is crucial for the production of expected values that match both the needs and expectations of stakeholders on one side, and the strategic goals and objectives of the organization on the other side (Bourne & Walker, 2005).

2.7 Stakeholders in the Financial Services Industry: Roles, Interests and Influences

Okoli et al. (2016) opined that the financial services sector has various categories of stakeholder groups who willfully or inadvertently contribute to the survival of the industry. Each group has distinctive interests that may conflict with each other, the project deliverables, and even the strategic objectives of the institution. Bryson (2004) argues that the creation and sustenance of these institutions result from the satisfaction of the needs and wants of their clients, who constitute their key stakeholder group. Figure 2.2 adapted from the Millenium Bank’s (n.d.) Stakeholder Mapping captures the key stakeholder groups that financial institutions engage with in their delivery of products and services.

Figure 2.2: Stakeholder Mapping and Classification. (Millennium Bank, n.d.)

Each of these stakeholder groups influences the project at least once during the project lifecycle. The product and service development team must therefore have the capacity to manage the contradictions inherent in these interactions as and when they present themselves (Yang et al., 2009b).  Karlsen (2008) sought to distinguish between the various stakeholder groups, identifying their roles, interests and potential impact on project deliverables. In his article “8 Project Stakeholders You Should Never Ignore Before Project Launch”, Brian (2017) elaborates on the vested interests stakeholders have in the end products of projects and how their early involvement in the management processes ensures they derive satisfaction from project deliverables, which ultimately determines the success of the project.

Table 2.2 below gives an overview of stakeholders in the financial services industry, exploring their roles and responsibilities, expectations, and potential impacts and is adapted from works of Karlsen (2008) and Brian (2017) as applicable to the financial service sector. Karlsen (2008) explored stakeholder relationships in engineering projects while Brian (2017) focused on eight groups of stakeholders to consider in undertaking any project.

Table 2.2 Stakeholders, their roles and responsibilities, expectations and potential impact

| Stakeholder Group | Roles and Responsibilities | Expectations/Potential Impact |
| --- | --- | --- |
| Customers and Clients | The requirements and specifications of a financial service or product package should be derived from the needs of customers. | Customers expect products and services to generate benefits for them including a value-added experience, higher returns on investments, lower service charges, or reduction in waiting and processing times. Client patronage of new a product defines its successful delivery. |
| Employees and Management | Employees and management are at the forefront of the product and service development process. Their understanding, acceptance and contribution to the project determine project success. Front desk, marketing and sales, and customer service personnel are critical to the successful delivery and patronage of developed products and services. Management is also responsible for decision making and ensures that projects are geared towards the institution’s strategic objectives. | Financial service products like internet banking, insurance packages, and investment packages are sold through employees. Their disintegration from the development processes will therefore be detrimental to the delivery and patronage of these packages. Employees expect that while new products generate returns for the institution as a whole, and customers, they will not be left out and will ultimately benefit through an improvement in their job operations |

Table 2.2 Continued

| Stakeholder Group | Roles and Responsibilities | Expectations/Potential Impact |
| --- | --- | --- |
| Competitors | Industry-wide competition can serve as a catalyst and benchmark for adopting best practices. Innovative ideas are developed in the quest to surpass achievements of competitors and can lead to the creation of exceptional products and services. | Competitors can be viewed as threats depending on the proprietary nature of the product under development. At the same time, competitors can positively impact and increase the benefits to be derived from a product or service via collaboration. A recent example is the collaboration of mobile network service providers and banking institutions in Ghana for the Mobile Money Interoperability System. |
| Regulatory Agencies | The role of regulators including the Bank of Ghana and the Securities and Exchange Commission is to provide guidelines and codes of conduct for players in the industry as well as supervise their operations to ensure adherence to legal requirements, ethical standards, and best practices. Per the Banks and Specialized Deposit-Taking Institutions Act 2017 (Act 930) for instance, financial institutions require the express permission of the Bank of Ghana to roll out new products or service packages. | Industry regulators expect financial institutions to comply with regulations. They also expect new products to lead to improvements in customer experience rather than the opposite. The impact from these agencies can be either positive or negative, where the negative manifests in fines, suspensions, and in some cases withdrawals of licenses and operational permits. |
| Contractors, Suppliers, and Consultants | Consultants and contractors possess the technical expertise to bring project specifications into realization. They include accounting and finance experts, project management professionals, IT systems analysts and designers among others. Suppliers also provide the needed inputs required in for the development of financial products and service packages. | They expect to receive clear expectations and requirements for the project. In cases where they are involved in the development of the product scope, they require clear, consistent, and timely flow of data from the contributing stakeholders of the project |
| Civil Society | Civil Society Groups in general serve as | In closely-knitted communities, the |

Table 2.2 Continued

| Stakeholder Group | Roles and Responsibilities | Expectations/Potential Impact |
| --- | --- | --- |
| Groups and Community Leadership | watch dogs and ensure that the processes and deliverables of a project are not delivered at the detriment of the people. Their involvement in the development process of products or services with elements of controversy can aid smoothing out of conflicts and public acceptance of such products. It will also ensure transparency, accountability, and instilment of public trust. | influence of opinion leaders and Civil Society Groups is substantial and having them onboard a project as supporters must be a part of the stakeholder engagement strategies. |

Adopted from Karlsen (2008) and Brian (2017)

2.8 Stakeholder Management Processes

Managing project stakeholders comprises of all the processes required to identify the groups, people or organizations that can impact or be impacted by the project, scrutinize their needs and anticipations that could serve as key project inputs, formulate effective management strategies, and engage them towards the successful development and delivery of results (PMI, 2017). The PMBOK (2017) outlines stakeholder management processes as follows:

Identify Stakeholders

The first step in stakeholder management is stakeholder identification, which involves recognizing the groups, people or organizations that can influence or be influenced by the inputs, activities, decisions or outcomes of a project. It entails substantiating and scrutinizing stakeholder information taking into consideration their actual and perceived influences, interests, participation and potential impact on project success. Stakeholder identification aids the project manager in identifying the needed efforts for each stakeholder group.

Plan Stakeholder Management

This includes the process of designing effective and efficient stakeholder management strategies to engage meaningfully with stakeholders throughout the project lifecycle. This planning is based on the initial identification and analysis of stakeholder dispositions, drivers and their real and potential impact on project success. This process provides a precise and deployable plan to interact with project stakeholders and maintain their interests and commitments to the project and its deliverables.

Manage Stakeholder Engagement

Engaging stakeholders involves targeted engagement activities for the respective stakeholder groups, which is carried out throughout the project lifecycle. During this process, the project manager requires the necessary support to curtail opposition from non-supportive stakeholders in order to increase the chances of project success.

Control Stakeholder Engagement

Controlling stakeholder engagement helps in maintaining the efficiency and effectiveness of stakeholder engagement activities as the project progresses. It also includes performing an assessment of the effectiveness of current engagement strategies and making necessary changes when it is detected that some strategies are ineffective.

Figure 2.3 as shown below is a graphical depiction of the various processes of project stakeholder management and while it appears to be cyclical in nature, it is iterative and continuous throughout a project’s lifecycle.

Identify Stakeholders

Plan Stakeholder Management

Manage Stakeholder Engagement

Control Stakeholder Engagement

Figure 2.3: Stakeholder Management Processes: Adopted from PMBOK, (2017).

2.9 Critical Success Factors for Effective Stakeholder Management

Managing stakeholders effectively is a critical factor for project success. Yang et al. (2009a) and Fummey (2016) outline some essential factors of effective stakeholder management. These factors are areas within which the attainment of satisfactory results will enable the successful delivery of project goals. The successful development and delivery of the target products and services is intricately tied to the attainment of these factors, and Yang et al. (2009a) describes these critical success factors as issues that need addressing and strategies that should be implemented to achieve project results. A questionnaire survey undertaken by Yang et al. (2009a) sought to identify the essentials of effective stakeholder management. The topmost fifteen (15) factors as proposed by respondents were as follows:

Table 2.3: Critical Success Factors for Effective Stakeholder Management

| Critical Success Factor | Arguments and their Proponents |
| --- | --- |
| Undertaking social responsibilities | In sync with the theory of Corporate Social Responsibility, Carroll (1979) argues that a firm owes it to its stakeholders to meet their needs for goods and services at reasonable prices, and that in the achievement of this, legal and ethical considerations should be given due cognizance. Donaldson and Preston (1995) argue that organizations should appreciate the diversity of their stakeholder groups, which should feed into the development of products and services. |
| Defining project missions | In “Why Good Projects Fail Anyway”, Matta and Ashkenas (2003) explored why more than 50% of big project fail, summarizing the reasons as gaps in planning, poor implementation, and inadequate project integration management, all of which can be managed with an elaborate project management plan. A clear definition of project goals is central to all project management activities, including the management of stakeholders. A clear understanding of what is required of a project aids the formulation of effective stakeholder engagement strategies (Winch, 2000). |
| Assessing stakeholders’ behavior | Stakeholder analysis grants a purview into the power, interests and attitudes of stakeholders towards the project. This aids in the mapping of strategies for their management. Common dimensions used in the assessment of stakeholder behavior include power, support, interest, and influence. Aaltonen et al (2008) identified eight behavioral traits, each of which requires complementary management strategies. Freeman (1984) grouped stakeholder behavior into three categories; namely observed behavior, cooperative potential, and competitive threat. |
| Identifying stakeholders | The root cause of a significant portion of failed projects can be traced back to poor stakeholder identification. Failure to identify key stakeholder groups leads to stakeholder marginalization, and ultimately the development of unwanted |

(Yang et al, 2009a)

Table 2.3 Continued

| Critical Success Factor | Arguments and their Proponents |
| --- | --- |
|  | products and services. Several researchers (Olander, 2006; Frooman, 1999; Walker et al, 2008) have emphasized the importance of identifying stakeholders in their works. |
| Predicting the influence of stakeholders | Some stakeholders wield a high level of influence on projects. Understanding their behaviors, attitudes and interest on projects outcomes helps with the determination of the probable impact of their actions. Olander’s (2007) Stakeholder Impact Matrix summarizes the potential impact of different stakeholder on the basis of their influence, interest, and attitude towards the project. |
| Assessing attributes of stakeholders | Mitchell et al (1997) posit that stakeholders assessment should be based on three key features including power, legitimacy, and urgency. Power is the degree to which one can exert influence over others. A stakeholder whose demand for prompt attention is prioritized over others is said to have more urgency. In the same vein, an individual or organization whose actions are deemed to conform to socially acceptable standards and practices is said to be legitimate. Assessing project stakeholders on the basis of these attributes create a better stakeholder management environment. |
| Understanding the area of stakeholders’ interest | Stakeholders hold diverse interests in the outcomes and deliverables of a project (Freeman et al., 2007). Their expectations vary as a result of their differing worldviews and backgrounds, and there is the need to have in-depth understanding of these issues. |
| Exploring challenges faced by stakeholders and their needs on projects | A thorough identification of the needs of stakeholders on a project creates understanding on their unique problems and challenges. It is the first step towards developing sustainable solutions (Olander & Landin, 2008). |
| Analyzing conflicts and coalitions among stakeholders | Common interests lead to the formation of coalitions while differing views lead to conflicts. Understanding this phenomenon is crucial for successful project stakeholder management as potential escalations can be terminated at their roots while coalitions can be harnessed (Schermerhorn et al., 2003). |
| Compromising conflicts | Conflict resolution among stakeholders is a key responsibility for project managers. Antony et al. (2002) argues that the relation between stakeholder satisfaction and effective conflict resolution techniques is linear. |

Table 2.3 Continued

| Critical Success Factor | Arguments and their Proponents |
| --- | --- |
| Analyzing the change of stakeholders | Over time, the respective influences, positions and interests of stakeholders evolve, making it a strategic issue to be given due consideration. This shift may result from external environmental factors beyond the control of stakeholders, including changing economic conditions, political changes, and technological advancement among others. These changes must be analyzed and managed proactively to mitigate the negative impact and harness opportunities and benefits it may present (Ward & Chapman, 2008). |
| Ensuring effective communication | Regular, planned and effective communication with all project stakeholders is vital for project success (Cleland, 1995). Project managers must possess good communication and bargaining skills in order to adequately handle stakeholder needs and form a positive culture within the project environment (Weaver, 2007). |
| Promoting a good relationship | Hartman (2002) has suggested that the nature of relationships existing between stakeholders and the project are critical for the successful project completion which inadvertently feeds into the fulfillment of stakeholders’ expectation. Bourne (2005) also opined that trust and commitment among stakeholders can be developed through an effective relationship management system. |
| Formulating appropriate strategies | The formation of appropriate stakeholder management and engagement strategies including strategies for communication, conflict resolution, and reward and recognition systems among others is of key significance for the successful delivery of project outputs (Freeman et al., 2007; Schwager, 2004). |
| Predicting stakeholder reactions | Cleland and Ireland (2002) argue that prior to implementation the project team should be able to predict the responses and reactions of stakeholders to proposed engagement strategies. |

2.10 Challenges of Project Stakeholder Management

The activity of managing stakeholders in and of itself is a challenging endeavor as the convergence of an organization’s strategic objectives with the needs and expectations of their diverse stakeholder groups creates bottlenecks on the path to project delivery. Karlsen (2002) posits that challenges and problems develop due to the dynamic nature of human interactions and communications. These challenges result from ill-defined or conflicting project responsibilities and authority levels, unplanned changes in project scope and specifications, poor stakeholder representation in decision-making, inability of stakeholders to comprehend their respective roles, and unclear needs of the end user. Kastner (2010) asserts that challenges of stakeholder management come from three sources: unclear stakeholders – those who do not clearly articulate their needs or are not open and honest about their interests and expectations; unidentified stakeholders – those who were not identified early in the project; and unreasonable stakeholders – those who do not embrace reason.

2.11 Benefits of Effective Stakeholder Management

Studies conducted by Hillman and Keim (2001) sought to establish the link between effective stakeholder management, stakeholder participation and shareholder value. They surmised that building effective management of key stakeholders like customers, employees, suppliers and the community as a whole could result in competitive advantage for the organization. This advantage is derived from the successful development and delivery of valuable products that generate both social and economic value for the organization. In the same vein, the legitimacy of an organization, its sole reason for existence, is highly reliant on its ability to effectively meet the expectations of its stakeholders. An active relationship with stakeholders aids proactive risk management as issues and problems are detected early and escalated before they develop into full-blown threats. Stakeholder-oriented businesses also enjoy the benefit of innovation and are found to be at the forefront of developing market trends in their industries.

CHAPTER THREE

RESEARCH METHODOLOGY

3.1 Introduction

The chapter focuses on the research methodology and design adopted for this work. It details the research methods, design and approach, study population, sample and sampling technique adopted, sample size, data collection method and data analysis employed, as well as the presentation of findings, all of which are targeted at answering the questions raised in the first chapter.

  - Research Design

According to Trochim (2005), research design acts as the foundational support for all aspects of a research work and is concerned with how the various sections of a study addresses research questions raised and overall research goals. The research design adopted for this study is the quantitative approach, implemented via a structured questionnaire survey targeted at five financial institutions in Sunyani Municipality. The study designed close-ended questions to correctly sieve out answers needed for analysis and interpretation. Data was collected from primary sources and the instrument used for the study was structured questionnaire. Analysis was done using SPSS followed by quantitative interpretations of these findings.

3.3 Research Strategy

Survey design was adopted for this study. According to Orodho (2009), survey helps in collecting data from individuals of a population to ascertain the recent status of the population in relation to the variables under consideration. The adoption of the questionnaire survey was a good strategy for this scholarship because it enabled the researcher to obtain information that explained the current situation in the financial services sector.

3.4 Target Population

Population, according to Mugenda and Mugenda (2003), is the total number of individuals or items having similar characteristics and considered under a field of inquiry, from which inferences can be drawn. For the purposes of this study, the target population was financial institutions in the Brong Ahafo region of Ghana.

3.4.1 Study Area

Sunyani Municipality was chosen for this study because it harbors the majority of financial institutions in Brong Ahafo Region. Also, unlike other cities in Brong Ahafo, it has a cross-sectional representation of all the key players of the financial services industry including savings and loans companies, investment banks, deposit-money banks, insurance companies, and microfinance institutions. The regulator of the financial services sector, Bank of Ghana, also has a regional office in Sunyani.

3.4.2 Study Population

Ruben and Babbie (1989) define study population as the sum of all elements from which the sample is actually selected. The study population for this research consisted of all employees in the numerous financial institutions in Sunyani Municipality. The target population for this study is 500.

3.4.3 Sampling Technique

The study employed convenient sampling to filter information from respondents based on two reasons. Firstly, the easy identification and selection of individuals or groups competent and well-versed in the phenomenon of interest (Cresswell et al., 2011). Secondly, the willingness and availability to participate, and the ability to communicate experiences and opinions in an expressive, reflective, and articulate manner was used as a selection criteria (Bernard, 2002; Spradley, 1979).

The study was carried out with a sample size of fifty (50) respondents and a 5% error margin was employed to ensure 95% confidence level. This was done via the use of convenience sampling.

3.5 Data Collection Instrument

This study made use of both secondary and primary data sources to improve the reliability and validity of results. Secondary data was collected from previous studies undertaken in related subject areas. Primary data was collected via the use of a structured questionnaire survey administered to employees in the selected financial institutions. The use of a structured questionnaire also ensured consistency in the responses of respondents.

The questionnaire was structured in five parts, A to E. Section A collected general information on respondents while sections B to E respectively collected responses on identifying stakeholders in the financial services sector, their roles, the critical success factors in managing stakeholders, and the challenges inherent in this management process.

3.6 Validity of Research Instrument

Five (5) respondents were used as a pre-sample to test the validity of the questionnaire, and the metrics included clear understanding, difficulty in questions, and respondents’ willingness to respond to questions (Ghauri & Gronhaug, 2005; Orodho, 2012). Pre-testing made the questionnaire language clearer, tested accuracy, and sustainability of instrument. Pre-tested respondents were randomly selected from the targeted population. Also, copies of the draft questionnaire were given to two (2) project management experts in a financial institution in Sunyani to cross-check whether the questions outlined were valid for the study subject. Their corrections together with those from the pre-test were incorporated into the final questionnaire.

3.7 Reliability of Research Instrument

Best and Kahn (1998) define reliability as the quality of consistency that an instrument demonstrates over time. The use of a structured questionnaire enhanced the reliability of results generated as it brought with it uniformity of questions both in the language construction and the number of questions, enabling respondents to be measured in a consistent manner.

3.8 Data Analysis

Data analysis was undertaken for this study using quantitative methodologies. First, data collected using structured questionnaires. Collected data was then entered into the Statistical Package for Social Sciences (SPSS) software and the results were organized in mean scores and standard deviation. For all the dimensions under measurement, a scale of 1 to 4 was used, and results were represented in tables and graphs.

3.9 Chapter Summary

This chapter described the procedures by which data required for the study was collected. Specifically, it covered the research methods, approach, strategy, population, sample and sampling techniques, and research instruments, data collection procedure, instrument validity and reliability.

CHAPTER FOUR

DATA ANALYSIS AND DISCUSSION OF FINDINGS

4.1 Introduction

This chapter presents the study’s results and the discussions of the findings of this study which sought to explore the role of stakeholders in the delivery of project in the financial services sector. The key sections of this chapter includes: respondents’ profile, descriptive results, measurement assessment, discussions, and chapter conclusion. The analysis was carried out via the use of Statistical Package for Social Sciences (SPSS). Of the fifty six (56) questionnaires distributed to respondents, a total of fifty (50), representing 89.29% were retrieved. Upon review, all 50 retrieved questionnaires were considered viable to be included for data analysis towards the study’s objectives.

4.2 Respondents’ Profile

The administered questionnaires sought to answer the questions raised at the beginning of this work in chapter 1, with the goal of gaining insight into who the stakeholders of the financial services sector are, what roles they play in the delivery of financial services and products, what the success factors in their management are, and what challenges are inherent in their management. As a result of the skewedness of the research towards the financial sector’s stakeholders, respondents of the survey questionnaire where purposively selected from within five (5) financial institutions in Sunyani; Bank of Ghana, GCB Bank Limited, Databank Ghana Limited, Legacy Capital Investment Limited, and Unique Insurance Limited.

This section further elaborates on the characteristics of the respondents including their age, gender, education qualification, number of years spent with their current employer institution, job position, and level of involvement in product and service design and delivery.

4.2.1 Age of Respondents

As shown in Table 4.1, majority of the respondents had ages between 0 to 29 years (46.0%, n=50), followed by those in the 30 to 39 years bracket represented by 34% (34.0%, n=50). Those in the age brackets of 40 to 49 years and 50 years and above each represented 10% of the total respondents as shown in the table below.

Table 4.1 Age Distribution of Respondents

| Category | Count | Percentage |
| --- | --- | --- |
| Below 29 years 30 – 39 years 40 – 49 years 50 years and above | 23 17 5 5 | 46.0 34.0 10.0 10.0 |
| Total | 50 | 100.00 |

Source Data: Field Survey, August 2018

4.2.2 Gender of Respondents

Majority of the respondents were male, representing 54% (54.0%, n=50) of the sampled population as compared to 46% females (46.00%, n=50).  Below in Table 4.2 is a tabular representation of this phenomenon.

Table 4.2 Gender Distribution of Respondents

| Category | Count | Percentage |
| --- | --- | --- |
| Males Females | 27 23 | 54.0 46.0 |
| Total | 50 | 100.00 |

Source Data: Field Survey, August 2018

4.2.3 Educational Qualification of Respondents

Regarding their educational background, majority of respondents indicated that they held a bachelor degree representing 50% of the total figure (50.0%, n=50). This was followed by 22% who held masters’ degrees (22.0%, n=50). SSCE/WASSCE/O’ Level certificate holders were in the minority represented by 14%, while Professional Certificate holders saw an even smaller figure of 10%. Finally, two (2) of the fifty (50) respondents indicated that they held other qualification, representing 4%. Figure 4.1 below clearly depicts this distribution.

Figure 4.1 Educational Qualifications of Respondents. Source Data: Field Survey, August 2018

4.2.4 Number of Years in Current Employer Institution

The data analysis revealed that a vast majority of respondents were fairly new recruits, having served in their respective institutions for a period between 1 and 3 years. This group accounted for 52% of the total respondents. This was followed by 16% each of respondents with less than 1 year and between 4 and 9 years of working experience with their current employer. Finally, 4% of respondents comprising of 2 people indicated that they had served for between 10 and 15 years on the job while 12% had served for more than 15 years. Table 4.3 below shows the distribution for this phenomenon.

Table 4.3 Respondent’s Number of Years in Current Jobs

| Number of Years in Current Job | Count | Percentage |
| --- | --- | --- |
| Less than one year Between 1 – 3 years Between 4 – 9 years Between 10 – 15 years More than 15 years | 8 26 8 2 6 | 16.0 52.0 16.0 4.0 12.0 |
| Total | 50 | 100.00 |

Source Data: Field Survey, August 2018

4.2.5 Job Positions of Respondents

It was found out that of the 50 respondents, directors, project managers/officers, communication and IT personnel, and other personnel represented 4%. The majority of positions held by respondents were in the areas of Front desk and customer service, sales and marketing, and programmes management, each of which capped 26% of respondents. Finally, 6% of respondents held administrative positions. Figure 4.2 below gives in-depth insight into the distribution of respondents’ positions within the five selected financial institutions.

Figure 4.2 Job Positions of Respondents. Source Data: Field Survey, August 2018

4.2.6 Level of Involvement in Product/Service Design and Delivery

Regarding involvement of respondents in service and product package development and delivery, 36% reported that they were highly involved in their institution’s project management processes (36.0%, n=50). This was followed closely by 28% each of respondents who indicated that they were moderately involved and slightly involved in these processes. Those with the least involvement, representing little to no involvement, constituted 8% of respondents (8.0%, n=50). Table 4.4 below clear depicts the distribution for this phenomenon.

Table 4.4 Respondent’s Level of Involvement in Product/Service Development

| Level of Involvement | Count | Percentage |
| --- | --- | --- |
| Low involvement Slightly involved Moderately involved Highly involved | 4 14 14 18 | 8.0 28.0 28.0 36.0 |
| Total | 50 | 100.00 |

Source Data: Field Survey, August 2018

4.3 Descriptive Results

This section further presents descriptive results on the study’s constructs. The constructs are identification of stakeholders, roles of stakeholders, critical success factors for stakeholder management and stakeholder management challenges. A 4-point scale that ranged from strongly disagree (=1) to strongly agree (=4) was used to measure all items.

4.3.1 Identification of Stakeholders

Seven (7) items were used to measure stakeholder identification and these items were adopted from the PMBOK (2017). The descriptive results on these items and their composite (average) scores are shown in Table 4.5 below. Of the 7 items analyzed, the lowest mean score was 2.71 (standard deviation = .562) and the highest means score was 3.74 (standard deviation = .957). The overall mean score was 3.37 (standard deviation = 1.439). Given the scale of 1 to 4, these results suggest that the majority of respondents agree with the various stakeholders groups identified in the financial sector for the delivery of product and services. This implies that respondents, who simultaneously serve as key stakeholders within the financial services industry to a large extent, agree to and understand that several other stakeholder groups affect and are affected by their inputs, processes, and outputs towards financial products and services delivery. These revelations are in consonant with Roeder (2013) who asserted that all persons who affect or are affected by an organization’s activities fall within their stakeholder body.

Table 4.5 Response on Identification of Stakeholders

| Item code | Item statement | Mean | Std Dev | Min | Max |
| --- | --- | --- | --- | --- | --- |
| IS1 | Customers and clients | 3.74 | 0.564 | 1 | 4 |
| IS2 | Employees and management | 3.64 | 0.562 | 2 | 4 |
| IS3 | Competitors – other financial institutions | 2.71 | 0.957 | 1 | 4 |
| IS4 | Regulatory agencies – Bank of Ghana, Securities and Exchange Commission | 4.04 | 5.820 | 1 | 4 |
| IS5 | Contractors, suppliers and consultants | 3.14 | 0.714 | 2 | 4 |
| IS6 | Civil society groups and community leadership | 3.02 | 0.713 | 1 | 4 |
| IS7 | The general public | 3.32 | 0.746 | 1 | 4 |
|  | Composite (average) score | 3.37 | 1.439 | 1.28 | 4.00 |

Source Data: Field survey (August, 2018)

4.3.2 Role of Stakeholders in the Financial Services Sector

Eighteen (18) items were adopted from Karlsen (2008) to measure the roles of the various stakeholder groups. To make the results easily interpretable, the scores obtained from respondents were recoded to reflect each of the seven (7) stakeholder classes. Respectively, the study rephrased the dimensions of various stakeholders as customers and clients; employees and management; competitors (other financial institutions); regulatory and supervisory agencies; contractors, suppliers, and consultants; civil society groups and community leadership; and the general public. The descriptive statistics of these items and their overall average scores are shown in Table 4.6.

Across the seven dimensions measured on a scale of 1 to 4, an average participant scored 3.75 (standard deviation = 1.853), 4.58 (standard deviation = 2.108), 3.22 (standard deviation = 2.051), 3.18 (standard deviation = 0.814), 3.23 (standard deviation = 0.676), 3.38 (standard deviation = 0.783) and 3.2 (standard deviation = 0.925). The mean and the standard deviation scores were obtained for all the seven dimensions respectively. Overall, the composite average score and standard deviation were 3.35 and 1.470 respectively.

Table 4.6 Extent of the Role of Stakeholders in the Financial Sector

| Item code | Item statement | Mean | Std Dev | Min | Max |
| --- | --- | --- | --- | --- | --- |
| CC1 | The needs of our customers dictate the requirements and specification of product and service packages. | 3.6 | 0.638 | 1 | 4 |
| CC2 | The successful design and delivery of our new products and services is defined by customers’ level of patronage of the finished product. | 3.48 | 0.677 | 1 | 4 |
| CC3 | Successful new product development requires in-depth understanding of our customers’ needs and wants | 4.18 | 4.245 | 2 | 4 |
| EM1 | Employees and management are the forefront of the product or service development process | 2.92 | 0.986 | 1 | 4 |
| EM2 | Employees and management contribute to new service and product ideas and help determine ways to implement them to get favourable customer responses. | 4.06 | 6.028 | 1 | 4 |
| EM3 | My institution’s top management support and commitment affect the success of our new services and product development programmes. | 3.4 | 0.670 | 2 | 4 |
| EM4 | Senior management work towards ensuring that project meet the strategic objectives of the institution | 3.36 | 0.749 | 1 | 4 |
| CPT1 | My institution relies on industry-wide innovation and information from competitors in the development of new product and | 3.16 | 0.817 | 1 | 4 |

Table 4.6 Continued

| Item code | Item statement | Mean | Std Dev | Min | Max |
| --- | --- | --- | --- | --- | --- |
|  | services |  |  |  |  |
| CPT2 | Some of our products and services require collaboration and support from competitors | 2.76 | 1.021 | 1 | 4 |
| CPT3 | In assessing the quality of our products and services, we use industry standards (ie. what is being done by our competitors) as a benchmark | 3.76 | 4.316 | 1 | 4 |
| RSA1 | My institution requires express approval from our regulators before new products/services are developed | 3.16 | 0.817 | 1 | 4 |
| RSA2 | My institution strives to comply with regulations and codes of ethics provided by supervisory agencies | 3.54 | 0.613 | 2 | 4 |
| RSA3 | My institution is required to furnish our regulators with detailed information on the features of new product and services prior to introduction into the market. | 3.06 | 0.890 | 1 | 4 |
| RSA4 | Disapproval and sanctions from regulators negatively affects our product performance | 2.98 | 0.936 | 1 | 4 |
| CSC1 | Our suppliers, contractors and consultants provide the needed inputs required for product and service development | 3.23 | 0.728 | 1 | 4 |
| CSC2 | Our suppliers, contractors and consultants provide us with the technical expertise required to bring our ideas into fruition | 3.24 | 0.624 | 2 | 4 |
| CGCL1 | Civil Society Groups and Community Leadership interests’ lies in ensuring that our products and services are not detrimental to the welfare of customers | 3.28 | 0.783 | 1 | 4 |
| GP1 | Significant negative reactions from the general public in the form of demonstrations, protests, and civil unrest will cause us to withdraw offending products and services from the market | 3.2 | 0.925 | 1 | 4 |
|  | Composite (average) score | 3.35 | 1.470 | 1.2 | 4.00 |

Source Data: Field survey (August, 2018)

Given the scale used to measure the items, these results suggest that respondents recognize the significance of the roles of stakeholders as well as the responsibilities they hold in the design and delivery of products and services in the financial service sector. Generally, findings support assertions by Nawelaik and Mills (2015) that each stakeholder group have varied roles to play, as well as have a diverse range of needs and requirements, interests, influences, and expectations towards any organization and its outputs.  The responses from survey participants further corroborates assertions made by Beringer et al. (2013) in which they posit that stakeholders possess a “double relationship” with project performance as their actions affect the project and they are in turn affected by the project outputs, in this case, financial products and services.

More specifically, the results from survey respondents reveal that customers are viewed to be the most important stakeholder group in the financial services sector. Majority of respondents agree that the successful development of a product requires in-depth understanding of customer, represented by a mean score of 4.18. This is followed closely by employees and management whose contributory role in product design and delivery processes garnered an average score of 4.06. The extent of the role played by competitors in terms of collaborative efforts towards design and delivery of new products and services saw the lowest mean score of 2.76. This perception among respondents could be due to the fierce competition in the financial services industry, coupled with the need to safe guard proprietary information and technologies, copyright and licensure issues, among others.

4.3.3 Critical Success factors for Stakeholder Management

Thirty-two (32) items were adopted from Yang et al. (2009a) and Fummey (2016) to measure the critical success factors for stakeholders’ management. To make the interpretation easier, the scores obtained were recoded to reflect each critical success factor for stakeholder management. More so, the study outlined the dimensions of critical success factors for stakeholders management as undertaking social responsibilities, defining project missions, analyzing stakeholder behavior, identifying stakeholders, predicting the influence of stakeholders, assessing attributes of stakeholders, understanding the area of stakeholders interest, exploring stakeholders need and constraints in project, analyzing conflicts and coalitions among stakeholders, resolving conflicts among stakeholders, analyzing the change of stakeholders, ensuring effective communication, formulating appropriate and effective strategies, and predicting stakeholders reactions to engagement initiatives. The descriptive statistics of the items and their overall average score are shown in Table 4.7.

Across the 14 dimensions, an average participant scored 3.95 (standard deviation = 3.174). 3.92 (standard deviation = 3.535), 3.33 (standard deviation = 0.640), 3.41 (standard deviation = 0.682), 3.23 (standard deviation = 0.354), 3.57 (standard deviation = 2.11) and 3.27 (standard deviation = 0.659), 3.88 (standard deviation = 4.318), 3.73 (standard deviation = 3.246),  3.40 (standard deviation = 0.608),  3.09 (standard deviation = 0.795),  3.90 (standard deviation = 2.263),  3.39 (standard deviation = 0.622), and  3.27 (standard deviation = 0.673).  These mean and standard deviation scores were obtained on all fourteen dimensions used to measure critical success factors for stakeholder management respectively, as listed in table 4.7. Overall, the composite average score and standard deviation were 3.54 and 1.779 respectively. Given the scale of 1 to 4 used to measure the items, these results suggest that these factors are the areas within which the attainment of satisfactory results will enable the successful delivery of project goals. The successful development and delivery of target products and services is therefore intricately tied to the attainment of these factors.

Table 4.7 Extent of Critical Success factors for Stakeholder Management

| Item code | Item statement | Mean | Std Dev | Min | Max |
| --- | --- | --- | --- | --- | --- |
| USR1 | Meeting customer needs at reasonable prices | 4.38 | 5.805 | 2 | 4 |
| USR2 | Due consideration for legal and ethical issues in product development | 3.53 | 0.543 | 2 | 4 |
| DPM1 | Clear definition of goals before commencement of product development | 4.16 | 4.244 | 2 | 4 |
| DPM2 | Elaborate project management planning | 3.24 | 0.560 | 2 | 4 |
| DPM3 | Clear understanding of project needs and requirement | 4.36 | 5.801 | 3 | 4 |
| ASB1 | Observing and assessing the behaviour of stakeholders | 3.3 | 0.646 | 1 | 4 |
| ASB2 | Categorizing stakeholder based on their support, interest and influence | 3.36 | 0.635 | 1 | 4 |
| ID1 | Identifying all stakeholders of the project prior to the commencement | 3.34 | 0.751 | 1 | 4 |
| ID2 | Ensuring no stakeholder group is marginalized | 3.48 | 0.614 | 1 | 4 |
| PIS1 | Assessing the actual and potential impact of stakeholders action | 3.32 | 0.712 | 1 | 4 |
| PIS2 | Predicting the potential influence of key stakeholder groups | 3.14 | 0.707 | 1 | 4 |
| AAS1 | Stakeholders influence is well evaluated | 3.10 | 0.691 | 1 | 4 |
| AAS2 | Demands of stakeholders are met | 4.34 | 4.989 | 2 | 4 |
| AAS3 | Rules and regulation from stakeholders are recognized | 3.27 | 0.676 | 1 | 4 |
| USI1 | Understanding the expectations stakeholders have for the project outcomes | 3.28 | 0.676 | 1 | 4 |
| USI2 | Understanding how or why the product/service is of interest to them | 3.27 | 0.643 | 2 | 4 |
| ESN1 | Meeting the needs of stakeholders contributing to product development | 3.91 | 4.336 | 1 | 4 |
| ESN2 | Addressing the challenges faced by stakeholders during development | 3.85 | 4.301 | 1 | 4 |

Table 4.7 Continued

| Item code | Item statement | Mean | Std Dev | Min | Max |
| --- | --- | --- | --- | --- | --- |
| ACC1 | Managing stakeholders conflicts to mitigate their effects on the project | 4.10 | 5.853 | 1 | 4 |
| ACC2 | Managing stakeholder partnerships to exploit the opportunities they present for the project | 3.36 | 0.640 | 1 | 4 |
| RCS1 | Project managers resolve conflict amicably | 3.45 | 0.581 | 2 | 4 |
| RCS2 | Stakeholders are satisfied with conflict resolution techniques | 3.36 | 0.635 | 2 | 4 |
| ACS1 | Stakeholders interest, influence, and positions change over time | 3.08 | 0.794 | 1 | 4 |
| ACS2 | There is the need to proactively manage these changes | 3.10 | 0.796 | 1 | 4 |
| EEC1 | Project manager and team need good communication skills | 3.59 | 0.553 | 1 | 4 |
| EEC2 | Stakeholders are involved in all communication process | 4.59 | 5.957 | 1 | 4 |
| EEC3 | Positive culture is formed within the project environment through constant communication and engagement | 3.53 | 0.581 | 2 | 4 |
| FAES1 | Good strategies for communicating project information to stakeholders | 3.48 | 0.581 | 2 | 4 |
| FAES2 | Good strategies for conflict resolution among stakeholders | 3.34 | 0.560 | 2 | 4 |
| FAES3 | Good strategies for reward and recognition of stakeholders | 3.36 | 0.727 | 2 | 4 |
| PSAE1 | Early detection of stakeholders responses and reactions | 3.26 | 0.670 | 2 | 4 |
| PSAE2 | Reactions of stakeholders are predicted and proactively managed | 3.28 | 0.677 | 2 | 4 |
|  | Composite (average) score | 3.54 | 1.779 | 1.5 | 4.00 |

Source Data: Field Survey, August 2018.

4.3.4 Stakeholder Management Challenges

Eight (8) items were used to measure stakeholder challenges and these items were adopted from Karlsen (2002). The descriptive results on the items and their composite (average) scores are shown in Table 4.8 below. Of the 8 items, the lowest mean score was 2.82 (standard deviation = .868) and the highest means score was 3.1 (standard deviation = .944). The overall mean score was 2.95 (standard deviation = 0.898). Given the scale of 1 to 4, these results, suggest that the activity of managing stakeholders in and of itself is a challenging endeavor as the convergence of an organization’s strategic objectives with the needs and expectations of their diverse stakeholder groups creates bottlenecks on the path to project delivery (Kastner, 2010). However, various stakeholder management challenges are handled well in various financial institutions regarding delivering their services and products.

Table 4.8 Extent of stakeholder Management Challenges

| Item code | Item statement | Mean | Std Dev | Min | Max |
| --- | --- | --- | --- | --- | --- |
| SMC1 | Poor stakeholder representation in project decision making | 3.1 | 0.952 | 1 | 4 |
| SMC2 | Inability of stakeholders to understand their respective roles | 2.82 | 0.774 | 1 | 4 |
| SMC3 | Unclear definition of interest and expectations of stakeholders | 2.94 | 0.890 | 1 | 4 |
| SMC4 | Unidentified stakeholders at the early stages of the project | 2.96 | 0.924 | 1 | 4 |
| SMC5 | Conservative stakeholders | 2.86 | 0.926 | 1 | 4 |
| SMC6 | Ill-defined or conflicting project responsibilities | 2.98 | 0.868 | 1 | 4 |
| SMC7 | Undefined and conflicting project authority levels | 2.9 | 0.909 | 1 | 4 |
| SMC8 | Unplanned changes in project scope, design and specification | 3.08 | 0.944 | 1 | 4 |
|  | Composite (average) score | 2.95 | 0.898 | 1.00 | 4.00 |

Source Data: Field Survey, August 2018.

4.4 Measurement Assessment

To examine the reliability and validity of the study’s scales, the study relied on Cronbach Alpha test and Exploratory Factor Analysis (EFA). Cronbach alpha test is a suitable technique for assessing the internal consistency of scales (Hair et al, 2014; Cronbach, 1951). Accordingly, the central purpose of using the EFA was to explore for the uni-dimensionality of the scales in the study’s context (O’Leary-Kelly and Vokurka, 1998).

The Cronbach alpha test conducted revealed that each scale in the study had strong internal consistency and was reliable given that the alpha values were above .70 (Cronbach, 1951). Identifying stakeholders, roles of stakeholders in the financial service, critical success factors for stakeholders management, and challenges of stakeholder management had alpha values of .899, .906, .949, and .954 respectively.

4.5 Discussions

A project stakeholder is an organization or individual whose anticipations, needs, position or influence can negatively or positively impact or be impacted by how project activities are carried out and the deliverables attained at project completion (PMI, 2017). Project stakeholders possess diverse and conflicting interests, influences, needs, expectations, roles, and responsibilities. These contradictory positions especially on key project issues may result in severe obstructions and affect overall project success. An organization must therefore identify and appreciate its stakeholder mix, manage their interests and demands, and promote proactive communication to successfully attain project deliverables (PMI, 2017). Again, arguments settle that due attention must be directed at identifying relevant stakeholders of the project in order to meet their respective needs for the survival of the organization (Baron, 2009).

Evaluating stakeholder’s demands and influence must also be treated as crucial in the planning, execution and closing of projects (Olander & Landin, 2005). To reduce uncertainty, stakeholder analysis should be carried out by the project management team to give the project organization insight into the project environment (Aaltonen, 2011). A widely held view on stakeholder management is that the value realized from stakeholders and their relationship with the project team ultimately determines the success or failure of a project.  In an attempt to contribute to the body of knowledge on stakeholder management, this study relied on a sample of fifty (50) employees from the financial services sector of Ghana, specifically Brong Ahafo Region.  The results obtained are discussed in further details below.

Identification of Stakeholders

The descriptive results on the items and their composite (average) score are shown in Table 4.5. Of the 7 items, the lowest mean score was 2.71 (standard deviation = .562) and the highest means score was 3.74 (standard deviation = .957). The overall mean score was 3.37 (standard deviation = 1.439). Given a scale of 1 to 4, these results, suggest that various stakeholders are strongly identified in the financial sector in delivery product and services. Nalewaik et al (2015) make a significant contribution to stakeholder categorization and see stakeholder groupings via their contractual ties to the project, magnitude of involvement, and status on the project. The argument espoused by Langtry (1994) contends that stakeholders possess legitimate and moral claims in that the organization is highly responsible for their well-being.

Role of Stakeholders in the Financial Services Sector

The descriptive statistics of the items and their overall average score are shown in Table 4.6. Across the seven dimensions, an average participant scored 3.75 (standard deviation = 1.853). 4.58 (standard deviation = 2.108), 3.22 (standard deviation = 2.051), 3.18 (standard deviation = 0.814), 3.23 (standard deviation = 0.676), 3.38 (standard deviation = 0.783) and 3.2 (standard deviation = 0.925). The means and the standard deviation scores were obtained on all the seven dimensions respectively. Overall, the composite average score and standard deviation were 3.35 and 1.470 respectively. Given the  scale of 1 to 4 used to measure the items, these results suggest that roles of stakeholders as well as their responsibilities are very important in the financial service sector in the delivery of products and services. Okoli et al (2016) opined that the financial services sector has various categories of stakeholder groups who purposefully or unintentionally contribute to the survival of the industry. Each group has distinctive interests that may conflict with each other, the project deliverables, and even the strategic objectives of the institution. Bryson (2004) argues that the creation and sustenance of these institutions result from the satisfaction of the needs and wants of their clients, who constitute their chief stakeholder group.

Critical Success factors for Stakeholder Management

The descriptive statistics of the items and their overall average scores are shown in Table 4.7. Across the 14 dimensions, an average participant scored 3.95 (standard deviation = 3.174). 3.92 (standard deviation = 3.535), 3.33 (standard deviation = 0.640), 3.41 (standard deviation = 0.682), 3.23 (standard deviation = 0.354), 3.57 (standard deviation = 2.11) and 3.27 (standard deviation = 0.659), 3.88 (standard deviation = 4.318), 3.73 (standard deviation = 3.246),  3.40 (standard deviation = 0.608),  3.09 (standard deviation = 0.795),  3.90 (standard deviation = 2.263),  3.39 (standard deviation = 0.622), and  3.27 (standard deviation = 0.673).  The mean and the standard deviation scores were obtained on all the fourteen dimensions used to measure critical success factors for stakeholder management respectively. Overall, the composite average score and standard deviation were 3.54 and 1.779 respectively.

Given the scale of 1 to 4 used to measure the items, these results suggest that these factors are the areas within which the attainment of satisfactory results will enable the successful delivery of project goals, implying that the successful development and delivery of financial product and service packages is intricately tied to the attainment of these factors. Yang (2011) describes these critical success factors as issues, activities and practices that should be addressed or implemented to achieve project results. Cleland and Ireland (2002) argue that prior to project implementation, the project team should be able to predict the responses and reactions of stakeholders to proposed engagement strategies. Cleland (1995) posited that regular, planned and effective communication with all project stakeholders is vital for project success. Weaver (2007) opined that project managers must possess good communication and bargaining skills in order to eloquently manage stakeholder needs and form a positive culture within the project environment. All these authors in their works, sought to reinforce the finding of this study in respect of the critical success factors for effective stakeholder management.

Stakeholder Management Challenges

The descriptive results on the items and their composite (average) score are shown in Table 4.8. Of the 8 items, the lowest mean score was 2.82 (standard deviation = .868) and the highest means score was 3.1 (standard deviation = .944). The overall mean score was 2.95 (standard deviation = 0.898). Given the scale of 1 to 4, these results suggest that the activity of managing stakeholders in and of itself is a challenging endeavor as the convergence of an organization’s strategic objectives with the needs and expectations of their diverse stakeholder groups creates bottlenecks on the path to project delivery. Karlsen (2002) posited that challenges and problems develop due to the dynamic nature of human interactions and communications. These challenges result from ill-defined or conflicting project responsibilities and authority levels, unplanned changes in project scope and specifications, poor stakeholder representation in decision-making, inability of stakeholders to comprehend their respective roles, and unclear needs of the end user.

# 4.6 Chapter conclusion

This chapter presented the study’s results and findings. It also discussed the findings in relation to the study’s objectives and the pertinent literature.  The subsequent chapter presents the summary of the findings, conclusion, and recommendations of the study.

CHAPTER FIVE

SUMMARY OF FINDINGS, CONCLUSION AND RECOMMENDATIONS

5.1 Introduction

The purpose of this study was to identify stakeholders of the financial services industry and analyze comparatively their roles in the delivery of financial services and products. This chapter of the study provides a summary of the study findings in congruence with the slated research objectives.   The chapter also presents thorough conclusion and recommendations based on the findings discovered by the study. The recommendations of the study covered two broad areas namely policy or practical recommendations and future research recommendations. Whilst the practical recommendations cover steps to improve product delivery development regarding stakeholder participation, future research recommendations cover information for future researchers on the topic under study.

5.2 Summary of Findings

The claim that stakeholders play a vital role in financial institutions is plausible as many organizations take them into consideration in the design and delivery of financial products and services for customer consumption. However, stakeholder identification and engagement in the financial services industry have not been seriously looked at. Stakeholders have been seen to a large extent to determine project success.  In the light of this, the purpose of the study was to analyze comparatively the roles of the various stakeholder groups in the delivery of financial service and product packages in Brong Ahafo Region.

The first objective of the study was to identify the various stakeholders and examine their roles in the delivery of projects in the financial services sector. The study found that various stakeholders’ were identified and the level of importance ascribed to each group varied among participants, with clients and customers as well as employees and management seeing the highest scores while competitors, as in other financial institutions were considered the least important stakeholder group. Again, stakeholders play a significant role in delivering a product or service in the financial service sector. The findings herein clearly depict that identifying stakeholders exerts significant effect on successful project design and delivery.

The second objective of the study was to explore the critical success factors for effective stakeholder management in the financial sector. The study found that critical factors for effective stakeholder management are very important in any institution. Overall, the study found a significant positive relationship between critical success factors for effective stakeholder management on project delivery in the financial services sector.

The third objective of the study was to identify stakeholder management challenges in the financial services sector. The study discovered that stakeholder management challenges on average pose slight to moderate problems for financial institutions. The dimensions used to measure challenges indicate that challenges were not unusual in project delivery in the financial sector. With special reference to unplanned changes in project scope, product design and specification, it was observed that this challenge had the greatest impact on the successful implementation of projects in the financial services industry.

5.3 Conclusion

Identification of stakeholders, examination and understanding of their roles, the critical success factors for their effective management, and the inherent challenges in their management in organization, especially the financial services sector are very vital subject matters to every organization, specifically agents of the financial services industry. Therefore, encouraging stakeholder management and engagement in institutions is a must. The study has proven that stakeholder engagement and management is very vital for an organization’s continual existence.

# 5.4 Recommendations

Based on the findings of the study, the following recommendations are provided;

- The study found that effective stakeholder management and engagement foster successful project implementation therefore, it is recommended that institutions develop and strengthen their practices and strategies for stakeholder engagement and management.

- It is also recommended that critical success factors and stakeholder management challenges must be looked at carefully in order to prevent problems arising from engaging and managing stakeholders on a project. This can be done through proper identification of stakeholders at the early start of the project, and a clear understanding of their needs, interests and expectations on the project.

5.5 Future Research Recommendations

The following future research recommendations are provided;

- The study was limited to five (5) institutions in Brong Ahafo and a sample size of 50 respondents, capturing the views of a single stakeholder group within the financial services industry. Further research involving a larger sample size will facilitate a better understanding of the issues under discussion in this work, as well as expose the differences and peculiarities in stakeholder management across the financial industry.

REFERENCES

Aaltonen K. Jaakko K, Tuomas O. (2008). Stakeholder Salience in Global Projects. International Journal of Project Management. 26(5): pp.509-516.

Aaltonen, K. (2011). Project Stakeholder Analysis as an Environmental Interpretation Process. International Journal of Project Management. 29(2): pp.165-183.

Albrecht J. C., Spang K. (2014). Project Complexity as an Influence Factor on the Balance of Costs and Benefits in Project Management Maturity Modeling. Prodecia – Social and Behavioral Sciences. 119 (2014): pp.162-171.

Alva H. N. (2018). How Leading Banks are Adapting to a Constantly Evolving Financial Sector/Interviewer: World Finance Magazine. https://www.worldfinance.com/banking/how-leading-banks-are-adapting-to-a-constantly-evolving-financial-sector Retrieved on 17th August 2018.

Antony J. Leung K. Knowles G. Gosh S. (2002). Critical Success Factors of TQM Implementation in Hong Kong Industries. International Journal of Quality and Reliability Management. 19(5): pp.551-566.

Ayatah, A. K. (2012). Examining Stakeholder Management Challenges and their Impact on Project Management in the Case of Advocacy and Empowerment NGOs in the Upper East Region of Ghana. (Unpublished master's thesis). Kwame Nkrumah University of Science and Technology, Kumasi, Ghana.

Association for Project Management [APM]. (n.d.). Stakeholder Engagement: Ten Key Principles of Stakeholder Engagement.  Bucks: APM. https://www.apm.org.uk/resources/find-a-resource/stakeholder-engagement/key-principles/ Retrieved on 16th August 2018.

Banks and Specialized Deposit-Taking Institutions Act 2017 (Act 930). Ghana.

Bank of Ghana. (2017). Bank of Ghana Annual Report 2017. Accra: Bank of Ghana.

Baron D. (2009). A Positive Theory of Moral Management, Social Pressure, and Corporate Social Performance. Journal of Economics & Management Strategy. 18(1): pp.7-43.

Beringer C. Jonas D. Kock A. (2013). Behaviour of Internal Stakeholders in Project Portfolio Management and its Impact on Success. International Journal of Project Management. 31(6): pp.830-846.

Bernard H. R. (2002). Research Methods in Anthropology: Qualitative and Quantitative Approaches. 3rd ed. Walnut Creek: Altamira Press.

Best J. W. Kahn J. V. (1998). Research in Education. 8th ed. Boston: Allyn and Bacon.

Bourne, L. (2005). Project Relationship Management and the Stakeholder Circle. Doctor of Project Management, Graduate School of Business, RMIT University, Melbourne.

Bourne L. Walker D. H. T. (2005). Visualizing and Mapping Stakeholder Influence. Management Decision. 43(5): pp.649-660.

Bourne L. (2013). Effective Stakeholder Engagement for Project Success. [PowerPoint presentation]. Melbourne: Pty Ltd. https://mosaicprojects.com.au/PDF_Papers/P176_engagement_for_project_success.pdf  Retrieved on 7th August 2018.

Brian J. (2017). 8 Project Stakeholders you should never ignore before Project Launch. www.blog.taskque.com/project-stakeholders-launch Retrieved on 16th August 2018.

Bryson J. M. (2004). What to do when Stakeholders Matter: Stakeholder Identification and Analysis Techniques. Public Management Review. 6(1): pp.21-53.

Carroll A. B. (1979). A Three-Dimensional Conceptual Model of Corporate Social Performance. Academy of Management Review. 4(4): pp.497-505.

Chandler L. V. (1967). Government’s Evolving Role in Financial Markets. Business Economics. 2(3): pp.12-14

Clarkson M. B. E. (1994). The Toronto Conference: Reflections on Stakeholder Theory. Business and Society. 33(1): pp.82-131.

Clarkson M. B. E. (1995). A Stakeholder Framework  for Analyzing and Evaluating Corporate Social Performance. Academy of Management Review. 20(1): pp.92-117.

Claessens M. (2015). Definition of Product and Service – What is a Product, What is a Service? Marketing-Insider. www.marketing-insider.eu/definition-of-product Retrieved on 12th August 2018.

Cleland D. I. (1995). Leadership and Project Management Body of Knowledge. International Journal of Project Management. 13(2): pp.82-88.

Cleland D. I. Ireland L. R. (2002). Project Management: Strategic Design and Implementation. (4th ed.). New York: McGraw Hill.

Cooray A. (2011). The Role of the Government in Financial Sector Development. Economic Modelling. 28(3): pp.928-938.

Creswell J. W. Klassen A. C. Plano C. V. L. Smith K. C. (2011). Best Practices for Mixed Methods Research in the Health Sciences. Washington DC: Office of Behavioral and Social Science Research, National Institute of Health.

Cronbach L. J. (1951). Coefficient Alpha and the Internal Structure of Tests. Psychometrika. 16(3): pp.297-334.

Dood E. M. (1932). For whom are Corporate Managers Trustees? Harvard Law Review. 45(7): pp.1145-1163.

Donaldson, T., Preston, L. E., (1995). The Stakeholder Theory of the Corporation: Concepts, Evidence, and Implications. Academy of Management Review. 20(1): pp.65-91.

Eesley C. Lenox M. J. (2006). Firm Responses to Secondary Stakeholder Action. Strategic Management Journal. 27(8): pp.765-782.

Fassin Y. (2009). The Stakeholder Model Refined. Journal of Business Ethics. 84(1): pp.113-135.

Freeman R. E. (1984). Strategic Management: A Stakeholder Approach. Boston: Pitman.

Freeman R. E. (1999). Response: Divergent Stakeholder Theory. Academy of Management Review. 24(2): pp.233-236.

Freeman R. E. Harrison J. E. and Wicks A. C. (2007). Managing for Stakeholders: Survival, Reputation, and Success. New Haven, Connecticut: Yale University Press.

Frooman J. (1999). Stakeholder Influence Strategies. The Academy of Management Review. 24(2): pp.191-205.

Fummey S. L. (2016). Exploring Critical Success Factors for Stakeholder Management in Construction Projects in Ghana. (Unpublished master's thesis). Kwame Nkrumah University of Science and Technology, Kumasi, Ghana.

Ghauri P. N. Gronhaug K. (2005). Research Methods in Business Studies: A Practical Guide. (3rd ed.). Financial Times. Prentice Hall.

Hair J. F. Sarstedt M. Hopkins L. Kuppelwieser V. G. (2014). Partial Least Squares Structural Equation Modeling (PLS-SEM): An Emerging Tool in Business Research. European Business Journal. 26(2): pp.106-121.

Hartman. F.T. (2002). The Role of Trust in Project Management. In Slevin D. P., Cleland D. I.,  Pinto J. K. (ed). The Frontiers of Project Management Research (pp. 225-235). Newtown Square, Pennsylvania: PMI.

Hill C. W. L. Jones T. M. (1992). Stakeholder-Agency Theory. Journal of Management Studies. 29(2): pp.131-154. http://dx.doi.org/10.1111/j.1467-6486.1992.tb00657

Hillman A. J. Keim G. D. (2001). Shareholder Value, Stakeholder Management, and Social Issues: What’s the Bottom Line? Strategic Management Journal. 22(2): pp.125-139.

Indrajit R. E. (2002). Project Management in Banking Industry: Learning from the Experience of Various Projects. [PowerPoint presentation]. Academia.edu https://www.academia.edu/14436477/PROJECT_MANAGEMENT_IN_BANKING_INDUSTRY_Learning_From_the_Experience_of_Various_Projects  Retrieved on 8th August 2018.

Karlsen, J. T. (2002). Project Stakeholder Management. Engineering Management Journal. 14(2): pp.19-24.

Karlsen, J. T. (2008). Forming Relationships with Stakeholders in Engineering Projects. European Journal of Industrial Engineering. 2(1): pp.35-49.

Kastner R. (2010). Why Projects Succeed: Stakeholder Management Challenges Justification for Planning. Planning Theory. 1(2): pp.I63 87.

Kerzner H. (2009). Project Management: A Systems Approach to Planning, Scheduling, and Controlling. (10th ed). Hoboken, New Jersey: John Wiley and Sons.

Langtry B. (1994). Stakeholders and the Moral Responsibilities of Business. Business Ethics Quarterly. 4(4): pp.431-443.

Liang X., Yu T., Guo L. (2017). Understanding Stakeholders’ Influence on Project Success with a New SNA Method: A Case Study of the Green Retrofit in China. Sustainability. 9, 1927. Google Scholar. Retrieved on 5th August 2018.

Matta N. F. Ashkenas R. N. (2003). Why Good Projects Fail Anyway. Harvard Business Review. (September 2003). www.hbr.org/2003/09/why-good-projects-fail-anyway Retrieved on 12th August 2018.

Millenium Bank (n.d.). Stakeholders of Bank Millennium Group: Mapping and Classification. www.bankmillennium.pl/static-content/EN/Stakeholders_mapping_1273424.pdf Retrieved on 16th August 2018.

Mitchell R.K. Bradley R. A. Wood D. J. (1997). Toward a Theory of Stakeholder Identification and Salience: Defining the Principle of Who and What really Counts. The Academy of Management Review. 22(4): pp.853-885.

Mugenda, O. M., Mugenda, A. G. (2003). Research Methods: Quantitative and qualitative Approaches. Nairobi: African Centre for Technology Studies.

Nalewaik A., Mills A. (2015). Project Stakeholder Concerns and Expectations. In: Proceedings of the 19th Pacific Association of Quantity Surveyors Congress. (pp.1-10). The Conference, Yokohama, Japan.

Okoli I. E. Monanu O. G. Adibe C. G. (2016). Effective Stakeholder Management in Banking Industries. International Journal of Research in Management, Science and Technology. 4(1): pp.32-36.

Olander S.  Landin A. (2005). Evaluation of Stakeholder Influence in the Implementation of Construction Projects. International Journal of Project Management. 23(4): pp.321-328.

Olander S. (2006). External Stakeholder Analysis in Construction Project Management. (Doctoral thesis). Lund University, Sweden.

Olander S. (2007). Stakeholder Impact Analysis in Construction Project Management. Construction Management and Economics. 25(3): pp.277-287.

Olander S. Landin A. (2008). A Comparative Study of Factors Affecting the External Stakeholder Management Process. Construction Management and Economics. 26(6): pp.553-561.

O’Leary-Kelly S. Vorkurka R. J. (1998). The Empirical Assessment of Construct Validity. Journal of Operations Management. 16(4): pp.387-405.

Orodho, J.A. (2009). Essentials of Educational and Social Science Research Methods. Nairobi: Masola Publishers.

Orodho, J. A. (2012). Techniques of writing Research Proposals and Reports in Education and Social Sciences. Nairobi: Kanezja Publishers

Preston L. E. Sapienza H. J. (1990). Stakeholder Management and Corporate Performance. Journal of Behavioral Science. 19(4): pp.361-375.

Project Management Institute [PMI]. (2017). A Guide to the Project Management Body of Knowledge (PMBOK Guide). 6th ed. Newtown Square: PMI.

Purvis R. L. Zagenczyk T. J. McCray G. E. (2014). What’s in it for me? Using Expectancy Theory and Climate to explain Stakeholder Participation, its Direction and Intensity. International Journal of Project Management. 33(1): pp.3-14.

Roeder T. (2013). Managing Project Stakeholders: Building a Foundation to Achieve Project Goals. New Jersey: John Wiley & Sons Inc.

Ruben A. Babbie E. R. (1989). Research Methods for Social Work. Michigan: Wadsworth Publishing Co.

Savage G. T. Nix T. W. Whitehead C. J. Blair J. D. (1991). Strategies for Assessing and Managing Organizational Stakeholders. Academy of Management Executive. 5(2): pp. 61-75.

Schermerhorn, J. R., Hunt, J. G., Osborn, R. N. (2003). Organizational Behavior. (8th ed). New York: John Wiley & Sons Inc.

Schwager H. P. (2004). Organizational Strategies to address Stakeholder Relationships: A Customer Portal Perspective. (PhD thesis). Aubum University.

Semali I. A. J. (2003). Understanding Stakeholders’ Roles in Health Sector Reform Process in Tanzania: The Case of Decentralizing the Immunization Programme. (unpublished doctoral dissertation), University of Basel, Switzerland.

Seymour T. J., Hussein S. (2014). The History of Project Management. International Journal of Management and Information Systems. 18(4): pp.233-240.

Simons M. (2016). The Impact of Customer Service on Customer Patronage in Banking – The Mediating Effect of ICT Adoption. (unpublished master’s thesis), Kwame Nkrumah University of Science and Technology, Kumasi, Ghana.

Singh R., Khan I. A. (2012). An Approach to Increase Customer Retention and Loyalty in B2C World. International Journal of Scientific and Research Publications. 2(6): pp.606-610.

Spradley J. P. (1979). The Ethnographic Interview. New York: Harcourt Brace Jovanich College Publisher.

Tammer M. D. (2009). Early Stakeholder Involvement in Projects. PM World Today. 11(4): 1-6.

Tapestry Networks. (2016). Revolutionary Change is Transforming the Financial Services Landscape. Financial Services Leadership Summit. Tapestry Network Inc.

Trochim W. M. K. (2005). Research Methods: the Concise Knowledge. Atomicdog Publishing.

Upchurch R. S. (1998). A Conceptual Foundation for Ethical Decision Making: A Stakeholder Perspective in the Lodging Industry (USA). Journal of Business Ethics. 17(12): pp.1349-1361.

Vrecko I., Barilovic Z. Bozicev M. (2015). The Role of IT Departments in the Enhancement of Bank’s Project Management. Informatologia. 48 (3): pp.123-134.

Walker D. H. T. Bourne L. Rowlinson S. (2008). Stakeholders and the Supply Chain. In Procurement Systems: A Cross-industry Project Management Perspective. (pp.70-100). London: Taylor and Francis.

Ward S. Chapman C. (2008). Stakeholders and Uncertainty Management in Projects. Construction Management and Economics. 26(6): pp.563-577.

Weaver P. (2007, October). Getting the “soft stuff” right – Effective Communication is the key to Successful Project Outcomes. Paper presented at the PMI Global Conference. Atlanta, Georgia.

Winch G. (2000). Construction Business Systems in the European Union. Building Research and Information. 28(2): pp.88-97.

Yang J., Shen G. Q., Ho M., Drew D. S. & Chan A. P. C. (2009a). Exploring Critical Success Factors for Stakeholder Management in Construction Projects. Journal of Civil Engineering and Management. 15 (4): pp.337-348.

Yang J. Shen G. Q. Ho M. (2009b). An Overview of Previous Studies in Stakeholder Management and its Implications for the Construction Industry. Journal of Facilities Management. 7(2): pp.159-175.

Yener D. (2002, November). Employees as Stakeholders: The Challenges of Building an Employee Ownership Culture. Paper presented at the OECD Corporate Governance Round Table South East European Regional Meeting. Zagreb, Croatia.

Youker R. (2017). The Difference between Different Types of Projects. 2nd ed. PM World Journal. 6(4). www.pmworldjournal.net Retrieved on 13th August 2018.

APPENDIX I

KWAME NKRUMAH UNIVERSITY OF SCIENCE AND TECHNOLOGY, KUMASI

DEPARTMENT OF CONSTRUCTION TECHNOLOGY AND MANAGEMENT

PROGRAMME: MSC. PROJECT MANAGEMENT

A COMPARATIVE ANALYSIS OF PROJECT MANAGEMENT DELIVERY IN THE FINANCIAL SERVICES SECTOR: THE ROLE OF STAKEHOLDERS.

QUESTIONNAIRE

Preamble

My name is Rose Kalu. I am a final year MSc. Project Management student from the Department of Construction Technology and Management at Kwame Nkrumah University of Science and Technology, Kumasi. As part of the requirement for the master’s degree, I am conducting a research on the topic: A Comparative Analysis of Project Management Delivery in the Financial Services Sector: The Role of Stakeholders.

The objectives of this study include:

- To identify the various stakeholders of the financial service industry and examine their roles in the development and delivery of financial products and services.

- To explore the critical success factors for effective stakeholder management in the financial sector.

- To identify stakeholder management challenges in the financial services sector.

The implication of the findings is for the future implementation and development of products and services in the financial services sector in Ghana and beyond.

Information given will be treated with utmost confidentiality and only be used for academic purposes. Please provide the correct information by ticking [√] and fill in the blank spaces where necessary.

Thank you for your participation and assistance with this study.

SECTION A: GENERAL INFORMATION

- What is your age?

[   ]   0 – 29				[   ] 30 – 39

[   ] 40 – 49				[   ] 50 and above

- What is your gender?

[   ] Male				[   ] Female

- What is your highest academic qualification?

[   ] SSCE/WASSCE/O Level Certificate 		[   ] Professional Certificate

[   ] Bachelor’s Degree 				[   ] Master’s Degree

[   ] Others (Please specify): _____________________________________________

- How long have you worked with this institution?

[   ] Less than 	a year					[   ] Between 1 – 3 years

[   ] Between 4 – 9 years				[   ] Between 10 – 15 years

[   ] More than 15 years

- What is your position in the institution?

[   ] Director						[   ] Programmes Manager

[   ] Project Manager/Officer				[   ] Administrative Manager

[   ] Communication/IT Manager			[   ] Sales/Marketing

[   ] Front Desk/Customer Service

[   ] Employee (Please specify role): ________________________________________

- How will you rate your level of involvement in the development and delivery (ie. product design, sales, marketing, distribution, etc.) of new products and services in your institution? (On a scale of 1 – 4, 1 being “Lowly involved” and 4 being “Highly involved”).

1 [   ]		           2 [   ]		           3 [   ]			     4 [   ]

Lowly Involved	 Slightly Involved  	Moderately Involved	        Highly Involved

SECTION B: IDENTIFICATION OF STAKEHOLDERS IN THE FINANCIAL SERVICES SECTOR

On a scale of 1 to 4, to what extent do you consider the following individuals as stakeholders of your institution?

1                                          2                                3                                  4

Strongly Disagree                   Disagree                     Agree                   Strongly Agree

|  |  | Level of Importance |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Identification of Stakeholders | 1 | 2 | 3 | 4 |
|  | Customers and Clients |  |  |  |  |
|  | Employees and Management |  |  |  |  |
|  | Competitors – other financial institutions |  |  |  |  |
|  | Regulatory Agencies – Bank of Ghana, Securities and Exchange Commission, etc. |  |  |  |  |
|  | Contractors, Suppliers and Consultants |  |  |  |  |
|  | Civil society groups and Community Leadership |  |  |  |  |
|  | The general public |  |  |  |  |

SECTION C: ROLES OF STAKEHOLDERS IN THE FINANCIAL SERVICES SECTOR

On a scale of 1 to 4, how will you rate the roles of the various stakeholders in the development and delivery of services and products in your institution?

1                                       2                               3                                 4

Strongly Disagree                  Disagree                     Agree                    Strongly Agree

|  | Roles of Stakeholders | 1 | 2 | 3 | 4 |
| --- | --- | --- | --- | --- | --- |
|  | Customers and Clients |  |  |  |  |
| 1 | The needs of our customer dictate the requirements and specifications of our product and service packages. |  |  |  |  |
| 2 | The successful design and delivery of our new products and services is defined by our customers’ level of patronage of the finished product. |  |  |  |  |
| 3 | Successful new product development requires in-depth understanding of our customers, their situation, their needs, and wants. |  |  |  |  |
|  | Employees and Management |  |  |  |  |
| 1 | My colleagues and I (as employees and management) are at the forefront of the product or service development process – including contributing to the designing, marketing, and sales processes. |  |  |  |  |
| 2 | My colleagues and I contribute to new service and product ideas and help determine ways to implement them to get favorable customer responses. |  |  |  |  |
| 3 | My institution’s top management support and commitment affect the success of our new services and products development programmes. |  |  |  |  |
| 4 | Senior management work towards ensuring that our projects (ie. development of customer product and service packages) meet the strategic objectives of the institution. |  |  |  |  |
|  | Competitors (ie. institutions offering similar products and services) |  |  |  |  |
| 1 | My institution relies on industry-wide innovation and information from competitors in the development of new products and services. |  |  |  |  |
| 2 | Some of our products and services require collaboration and support from our competitors. |  |  |  |  |
| 3 | In assessing the quality of our new products and service, we use industry standards (ie. what is being done by our competitors) as a benchmark. |  |  |  |  |
|  | Regulatory/Supervisory Agencies – BoG, SEC, GRA, etc. |  |  |  |  |
| 1 | In developing new products for the market, we require express approval from our regulators. |  |  |  |  |
| 2 | In our development processes, we strive to comply with regulations and code of ethics provided by our supervisory agencies. |  |  |  |  |
| 3 | We are required to furnish our regulators with detailed information on the features of products and service packages prior to introducing them to the market. |  |  |  |  |
| 4 | Disapproval and sanctions from our regulators negatively affects our development of new products and services. |  |  |  |  |
|  | Contractors, Suppliers and Consultants |  |  |  |  |
| 1 | They provide the needed inputs required for product development. |  |  |  |  |
| 2 | They provide us with the technical expertise required to bring our ideas into fruition. |  |  |  |  |
|  | Civil society, Groups and Community Leadership |  |  |  |  |
| 1 | Their interest lies in ensuring that our products/services are not detrimental to the welfare of our customers. |  |  |  |  |
|  | The General Public |  |  |  |  |
| 1 | Their significant negative reactions (eg. demonstrations, protests, and civil unrest) to our products will cause us to withdraw them from the market. |  |  |  |  |

SECTION D: CRITICAL SUCCESS FACTORS FOR STAKEHOLDER MANAGEMENT

On a scale of 1 to 4, how will you rate the following critical success factors for effectively managing stakeholders in the delivery of products and services in the financial sector?

1                                      2                                  3                                   4

Strongly Disagree               Disagree                       Agree                      Strongly Agree

|  | Critical Success Factor | 1 | 2 | 3 | 4 |
| --- | --- | --- | --- | --- | --- |
|  | Undertaking Social Responsibilities |  |  |  |  |
| 1 | Meeting customer needs at reasonable prices |  |  |  |  |
| 2 | Due consideration for legal and ethical issues in product development |  |  |  |  |
|  | Defining Project Missions |  |  |  |  |
| 1 | Clear definition of goals before commencement of product development |  |  |  |  |
| 2 | Elaborate project management planning. |  |  |  |  |
| 3 | Clear understanding of project needs and requirements. |  |  |  |  |
|  | Analyzing Stakeholder Behavior |  |  |  |  |
| 1 | Observing and assessing the behavior of stakeholders. |  |  |  |  |
| 2 | Categorizing stakeholders based on their support, interest and influence. |  |  |  |  |
|  | Identifying Stakeholders |  |  |  |  |
| 1 | Identifying all key stakeholders of the project prior to commencement. |  |  |  |  |
| 2 | Ensuring no stakeholder group is marginalized or left out. |  |  |  |  |
|  | Predicting the Influence of Stakeholders |  |  |  |  |
| 1 | Assessing the actual and potential impact of stakeholders’ actions. |  |  |  |  |
| 2 | Predicting the potential influence of key stakeholders groups. |  |  |  |  |
|  | Assessing Attributes of Stakeholders |  |  |  |  |
| 1 | Stakeholders influence is well evaluated |  |  |  |  |
| 2 | Demands of stakeholders are met |  |  |  |  |
| 3 | Rules and regulations from stakeholders are recognized |  |  |  |  |
|  | Understanding the Area of Stakeholders Interest |  |  |  |  |
| 1 | Understanding the expectations stakeholders have for the project outcomes. |  |  |  |  |
| 2 | Understanding how or why the product/service is of interest to them. |  |  |  |  |
|  | Exploring Stakeholders Need and Constraints in Projects |  |  |  |  |
| 1 | Meeting the needs of stakeholders contributing to product development |  |  |  |  |
| 2 | Addressing the challenges faced by stakeholders during development |  |  |  |  |
|  | Analyzing Conflicts and Coalitions among Stakeholders |  |  |  |  |
| 1 | Managing stakeholder conflicts to mitigate their effects on the project. |  |  |  |  |
| 2 | Managing stakeholder partnerships to exploit the opportunities they present for the project. |  |  |  |  |
|  | Resolving Conflicts among Stakeholders |  |  |  |  |
| 1 | Project managers resolve conflict amicably |  |  |  |  |
| 2 | Stakeholders are satisfied with conflict resolution techniques. |  |  |  |  |
|  | Analyzing the Change of Stakeholders |  |  |  |  |
| 1 | Stakeholders’ interest, influence, and positions change over time. |  |  |  |  |
| 2 | There is the need to proactively manage these changes. |  |  |  |  |
|  | Ensuring Effective Communication |  |  |  |  |
| 1 | Project manager and team need good communication skills |  |  |  |  |
| 2 | Stakeholders are involved in all communication processes |  |  |  |  |
| 3 | Positive culture is formed within the project environment through constant communication and engagement. |  |  |  |  |
|  | Formulating Appropriate and Effective Strategies |  |  |  |  |
| 1 | Good strategies for communicating project information to stakeholders |  |  |  |  |
| 2 | Good strategies for conflict resolution among stakeholders |  |  |  |  |
| 3 | Good strategies for reward and recognition of stakeholders |  |  |  |  |
|  | Predicting Stakeholder Reactions to Engagement Initiatives |  |  |  |  |
| 1 | Early detection of stakeholder responses and reactions |  |  |  |  |
| 2 | Reactions of stakeholders are predicted and proactively managed |  |  |  |  |

SECTION E: STAKEHOLDER MANAGEMENT CHALLENGES.

On a scale of 1 to 4, how will you rate the following challenges of stakeholder management in the financial services sector?

1                                         2                                 3                                   4

Strongly Disagree                   Disagree                       Agree                   Strongly Agree

|  | Stakeholder Management Challenges | 1 | 2 | 3 | 4 |
| --- | --- | --- | --- | --- | --- |
| 1 | Poor stakeholder representation in project decision making |  |  |  |  |
| 2 | Inability of stakeholders to understand their respective roles |  |  |  |  |
| 3 | Unclear definition of interests and expectations of stakeholders |  |  |  |  |
| 4 | Unidentified stakeholders at the early stages of the project |  |  |  |  |
| 5 | Conservative stakeholders |  |  |  |  |
| 6 | Ill-defined or conflicting project responsibilities |  |  |  |  |
| 7 | Undefined and conflicting project authority levels |  |  |  |  |
| 8 | Unplanned changes in project scope, design, and specifications |  |  |  |  |