CHALLENGES FACING INTERNATIONAL JOINT VENTURES IN EXECUTION OF CONSTRUCTION PROJECTS IN GHANA.

By

(BSc. Construction Technology)

Joshua Blerpo

A thesis submitted to the Department of Construction Technology and Management, Kwame Nkrumah University of Science and Technology, Kumasi in partial fulfilment of the requirement for the award degree of

MASTER OF SCIENCE IN CONSTRUCTION MANAGEMENT

Novermber, 2019.

# DECLARATION

I hereby declare that this submission is my own work and that, to the best of my knowledge and belief, it contains no material previously published or written by another person nor material which to a substantial extent has been accepted for the award of any other degree or diploma at Kwame Nkrumah University of Science and Technology, Kumasi or any other educational institution, except where due acknowledgment is made in the thesis.

Joshua Blerpo (PG9189917) 		………………………….	………………..

Students Name and ID		Signature			Date

Certified by:

Mr. James Coffie Danku     		………………………….	………………….

Name of Supervisor			Signature			Date

Certified by:

Prof Bernard K. Baiden		…………………………...	……………………..

Name of Head of Department		Signature			Date

# ABSTRACT

Projects which have been globally constructed pose a high level of challenges and complexities that produces greater potentials of overrun and conflict when associated with local. The complexity of the global setting is affected by wide-ranging variables which does not form part of the local markets in addition creates challenges never come upon in local conditions. The aim of the study was to identify the challenges facing international construction joint ventures in Ghana. For all purposes, a literature search was carried out and a survey conducted using a well-structured questionnaire. Eighty-two (82) questionnaire were distributed by purposive sampling, and sixty-five (65) completed questionnaires representing 80% were considered valid for the analysis. The data collected were analyzed using Relative Importance Index (RII) and descriptive statistics thus percentages and frequencies. The study discovered that Policy changes in parent, Erosion of applicability of certain partner competencies, expending time and energy to create equally congenial management practices. Inheriting a partner’s financial problems, Divergences about workforce apportionment and positions in the pecking order of the project team, are major problem governing international joint venture construction project execution in Ghana. Inheriting a partner’s financial problems, having disagreements about accounting standards and recurrent variations in present economic strategies and commercial acts, Expending time and energy to establish mutually agreeable managerial practices, frequent changes in current economic policies and commercial laws, Lack of management competence, Erosion of applicability of certain partner competencies, Technology-transfer disputes are the implication of the challenges on project performance. Among others, it was recommended that joint venture managers should improve the information flow inside a joint venture, which partially requires negotiations with a parent company on the matter of proprietary rights.

Keywords: international, construction, management, economic policy, purposive sampling

TABLE OF CONTENTS

DECLARATION	ii

ABSTRACT	iii

LIST OF TABLES	vi

ACKNOWLEDGEMENTS	vii

DEDICATION	viii

CHAPTER ONE	1

INTRODUCTION	1

1.1 Background of the Study	1

1.2 Problem Statement	3

1.3 Research Questions	4

1.4 Aim and Objectives	5

1.4.1 Aim	5

1.4.2 Objectives	5

1.5 Research Scope	5

1.6 Research Methodology	6

1.7 Justification of the Study	6

1.8 Thesis Structure	7

CHAPTER TWO	8

LITERATURE REVIEW	8

2.1 INTRODUCTION	8

2.2 INTERNATIONAL CONSTRUCTION JOINT VENTURES (ICJVs)	8

2.2.1 International Construction Projects	12

2.3 PROBLEMS GOVERNING INTERNATIONAL PROJECT EXECUTION	14

2.4 Challenges and Risk on Project Performance	19

CHAPTER THREE	24

RESEARCH METHODOLOGY	24

3.1 INTRODUCTION	24

3.2 PHILOSOPHICAL POINT OF THE RESEARCH	25

3.3 RESEARCH STRATEGY	27

3.4 RESEARCH DESIGN	27

3.5 RESEARCH METHOD	29

3.6 DATA SOURCES	30

3.7 POPULATION AND SAMPLING SIZE	30

3.7.1 Sampling Techniques and Data Collection	30

3.8 Questionnaire Design and Development	31

3.9 Data Analysis	32

3.10 Ethical Consideration	33

3.10.1 Reliability and Validity	33

CHAPTER FOUR	34

SURVEY RESULTS, DATA ANALYSIS AND FINDINGS	34

4.1 INTRODUCTION	35

4.1.1 Sample Characteristics	35

4.2 DESCRIPTIVE STATISTICS (DEMOGRAPHIC DATA)	36

4.2.1 Organizational Role	36

4.2.2 Educational level of respondent	37

4.2.3 Experience (Number of International Construction Joint Venture) participated with foreign companies	37

4.2.3 Working Experience of Respondents in the Construction Industry	38

4.3 ANALYSIS AND DISCUSSION OF MAIN OBJECTIVES	39

4.3.1 Problems governing international construction joint venture project execution	39

4.3.2 The implication of the challenges on project performance in Ghana	43

4.3.3 Strategies for better planning and execution of international joint venture construction projects.	45

CHAPTER FIVE	47

SUMMARY OF FINDINGS, CONCLUSION AND RECOMMENDATION	47

5.1 INTRODUCTION	47

5.2 SUMMARY OF FINDINGS	47

5.2.1 Problems governing international joint venture construction project execution	47

5.2.2 The implication of the ICJV challenges on project performance in Ghana	48

5.2.3 Strategies for better planning and execution of international joint venture construction projects in Ghana.	49

5.3 CONCLUSION	50

5.4 RECOMMENDATION	51

REFERENCES	52

# LIST OF TABLES

Table 4.1: Organizational Role …..……………………………………………………..40

Table 4.2: Educational Level...………………………………………………………….41

Table 4.3 Experience in ICJV projects participated...…………………………..………42

Table 4.4: Working Experience of Respondents in the Construction Industry....………43

Table 4.5 Problems governing international joint venture projects execution………….45

Table 4.6 Implication of ICJV challenges on project performance……………………..47

Table 4.7: Strategies for efficient acquisition mode for SMEs in Ghana …..…………..49

# ACKNOWLEDGEMENTS

My first appreciation goes to Almighty God for the opportunity, as well as the direction and wisdom to experience this program. I owe my supervisor, Mr. J. C. Danku many thanks for his valuable commitment and leadership. I also owe much credit to Mrs Edna Dede Tetteh for her immense contribution from the beginning to the end of the program. I also I also acknowledge and appreciate the staff of the Institute for Construction Technology, KNUST, Kumasi. I am very grateful for my wife, Mrs. Gifty Blerpo, parents and my children, Shirley and Joel Blerpo, who have supported me in many ways.

Finally, I thank my colleagues for their constructive criticism and for all those who contributed to making this a success.

# DEDICATION

I dedicate this work first to Almighty God for the gift of life and how far he has brought me. In addition, I dedicate this work to my parents for their constant prayers, support and encouragement throughout the program and, indeed, it would have been difficult without you. In addition, I dedicate this work to my wife and children for their understanding, support, and for keeping up the mistakes in my absence throughout this time, Mrs. Gifty Blerpo, Shirley and Joel Blerpo.

# CHAPTER ONE

# INTRODUCTION

# 1.1 Background of the Study

With the current trend towards globalisation and the increasing technical problems facing today’s business environment, the formation of strategic alliances has become an important part of some firms’ business plan (Kauser and Shaw, 2004). The reason for the upsurge in this trend is the difficulty which most firms face in achieving self-sufficiency in the changing global economy. Many sectors, industries and product groups adopt the formation of joint ventures (JV) to break into the economic market (Griffith, 2001). The last decade or two have seen partnering between firms in the construction industry. This is as a result of the inability of the firms’ management to keep up with the constant competitive change in a wide range of technological, design and developmental requirements (Kauser and Shaw, 2004). Joint venture has thrived in relevance as a medium of operating businesses in and across national boundaries. As such, it is not surprising that much attention has been given to this subject matter in both the media and academic circle (Reuer, 2000; Li et al., 2001). A joint venture (JV) is simply the marriage between two or more legally distinct firms who contribute resources to a semiautonomous legally separate entity, of which they participate in the decision-making process (Geringer, 1988). In a situation where at least one partner is situated separately from the undertaking operation country, it is termed international joint venture (IJV) as according to (Geringer and Hebert, 2001). Construction joint venture (CJV) refers to the cooperation that enables at least, two construction firms, two consultancy firms or between construction and consultancy firm, to combine resources and abilities in the duration of a project. Thus, it is an arrangement that enables two or more legally distinct firms to jointly carry out Architectural, Engineering and Construction (AEC) projects. According to Chan and Tse (2003) global construction developments encompass transnational contributors from diverse political, legal, economic, and cultural background.

It is widely argued that international construction joint ventures (ICJVs) provide a platform where new advance technologies and management expertise are realized, improve quality, reduce work at the project level and mitigate the effect of the cyclical domestic market conditions as well as establish continuing strategies for the balanced growth of domestic and international construction portfolios (Contractor and Lorange, 2004; Cheng et al. 2004; Zhang and Zou, 2007; Han et al. 2007). Nevertheless, in developing countries the attractiveness of foreign investment through JVs is because they are a means of sustaining market development, acquiring advanced technology as well as developing managerial skills necessary to create economic growth (Li et al. 2000). Not far away, citing Ghana as an example, Ghana has since the mid-1960s established an extensive joint participation programme through legislation and administration of investment codes with the objective to develop, finance and contribute to national socio-economic development by building the infrastructure and productive facilities (Afriyie, 1988). Boateng and Glaister (2000) provided evidence to support the overwhelming preference by foreign investors for IJVs in Ghana. A report from the Ghana Investment Promotion Centre shows that, of the 1821 registered projects between the years of 2011-2016, a total 595 projects (32.7%) were executed with JV arrangement by firms. However, out of the 595 joint ventures projects, 206 (34.6%) were building/construction projects. This is a clear indication that, foreign direct investment in Ghana through international joint venture has gain widespread attention.

Accompanied by the growing body of related remunerations related to international cooperative projects is the high degree of instability and poor performance (Parkhe, 1993). Results in several studies shows high estimated rate of about 20% - 30% failure in the developed countries and 40% - 70% failure in the developing countries (Bamford et al. 2004). Due to the complexities that characterize construction activities, and the multidimensional nature of international construction market, issues such as multiple ownership, elaborate financial provisions, cultural, and different political ideologies are often associated with international construction (Chan and Tse, 2003). These projects are more difficult to manage than domestic projects as the challenges involved are more numerous and less predictable (Gunhan and Arditi, 2005). Understanding the challenges as well as the outcomes associated with international construction project execution, are crucial to the growth and sometimes the bare survival of construction companies.

# 1.2 Problem Statement

High level of challenges and complexities is experienced by International construction projects, and this has resulted to greater likelihoods of overrun and conflict when compared with domestic (Han et al. 2008). According to El-Sabek and McCabe (2018) the increase complexities and high level of risk is as a result of complex interface and long planning horizons, planning processes that involve many participants with conflicting interests, and project scope that can change significantly over time. A number of studies on the barriers to successful implementation of international joint venture construction projects have been conducted in the developed countries (Chan and Tse, 2003; Gunhan and Arditi, 2005), with little studies in the developing countries (Ofori, 1991). However, the work of researchers shows that, developing countries are the hardest hit by these problems. The complexity of international environment is affected by wide-ranging variables that are not part of the domestic markets and that create challenges never encountered in domestic conditions. The sensitivity of international joint venture construction projects to the world events like political, financial, cultural and legal risks needs to be considered in the developing countries like Ghana. Understanding the challenges as well as the outcomes associated with international construction project execution in Ghana, is an essential issue to the development and at times the survival of construction companies due to the increasing foreign direct investment through international construction joint venture. Therefore, this study seeks to explore the challenges governing international joint venture construction project execution in Ghana.

# 1.3 Research Questions

The key research questions that will be employed to facilitate the study are;

- What are the challenges governing international joint venture construction project execution?

- What are the are outcomes or implications of the challenges on project performance?

- What strategies can be employed for better planning and execution of international joint venture construction projects in Ghana?

# 1.4 Aim and Objectives

# 1.4.1 Aim

The aim of the study is to identify the challenges facing international joint ventures in the execution of construction project in Ghana.

# 1.4.2 Objectives

To satisfy the above stated research aim the following objectives will be set:

- To identify the problems governing international joint venture construction project execution in Ghana;

- To ascertain the outcome/implication of the challenges on project performance in Ghana;

- To identify strategies for better planning and execution of international joint venture construction projects in Ghana.

# 1.5 Research Scope

This study focusses contextually on the challenges governing international joint venture construction project execution in Ghana. With the increasing focus of infrastructure development in Ghana, a number of foreign firms have partnered with local firms to deliver construction projects as well as consultancy services in the country. These contractors tend to set up their head offices in the major cities such as Accra. With the main motive of benefiting from external expertise local contractors form joint ventures with foreign contractors in order to execute the works. Also, with the quest of being competitive and to secure larger projects, small local contractors find the joint venture as an attractive tool to secure larger and more complex projects which individual firms deem themselves not sufficient to undertake. Most of these contractors operate within the Accra metropolis of Ghana. Therefore, the study will be limited to international joint venture construction companies within the Accra Metropolis.

# 1.6 Research Methodology

The study will employ a quantitative research method. A structured questionnaire survey will be designed to collect primary data from international construction joint venture partners in Accra Metropolis and Kumasi Metropolis. A list of targeted respondents will be drawn up from the records maintained by Ghana Investment Promotion Centre (GIPC). Purposive sampling technique will be used for this study. In order to directly approach contractors who would readily provide the primary data required, the researcher adopted this technique. A period of not more than two weeks would be used for the collection of the primary data and the secondary data would be obtained from both published and unpublished sources throughout the entire project period. Data collected from the questionnaire survey would be analyzed using descriptive statistics.

# 1.7 Justification of the Study

The adoption of international joint ventures from the business industry has resulted in better performance of construction firms in undertaking larger and more complex projects. The findings of our study will advance our knowledge on how to effectively execute and mange international joint ventures construction projects, and to understand the challenges as well as the outcomes associated with international construction project execution. This knowledge is important for both academics and also the management of international construction joint ventures. Even though there exist literature on the risk governing international joint ventures projects in general, very little research has been conducted on challenges in the field of international construction joint ventures. In academics, this survey would add knowledge to the subject area and also serve as a basis for further research for students, teachers, researchers and consultants to conduct studies into other related areas. This could be used as reference material.

# 1.8 Thesis Structure

The thesis has been arranged into five (5) chapters. The first chapter focused on the background, problem statement, research methods, and significance of the research, research aim, the research questions, research objectives and scope of the research. The second chapter comprises the appropriate literature review, which brings clarity to problems governing international joint venture construction project execution, the outcome/implication of the challenges on project performance, strategies for better planning and execution of international joint venture construction projects etc. The third chapter identified and brought together the methodology of the research. The fourth chapter reported on the results of the data and discussion of the results. Lastly, the fifth chapter presented details on the summary of the findings, conclusion and recommendations.

# CHAPTER TWO

# LITERATURE REVIEW

# 2.1 INTRODUCTION

The chapter two presents a literature review for the study. Pertinent literature on challenges facing international joint ventures in execution of construction projects in Ghana are explored. Report gathered in the chapter two provides an outline for comparing and determining the study’s significance and a benchmark for comparing the results with other findings (Creswell, 2009).

# 2.2 INTERNATIONAL CONSTRUCTION JOINT VENTURES (ICJVs)

According to Construction Industry Institute (1991) partnering refers to “a long-term commitment between two or more organizations for the purpose of achieving specific business objectives by maximizing the effectiveness of each participant resources. This requires changing traditional relationships to a shared culture without regard to organizational boundaries. The relationship is based on trust, dedication to common goals, and an understanding of each other’s individual expectation and values”.  This concept as Gunhan and Arditi (2005a) posits is not new, globalization provides the possibility of new opportunities to construction companies.

The construction industry represents over 10% of the global economy and thus its importance cannot be overstated. The growth of firms in the industry in truly global operations has been an important factor in the internationalization of construction. For instance, as Mohammed (2003) indicates, countries that are developing view international joint venture implementation as a viable means of salvaging the pressures that comes with the intrusion of investors overseas and the attempt to meet national development. IJV according to Nelson (2002) refers to the partnership   as cooperation among firms that gives them the economic prowess in order to achieve set objectives over the estimated time and also gives them goodwill. The importance of IJV cannot be overemphasized as it purports to strategically position firms in a competitive environment the opportunity to have shared equipment with firms within their circles. This gives an added advantage because it creates an atmosphere where risk and rewards would be shared among the firms, something that would have been the burden of only one firm. In the construction industry, the use of IJVs as Mohammed (2003) postulates curtails from concepts on how planned activities stimulates the viable positioning of a construction firm in the industry.

Firms with varied merits and demerit form JVs to jointly tender in and complete undertakings. This has been the order of the day because of the ever-rising difficulties and the degree of risks associated with major construction jobs (Kumaraswamy et al., 2000). Construction firms have expansively capitalized on IJVs to penetrate emerging construction markets all over the world. As indicated earlier, the turnout of ICJVs keeps advancing around the globe at an alarming rate, specifically in the emerging countries. Mansfield (1999) posits that, among the motives of creating ICJVs are to partake in foreign projects; spread financial risk; uphold a foreign aura mainly when the domestic market has gone down; bring in outside expertise; access greater manpower from local partner; and to utilize existing geographical or regional base. Many are the motives when partners come together to form ICJVs as Mansfield (1999) have highlighted.

Parties involved in ICJV formation in most cases come with different objectives (Sridharan, 1997).  During the period of formation of the conditions of the ICJV agreement these objectives need to be addressed. According to Kwok et al (2000), a considerable time is spent during the phase of formation to identify the common compatible interests in the task-related areas of potential partners. Overseas firms that have exceptional organization-specific advantages which are strongly desired by the local partner, are typically in the position to negotiate a contract from a position of strength (Sridharan, 1997). Thus, the level of equity and resource contributions are determined depending on the bargaining power exercised, responsibilities of each partner are allocated, and lines of formal communications between the them and with external parties are established. Kwok et al. (2000) identified that, during the formation, the likelihood of achieving a formal joint venture agreement is dependent on several critical factors which come into play either to obstruct or improve the process and as a result increase or decrease. Clearness of support systems between related parties, negotiation, governance and policy making, profit and loss distribution, clarity of sharing of risks and liabilities, dispute resolution procedures, and composition of decision-making body among several others are the factors which come into play.

According to Bing et al. (1999), the three stages in the life cycle of a JV are start-up; followed by operation and then dismantle. From the time within which the firms contact themselves till the formation of IJV, in addition to any discussions and agreement reached constitute the start-up phase. The operation phase denotes the period of construction work being executed. The dismantle phase is the time frame in which most construction tasks come to completion, the clean-up stage, and any other agreement that may be reached to finalize matters (Bing et al., 1999). During the operation of the ICJV the related party selection and enterprise creation procedures set the basis of the association between the related parties (Mohamed, 2003). The unflinching communication and interaction characterized by a conducive atmosphere in a planned and effective decision-making process would result in the smooth running of ICJVs (Sridharan, 1997). Without a clear understanding of the future, IJVs wouldn’t survive. The related parties must find a way to streamline their core values and aspirations and when a change is the only option available, they should be able to reach a consensus (Doz, 1996).

Global construction designs are one of the bodies that comprises multinational participants from various upbringing. This includes political, economic, legal, and cultural perspective (Chan and Tse, 2003). Some of the associated shortcomings of the ICJV are as a result of circumstances inherent in the host country. In lieu of this, JV firms are prone to some risks that are inherent and restricted to their surroundings. Some of the associated shortcomings include accounting standard disparities, sharing of related parties’ financial challenges, trust issues amongst related parties, incompetence on the side of some partners, disagreement in management style and the likes (Bing et al., 1999). In order to mitigate the risk associated in the operations of ICJVs, it is recommended that the host firm should have a lasting relationship with the government and should be financially sound (Bing and Tiong, 1999). In order to ensure the smooth flow of activities among JV parties, it is advised that there should be an intense relationship management amongst them. One mandatory requirement that can necessitate a successful design process is the implementation of project management skills. A lot of consideration ought to be done when choosing a JV and its associates. This is needful because they would need to complement each other so as to fill the capability gaps of one another. This is an aspect of the scoping and needs analysis stage, which is an aspect of team development stage (Walker and Johannes, 2003). Ostler et al., (1998) ascertains a number of challenges attributed to construction firms by the host government agency when functioning in a global stage. These factors are nothing short of political, economic, structural, policy, environmental, market, and production factors. A wide range of these threats, which includes variations in law, pilfering, unusual interruption in approval and consistency and solvency is revealed in the review of literature (Zhi, 1995; Salzmann and Mohamed, 1999; Wang et al., 1999 cited in Mohamed, 2003).

# 2.2.1 International Construction Projects

Transmission of technology has become possible and more or less has become the order of the day because we are accustomed in a computer age era. We live in a global village where economic cooperation has become the order of the day. Intercontinental construction projects form part of the events that include international partakers from diverse political, legal, cultural, and economic settings. As Stebblings (1998) posits, international construction projects are only undertaken by at least one of the prospective construction team leaders. According to Chan and Tse (2003), the complexity of the construction industry as well as its multidimensional nature has caused the need to improve the situation, and that, almost every construction project is undertaken by a pool of construction personnel from developed countries. A number of authors (Lucas 1986; Ashley and Bonner, 1987; Aziz, 1992) have identified the motive for engaging international construction projects. That is, most foreign firms seek to obtain contracts overseas to increase their volume of foreign construction. Also, at the national level, the volume of international contracts contributes to a nation’s trade balance aside it balancing the growth of their firms contributing to their security through increased global activities. Han et al. (2005) posits that, this will mitigate the impact of the cyclic nature of their workload.

According to Levy (2000), generally, construction project defines the physical structure that is initiated by the designers’ drawings and gets transformed into finished products through a set of methods and processes. Thus, construction projects have different stakeholders involved in it, however, this time with stakeholders from both the local and international markets (i.e. ICJV). Chan and Tse (2003) posits that, collaboration between the concerned parties or stakeholders requires a clear project definition, and each set of objectives under the definition may be subject to changes as the project evolves. Parties to international construction projects are in most cases concerned with clarity of local laws and the interpretation of those contracts governed by local laws. Unlike the general construction projects, trans-global partnership calls for better cultural consideration and understanding in terms of personnel management by the concerned parties. Human problems are involved, like communication, language, and understanding of cultural differences. It is generally acknowledged that the contextual environment of a country or region also influences the construction sector of each jurisdiction. As Chan and Tse (2003) posits, friendship stands key and thus in understanding a people it is must that the foreign party identify itself with the local party or market for the successes of the entire construction project.

# 2.3 PROBLEMS FACING INTERNATIONAL PROJECT EXECUTION

All foreign enterprises are liable to host risks that have a connection with government to a certain degree. According to Root (1994), unsteadiness linked with variations in the policies of the hosting government in connection with transnational investments can straightforwardly influence business dealings. As El-Higzi (2000) discovered that the primary host government-related challenges faced by construction companies functioning in the multinational scene. They comprise environmental, structural, market, economical, policy, political and production factors. A critical reconsideration of literature as Wang et al. (1999) postulates identifies a various number of potential factors that poses risk, such as legislative changes, approval delays, creditworthiness, expropriation, and reliability and corruption. In the UK and Australia, a number of studies were carried out to indicate that economic and political stability of host countries is a key variable for working in international construction (El-Higzi, 2000). Also, native legislations relating to international investment may affect ICJVs agreement. For instance, some governments forbid total multinational ownership therefore causing hardships if the native partner should quit. Other governments may require that local personnel be placed in some or all management positions. Also, inappropriate legislation and frequent changes in current economic policies and commercial laws can affect the ICJV’s performance negatively especially in the execution of construction projects. Bilas et al. (2007) also added that, in cases where the goals of each partner in the ICJV are not clearly stated by the contract, the input of partners’  resources, their obligations and accountabilities, rights, nature of the job, profit share and its distribution method, conflict solving, and other key aspects of the investment can cause differences and lead to the failure of the joint venture.

The ICJV managerial team is confronted with major present challenges such as system, culture and relations development, for the purposes of decreasing the risk of a problem appearance in management. Challenges may seem to occur on the board level, an example can be in a case where two managers who were selected by the two partners having an equal stake, say 50:50 in the business have opposing stances, or in a case where there is a minority partaker who impedes the process with his veto power (Bilas et al., 2007). Researchers maintain that, similar challenge may even be encountered at the shareholder level, if some resolutions and issues are passed on from the board level and shareholders’ approval is needed, hence the challenges may occur when two owners have equal holdings or in the instance where a significant minority participant triggers his or her veto power. Turovski (2005) pointed out that, a large number of managers are of the same view that being in charge an entity in ICJV is more challenging as compared to running its subsidiary, in that, the organization is much more complicated and harder to control. Thus, it can be said that the ICJVs challenges are internal, not external. Talking to many board members, Turovski (2005) identified three major challenges in ICJVs management: Non-existence of control; inadequate trust between partners; and Uncertainty related to the likelihood of leaving the JV. The idea that the complete control in decision making will be replaced with divided control most often than not threatens managers. This is a clear indication of a problem the management faces, particularly in the instance where the assets that are contributed to the business are still generally priceless to the mother company. Secondly, a large number of heads listed inadequacy of trust as part of the leading challenges faced by the businesses that engage in joint venture agreements. In the instances where increased stress, as well as, challenges occur amongst similar parties in the agreement, managers mostly use huge or large sums monetary and the scarce resource of time in the quest to resolve the situation. In some severe situations, disparities have been found to go all the way to lawyers and arbitrators. Lastly, according to Turovski (2005), choosing to have a well-defined and laid out regulation of dissolution, and suitably structuring it, is mostly very demanding. Top officials will like to have a clear procedure and method of exiting, in the case where the situations become different. However, the effort to establish what is just and moderate, determined at the inception of the investment, may in the long run end up being inappropriate when it is time to dissolve the organisation.

A number of writers are also in agreement to the fact that most of the problems faced by managers in IJVs happen due to the misunderstandings, eventually causing bad and wrong organisational habits and practices, which at the long causes IJVs to fold up. According to Fey and Beamish (2000), it was observed that there were four major sources of misunderstandings in relation to joint venture agreements:

- Cultural differences between partners

- Aspiration for control and autonomy

- Own parent company needs

- Different objectives of parent companies

A primary reason for this challenge affecting all joint venture agreements is the presence of many mother companies, that may have contrasting and conflicting opinions: on the expansion frequency and growth rate of the organisation, on the types of produce or specific markets or population to target, the type of organization they should aspire to become, and in some cases, the factors that determine good, bad, right or wrong management etc. Specifically, two sections are critical in considering the challenges of the presence of more mother organisations. The foremost section can be found on the board. International companies that are involved in joint ventures have boards that comprises of agents assigned by the mother company to represent them, which causes challenges as a result of conflicting aims and goals, regulations and/or the value systems. This can amount to hampered and slow decision making, amongst a number of other things. Also, there is quit I difference between other forms of business organizations and joint ventures, specifically, in the area pf the politics of the human capital. A number of joint venture businesses have their top officials, performing general and functional roles, coming directly from their mother institutions. In actual fact, there are a tremendous number of situations where two general directors, one each from the two mother institutions, are selected to ensure the interests, aims and objectives of their mother institutions are achieved. The major cause of that is the absence of trust between the two parties. This can therefore result in under satisfaction and poor and/or low efficiency in the company. However, certain joint venture businesses can be easily managed. This can be found in the case of very huge jobs or projects, where a mother institution is nothing but a source of resources and has very minimal knowledge in relation to the project or job and the other institution, being an expert in that field, actually performs the role of  managing the joint organisation. In the study of construction joint venture agreements, a critical issue that must be considered and answered is the problematic question of trust amongst mother bodies, whose definition can be a degree of positive expectations in relation to the other party. Bamford et al. (2004) suspected the existence of  a positive correlation between the trust level and the level of efficiency of the joint organisations. The work of Fey and Beamish (2000) proved that a highly positive relationship exists between the issue of trust and a flourishing organisation carried out on international partnerships. Quite interestingly, it should be noted that this study uncovered that, trust has a lot to do with the culture of people, therefore cultural roles are very much not the same in various geographical regions. In the work of Madhok (1995), it was indicated that trust definitely has a part to play if an organisations efficiency is to grow or increase, grows the value of the asset thereby causing a positively correlation to the success of the joint entity. Büchel (2003) lists five “mine fields” which may damage the cordial ties between business partners and must be prevented so as to totally achieve the maximum of this form of partnership. Namely;

- No clarity in the functions of partners

- Ununiformly shared risk and benefits

- No trust between joint organisational heads

- Unpreventable crisis

- Non-existence of exit mechanisms

The primarily critical problem which should be taken care of before agreeing on any conclusive agreement is the method and procedure in sharing and apportioning of the value that the joint body makes on the mother body. An important matter in relation to a long-run partnership is to clearly make available an honest, fair and unbiased risk and benefit ratios and proportions.

# 2.4 Challenges and Risk on Project Performance

The definition of project performance can be the magnitude of realizing the aims and objectives of an already defined project. Considering the construction industry, IJVs are basically established in order to carry out project-based activities. A section of the success in operation of an IJV in the construction industry can be defined in terms of the success of the job. Often, the most frequent cited aims of a project are connected to time, budget, and functionality/quality considerations (Handa and Adas, 1996) and also with the satisfaction of the client being considered (Ashley et al., 1987). The performance of projects can be is described as an objective measure of project targets including completion of the project on schedule, within budget, in good quality, and with maximum client satisfaction. ICJVs include stakeholders from various cultural backgrounds, with a variety of languages and behavioural patterns. One major worry of construction professionals carrying out in multinational projects, is their inability to come to terms with multinational cultures, ethical behaviours, and languages (Bilas et al., 2007). A number of the project performance challenges can be linked to the difference in cultures in existence at the national and organizational levels. Variety in cultures mostly end up in a breakdown in communications which sometimes creates mistrust, and may even cause members to disengage in the JV. Apart from the issues relating to culture, the contrast in the styles of management of the two participating groups may bring about disagreements and crises, and not resolving of those disputes will at the end amount to affecting the eefficiency of the JV and certainly the construction project (Fey and Beamish, 2000). Even though certain organisations can collaborate with the same partner in various jobs, construction IJVs are classified as project-based instead of continuous collaborations. Different from various other industries, construction is a complex blend of disparate needs, skills and techniques that are difficult to coordinate. It is widely accepted that a construction project is subject to more risks than other business activities because of its complexity (Büchel, 2003). The risks involved with construction companies may be split into those that are related to the management of internal resources and those that are prevalent in the external environment. Internal factors are relatively more controllable and vary from project to project. External risks are relatively uncontrollable, but they need to be continually scanned and forecasted in order to develop company techniques for controlling and improving their impact (El-Higzi, 2000).

The successes of IJV projects are defined in both objective and subjective terms: “project performance” is an objective indicator that measures the extent to which project objectives are realized in terms of schedule, cost, quality, and client satisfaction, whereas “overall satisfaction” is a subjective indicator that measures the performance of the IJV as perceived by an IJV partner. According to Nielsen (2002), risks effects on the performance of ICJV include: a) cultural distance that lead to in most cases communication problems, which hinder knowledge exchange and interorganizational learning; b) managerial conflicts due to misunderstandings, which lead to additional costs; c) influence partner firm approaches to conflict resolution, which adversely impact operations; and d) erosion of applicability of certain partner competencies, which decrease the potential benefits from cooperation. Also, the disparities in the cultures of organisations separate IJV parties on the basis of their practices of management. These are believed vital for the running of their representative entities. In the case where organizations in an IJV are different in their operations, these disparities can cause problematic behavioural patterns, resulting in infightings and interaction issues and difficulties. Stakeholders having different organizational structures may use the resource of time and energy to build communally friendly managerial practices and procedures in order to enhance the interaction and which can lead to increased costs and much more mistrust (Park and Ungson, 1997). Investigating a great number of IJVs, Pothukuchi et al. (2002) discovered that “the presumed negative effect from partner dissimilarity on IJV performance originates more from differences in organizational structures than differences in national culture.” In another study of alliances, Brown et al. (1989) concluded that “large differences in partners’ organizational structure can have a significant negative influence on IJV performance.”

2.5 STRATEGIES FOR BETTER PLANNING AND EXECUTION OF INTERNATIONAL JOINT VENTURE CONSTRUCTION PROJECTS

If an entity from an international joint venture starts an undertaking and runs fruitfully, and grows stabile relations, everything will be carried out habitually and without greater challenges. But the partnership’s real test will occur if an unforeseen eventuality occurs. That could be a little bit problematic to the partners. Such a thing could be prevented from occurring by allowing ceaseless flow of information within the related parties, which partially requires negotiations with a parent company on the matter of proprietary rights (Bilas et al., 2007). When the disputes grow beyond the certain level, and stakeholders find that they cannot work together anymore, it is necessary to have formal exit mechanisms, in order to prevent very costly and prolonged court cases. Even though there are a number of disparities among the company which is completely owned and an entity which is a joint venture, Bamford et al. (2004) find that some of the rules of good governance can be applied to both:

- Name at least one external director who would be responsible to promote the joint venture’s interests as a whole, especially when the parent construction companies have opposite goals.

- Name executives or an influential board president. Company should use a highly-specialized joint venture governance model, in which the board members would be individual experts for specific areas, like legal issues, production, and finances.

- Employ an external audit. Large joint ventures do a fairly good job of generating basic financial and operating data. However, they tend to be less effective at understanding their own economics from the perspective of their corporate parents and at generating second-level management data so essential to grasping the real issues and prospects of a business.

- Create a real challenge process. Too often, and for many reasons, international joint ventures are shielded from thorough performance scrutiny. For one thing, they exist on the corporate periphery, outside their parent’s normal reporting process. Likewise, their parent companies may be reluctant to invest scarce managerial resources in efforts to oversee them properly. Nonetheless, a company making a large investment in a joint venture should oversee it with the same level of intensity that would be devoted to other business of the same size. One important consideration is how to create a rigorous reporting and review process that engages all of the corporate parents without subjecting the joint venture to “double jeopardy”.

Further, Zhang and Zou (2007) indicates that partners prefer to set up a joint venture for risks cases. That is, the two firms involved in this case set up the joint venture so as to finish one project and both partners stand risk-averse. To focus the effect of the background risk on the choice of cooperation means under different conditions, the project can be divided into two subprojects clearly. Both partners undertake their project risk which belong to their subprojects. This form of strategy is called separated type joint ventures; as it provides efficient incentive to the partners to deal with their risks. Also, Hofstede (1991) developed a pioneering and widely accepted classification scheme which breaks national culture into the following five dimensions. He stated that,” power distance focuses on the degree of equality or inequality between people in a country’s society. It measures inequalities in income distribution and the opportunities provided to people. Individualism-collectivism focuses on the degree the society reinforces individual or collective achievement and interpersonal relationship. Masculinity-femininity focuses on the degree the society reinforces the traditional masculine work role model of male achievement, control, and power. Uncertainty avoidance focuses on the level of tolerance for uncertainty and ambiguity within the society, the extent to which rules are obeyed and risks are avoided. Long-term orientation focuses on the degree the society embraces long-term devotion to traditional, forward thinking values. Several researchers reported that differences in national cultures are a source of poor communication, inadequate cooperation, lack of commitment, and ineffective conflict resolution between IJV partners (Harrigan, 1988; Parkhe, 1991; Mohr and Spekman, 1994). These problems occur because of the dissimilarities of partners’ interpretation of and responses to strategic and managerial issues.”

# CHAPTER THREE

# RESEARCH METHODOLOGY

# 3.1 INTRODUCTION

This chapter expounds on the processes executed to achieve the aim and objectives of the project. The next level in the study after identifying the research question and review of literature is selecting the methodology that is most appropriate in addressing the issues in the research (Blumberg et al., 2005). Collis and Hussey, (2013) has emphasized that design process from hypothetical testing to data collection and data analysis is the overall approach to research methodology, therefore methodology employs the tactics of discovery how to go about finding out what we believe is true (Christou et al., 2008). This chapter focus on the framework of the study, research design instrument, data collection and data analysis.

# 3.2 PHILOSOPHICAL POINT OF THE RESEARCH

Various factors influence the philosophical disposition of any research.  These philosophical patterns have to examine as to the research instrument to employ for the research (Christou et al, 2008). These philosophical patterns are defined as an approach to viewing natural phenomena that comprises a set of philosophical assumptions that guide one’s tactics to inquiry (Polit and Beck, 2004). Research philosophy entails development of knowledge and the characteristics of that knowledge. Accordingly, philosophical paradigms such as ontology, epistemology, axiology and methodology assumptions need to be accessed in detail since the shape the choice of the research (Christou et al, 2008). Focal concerns for social research is on ontological and epistemological stand points of view and are discussed below.

Ontology refers to what constitutes the ‘real’ world and understanding its existence which is sovereign to our knowledge (Marsh and Stoker, 2002).  Fitzgerald and Howcroft (1998) states that ontology has two positions thus relativist and realist positions. Realist believe that outside world consists of pre-existing hard and tangible structures and these structures exist independently of one’s capacity to acquire knowledge. Realist position is practical and not abstract or idealist views. The relativist tailors to multiple existence of realities by an individual’s mind construct (Fitzgerald and Howcroft, 1998). The realist position is adopted for the knowing the factor and requirements for organizing a procurement unit and its influencing factors.

Epistemology refers to valid knowledge constituents and how these can be achieved. This position can be either positivist (objective) or intepretivist (subjective) as referred by Streubert and Carpenter (1999). Positivist are of the view that the social world exists as an external entity and its attributes objectively accessed with scientific methods rather than being concluded subjectively through intuitive activities (Easterby-Smith et al, 2008; Saunders et al, 2012). Positivists claim that the facts can be presented independently of the observer so that research is totally objective and accurate (Fellows and Liu, 2008).

Intepretivist position holds the ideology that a person’s reality is deduced from observations, perceptions and modified by socialization is likely to be different from the other person (Fellows and Liu, 2008). This position believes that people description of reality is based on the language they understand (subjective) and not what exist objectively. Intepretivist do not obviate the objectivity of reality rather their assertion is that reality cannot be understood outside the spheres of culture and values. According to Creswell (2007), in interpretative research the opinions of participants are mostly depended on for the situation under study. At the epistemological level the positivist position is employed for the research to understand what factors was considered in setting up the procurement unit and this will enable the researcher appreciate the considerations and influences in setting up the procurement unit.

Positivism adopts a clear quantitative approach to investigating phenomena (Creswell, 2009; Greener, 2008). Positivist argue that this research based on this approach can be “value free and objective” rather than subjective and value-laden (Greener, 2008).

# 3.3 RESEARCH STRATEGY

Considering the philosophical position of this study thus positivist on one hand, and the nature of the problem identified in literature as well as the pilot interview on the other hand, survey strategy emerges as more appropriate. Creswell (2005) defined a survey research as an orderly gathering of information for the purpose of understanding and/or predicting some aspect of the behaviour of the population of interest. Surveys are classified under longitudinal and cross-sectional studies. Survey was appropriate for this study because of the following reasons: i) it allows researcher to solicit for data about situations, practices or views at a particular time frame through questionnaires or interviews; ii) it also permits a researcher to study more variables at one time; iii) survey allows the use of quantitative analytical techniques to draw conclusions. Furthermore, survey is the strategy that responds suitably to all the research questions which are of the type of what, who, what, where, how much and how many (Saunders, et al., 2012). The use of Likert scales which are a widely accepted way of collecting data for studies was used. Further, the researcher gathered information from respondents by means of questionnaires, emails, and face to face interaction in the case of a survey research strategy.

# 3.4 RESEARCH DESIGN

Saunders et al. (2012) define research design as the general plan of providing answers to the research questions that have been asked as well as gathering and analyzing the collected data. Thus, it explains the overall plan of the research. Burns and Grove (2003) added that, it is the general process of undertaking the research. Through a well formulated research design, researchers are able to gain maximum control over several thwarting factors that undermines the validity of the study. According to Creswell and Clark (2017), selecting appropriate research design is based on the nature of research problem or issue being addressed, the experience of the researcher, and the respondents for the study. Two types of research designs are advanced: Descriptive Research Design and Correlational Research Design. Descriptive research design is designed to give a clear picture of a situation as it naturally happens (Burns and Grove, 2003). Thus, situations are usually described using descriptive research design. Profile of persons, situations or events are the basic object of measurement in descriptive research. It is also employed for the justification of current practices, make judgement and to develop theories. This also deals with clarification of the existence of a relationship that exist between two or more aspects of a situation or phenomenon as well as forecast future happenings. This is mostly considered by research questions or hypothesis which specifies the direction and nature of the relationship between the variable being examined. Correlational research design comes in where there is the need to possibly investigate the relationships among variables without trying to influence those variables. However, the degree of relationship between the variables is of much concern. Correlational study deals with measuring two variables and then determining the degree of relationship that exist between them (Christensen et al. 2011). Generally, correlational research design is incorporated into quantitative research methods, and effective in enabling us accomplish research objectives of description and prediction (Christensen et al. 2011). Further, correlational research design normally involves multiple variables that helps to improve the researcher’s ability to make predictions. The study employed a descriptive research design to justify the current practices, make judgement and to develop theories. This also deals with clarification of the existence of a relationship that exist between two or more aspects of a situation or phenomenon as well as forecast future happenings.

# 3.5 RESEARCH METHOD

The research method adopted for this study was purely quantitative method, to address the research questions. This method gives a quantitative or numeric description of trends, attitudes, or reactions of a population by studying a sample of that population (Creswell, 2009). This study adopted a quantitative research design to examine the objectives. These are justifications why quantitative research was adopted for this research, gathers accurate data plus study relations between facts as well as relations in agreement with theory, this was done using many data gathering performances as well as analytical methods. Preceding to the prompting of the initial study, a wide-ranging collected works review was embarked on. The literature review shielded extensively on matters constructing rounds in the discipline; particularly a broad synopsis on the Ghanaian construction industry as well as the problems governing international joint venture construction project execution in Ghana and the outcome/implication of the challenges on project performance in Ghana. Strategies for better planning and accomplishment of worldwide joint venture construction ventures in Ghana.

# 3.6 DATA SOURCES

The researcher employed primary sources of data. The main purpose of the study is to gather info that can be analyzed, to enable interpretation, and aided the investigator to grow unique information such as eye witness accounts, and personal observations.

# 3.7 POPULATION AND SAMPLING SIZE

With the main focus of the study, identifying the challenges facing international joint ventures in the execution of construction project in Ghana, the survey population comprise Ghanaian construction companies that had participated in ICJVs with foreign companies. A list of targeted respondents was drawn up from the records maintained by Ghana Investment Promotion Centre (GIPC). According to the GIPC records, a total of 166 projects were registered with JVs arrangement from January 2006 to December 2016. However, out of the 166 registered projects, 149 (89%) were construction related activities. This list served as the sampling framework.

# 3.7.1 Sampling Techniques and Data Collection

The study generally followed the recommendation of Dillman (2007) to ensure a high response rate. Purposive sampling technique was used in selecting survey respondents. First and foremost, before the questionnaire distribution, the researcher contacted potential respondents through phone calls or face-to-face meetings and explained the background of the study and importance of their participation. Further, those that the researcher could not locate directly, the questionnaire was sent to their respective mails addresses to elicit information pertaining to area under study and contingent on the objectives. It is noted that about 149 international joint construction venture projects have been executed, out of which 82 of these joint venture projects were executed in the Accra metropolis, and with their offices located there as well. Therefore, this formed the sample size for the study. For every office or respondents contacted for the study, priority was given to senior members of organization. The focuses on these key informants is that, they are the top management decision-makers and have knowledge of the firm, familiarity with the environment of the firm, access to strategic information and knowledge on the performance of the organization (Zhou et al. 2010). Either the local, or the foreign partner whom the researcher easily had a direct hand on was administered with questionnaire. In each firm that was visited, two people was given with questionnaire to fill out.

# 3.8 Questionnaire Design and Development

The questionnaire was planned and organized to be respondent-friendly in order to enhance the participation of a lot and in as a result, increase the rate of response. The questionnaire was designed using plain language devoid of ‘technical’ words, except where used it was explained to the respondents. Apart from the use of simple language, the questionnaire was specifically designed to contain close-ended questions. The layout and format of the questionnaire were carefully considered as they impact on the response rate. Instructions were given at the beginning of every major part for filling the questionnaire. The questionnaire was in two main sections, Parts A and B. The Part A focused primarily on the demographics of the respondents and as such requested the background information of the respondents. Surveys have proved the importance of demographic parameters or background information, specifically in quantitative analysis.

The Part B was based on the survey objectives and therefore was based on the literature review with relation to the problems governing international joint venture construction project execution, the outcome/implication of the challenges on project performance and strategies for better planning and carrying out of foreign joint venture construction projects in Ghana.

# 3.9 Data Analysis

The final questionnaires were amended to guarantee wholeness, uniformity and readability. Once the data had been checked, they were arranged in a format that enabled easy analysis. The retrieved questionnaire was aggregated into larger units and were processed and entered into the Statistical Packages for Social Sciences (SPSS version 23). The SPSS software was employed to organize the survey findings and to cross-tabulate the relationships between the variables. To elucidate the discussion in this discipline, the data obtained was presented graphically and in tabular form. Information involving the background of respondents are presented in pie charts and bar graphs. Successively, the results are analyzed statistically descriptive statistics (frequencies and percentages)

# 3.10 Ethical Consideration

The study will consider some broad ethical areas including voluntary participation, informed consent, confidentiality and anonymity. The participants from whom the data will be gathered for this study will not be coerced or put under any form of pressure to participate in the study. Informed consent stating who the researcher is, what the study is all about and the desired outcomes and potential risk for being part of the study will be taken from participants either in written or verbally. To ensure anonymity, the identity of participants will not be required neither will any clue be given in the presentation of the results to reveal the identity of any participant. This was to ensure the confidentiality of each participant.

# 3.10.1 Reliability and Validity

Validity refers to the degree which a test or an instrument measures or performs the assignment it’s meant for. For qualitative study i.e., semi-structured interviews no set standards exist for evaluating the validity or authenticity of conclusions but there is the urgency of careful consideration to evidence and methods on which conclusions are based in this research. Criteria for assessing individual information can be based on three (Becker, 1958):

- How creditable the informant is?

- Were the statements made in response to the researchers or were they spontaneous

- How does the presence or absence of the researcher or the researcher’s informant influence the actions and statements of the other groups?

All these criteria will be carefully considered and observed for the interview process to help validate the data collected. The information that are gathered will be transcribed and returned to the respondents for concurrent confirmation on the accuracy and precision of the content gathered

# CHAPTER FOUR

# SURVEY RESULTS, DATA ANALYSIS AND FINDINGS

# 4.1 INTRODUCTION

This section analyses the findings of the study, displays the results and discusses the main research objectives. The first section describes the sample characteristics and descriptive statistics. The succeeding sections presents results and discussion of the main research findings. It discusses the respondent’s views on the problems governing international joint venture construction project execution in Ghana, determine the outcome/implication of the challenges on project performance and the strategies for better planning and execution of international joint venture construction projects in Ghana. The analysis saw the adoption of simple descriptive statistics like, percentages, and the relative importance index. The results have been presented in tables and interpreted accordingly.

# 4.1.1 Sample Characteristics

Using purposive sampling and distributing one (1) questionnaire per each firm, out of the 82 questionnaires distributed, 65 questionnaires representing 80% were completed and retrieved. Subsequently, considering the deletion of outliers and missing values due to incomplete data, it was noted that all the 64 completed questionnaires were considered valid for the analysis. The analysis of the outcomes is founded on these number of questionnaires received and subsequently formed the bases of the discoveries of this study. The high response rate of 80% can be credited to the fact that questionnaires were administered personally to respondents and sequential follow-ups were made afterwards.

# 4.2 DESCRIPTIVE STATISTICS (DEMOGRAPHIC DATA)

# 4.2.1 Organizational Role

Nearly, 17% were Project Managers (N=11), 20% were Engineer (N=13), 15% were Contractor (N=10), 9% were Architect (N=6), 3% were Foremen (N=2), 14% Quantity surveyors (N = 9) and 21% were construction managers (N = 14). The respondent position is vital to ensure some degree of reliability of the data. The high representation of quantity surveyors, contractors, project managers etc. was inevitable as these professionals are very key and usually engage in the construction activities. This makes them credible and reliable source of information which is needed for this study.

Table 4.1: Organizational Role

| Item | Frequency | Percentage (%) |
| --- | --- | --- |
| Quantity Surveyor | 9 | 14% |
| Construction Manager | 14 | 21% |
| Project Manager | 11 | 8% |
| Contractor | 10 | 15% |
| Engineer | 13 | 20% |
| Architect | 6 | 9% |
| Foreman | 2 | 3% |
| Total | 65 | 100 |

Source: Field Survey, 2018

# 4.2.2 Educational level of respondent

Table 4.2 below shows that Majority of the respondents of the survey were either Holders of PhD, Master’s Degree (MSc, MPhil, and MBA), Bachelor of Science or Higher National Diploma. 6% of the Respondents were holders PhD, 37% are holders of a Master Degree, 46% holds a Bachelor’s Degree, and whiles 11% were holders of Higher National Diploma. The results indicate that majority of the respondents are highly educated and well qualified. The respondents work for well-established firms that have a lot of experience. They also fall within the targeted group the researcher intended to study.

Table 4.2: Educational Level

| Item | Frequency | Percentage (%) |
| --- | --- | --- |
| Higher National Diploma | 7 | 11% |
| Bachelor’s Degree | 30 | 46% |
| Master Degree | 24 | 37% |
| PhD | 4 | 6% |
| Total | 65 | 100 |

Source: Field Survey, 2018

# 4.2.3 Experience (Number of International Construction Joint Venture) participated with foreign companies

Respondents experience regarding the number of ICJV projects participated are represented in the table 4.3. The responses show that, 10% have participated in less than 5 projects, 28% have participated in 5-10 projects, 46% have participated in 11- 15 projects and 16% have also participated in 16 and above international construction joint venture projects. The respondents have worked on ICJV projects and have obtained considerable experience and therefore falls within the targeted group the researcher intended to study.

Table 4.3 Experience in ICJV projects participated

| Item | Frequency | Percentage (%) |
| --- | --- | --- |
| Less than 5 projects | 7 | 10% |
| 5- 10 projects | 18 | 28% |
| 11 – 15 projects | 30 | 46% |
| 16 and above projects | 10 | 16% |
| Total | 65 | 100 |

Source: Field Survey, 2018

# 4.2.3 Working Experience of Respondents in the Construction Industry

The intention of this question was to identify the level of experience of the respondents in the construction industry since how long they have been in the construction industry will affect the quality of the response given. From the table, bulk of the respondents have been in the building industry for more than 6 years representing 88% (N=16+24+17). Approximately, 12% indicated level of less than 5 years’ practice in the building industry. Accordingly, it can be deducted that, they have had a lot of experience in the Ghanaian construction industry and for that matter are capable of giving in-depth information on the issues under discussion. And the balances of a variety of levels of experience will therefore enable a generalized and realistic view as far as this research is concerned.

Table 4.4: Working Experience of Respondents in the Construction Industry

| Item | Frequency | Percentage (%) |
| --- | --- | --- |
| Less than 5 years | 8 | 12% |
| 6 to 10 years | 16 | 26% |
| 11 to 15 years | 24 | 38% |
| Above 16 years | 17 | 24% |
| Total | 65 | 100 |

Source: Field Survey, 2018

# 4.3 ANALYSIS AND DISCUSSION OF MAIN OBJECTIVES

# 4.3.1 Problems facing international construction joint venture project execution

From Table 4.5 below, using relative importance index to determine the problems governing international construction joint venture project execution, Policy changes in mother institutions disturbing the project was rated first with a mean and an RII value of 4.38 and 0.912 correspondingly.

Other factors in other of ranking are Erosion of applicability of certain partner competencies, Expending time and energy to come out with equally responsive managerial practices, Inheriting a partner’s financial problems, Differences about the allocation of staff and the strategic arrangement of project members to form a team pecking order, Misunderstanding of foreign cultures, ethics, and languages, Regular variations in current economic policies and commercial laws, Fluctuations in host government policies towards foreign investment, Technology-transfer disputes, Differences in national cultures between ICJV partners, hitches arising as a result of loggerheads on work to be done. Having divergent views about accounting standards being used, trust issues among relate parties employees, Insecurity related to the possibility of leaving the Joint venture and Lack of trust between partners. The least ranked problems are Cultural differences and Lack of appropriate legislation which had mean of 3.95 and RII values of 0.712.

These problems as ranked by respondents conforms to that of literature. According to Root (1994), uncertainty linked with fluctuations in host government policies regarding overseas investment can straightly affect professional operations. As El-Higzi (2000) brings on board some host government-related threats faced by construction companies working in global platform. A review of the literature as Wang et al. (1999) postulates stated that”a wide range of these risk factors, such as changes in law, corruption, delay in approval, expropriation, and reliability and creditworthiness.” In studying the studies conducted in the UK and Australia, it is noted that, economic and political stability of host countries is a key condition for working in overseas construction (El-Higzi, 2000). Bilas et al. (2007) also added that, in cases where objectives of each stakeholders in the ICJV are not clearly demarcated by the contract, partners’ contribution in resources, their obligations and responsibilities, rights, nature of the job, profit share and its distribution method, conflict solving, and other key aspects of the investment can cause disagreements and the joint venture collapse. Turovski (2005) pointed out that, majority of managers agree that managing the entity in ICJV is far challenging compare to running its subsidiary, in that, the organization is much more complicated and harder to control. Thus, it can be said that the ICJVs challenges are internal, not external. Talking to many board members, Turovski (2005) identified three major challenges in ICJVs management: Lack of control; Lack of trust between partners; and Insecurity related to the possibility of leaving the JV. Which are all supported by literature and are considered as a critical problem governing international construction joint venture project execution. Conclusion can be drawn from the fact that these problems governing international construction joint venture project execution are critical and strategies to mitigate these problem needs to be employed. Objective one, that is, to identify problems governing international construction joint venture project execution was achieved as respondents responded to the problems identified from literature.

Table 4.5 Problems facing international joint venture projects

| No. | Problems | Mean | RII | Ranking |
| --- | --- | --- | --- | --- |
| 1 | Policy changes in parent companies affecting the project | 4.38 | 0.912 | 1st |
| 2 | Erosion of applicability of certain partner competencies | 4.31 | 0.882 | 2nd |
| 3 | Expending time and energy to establish mutually agreeable managerial practices | 4.29 | 0.901 | 3rd |
| 4 | Inheriting a partner’s financial problems | 4.25 | 0.872 | 4th |
| 5 | Disagreements about staff allocation and positions in the project team hierarchy | 4.21 | 0.885 | 5th |
| 6 | Misunderstanding of foreign cultures, ethics, and languages | 4.33 | 0.854 | 6th |
| 7 | Frequent changes in current economic policies and commercial laws | 4.24 | 0.865 | 7th |
| 8 | Changes in host government policies towards foreign investment | 4.35 | 0.891 | 8th |
| 9 | Technology-transfer disputes | 4.34 | 0.892 | 9th |
| 10 | Differences in national cultures between ICJV partners | 4.33 | 0.893 | 10th |
| 11 | Disagreement on work allocation to be done | 4.30 | 0.864 | 11th |
| 12 | Disagreements on accounting standards used | 4.28 | 0.861 | 12th |
| 13 | Distrust among partner employees | 4.25 | 0.852 | 13th |
| 14 | Insecurity related to the possibility of leaving the JV | 4.29 | 0.826 | 14th |
| 15 | Lack of trust between partners | 4.12 | 0.798 | 15th |
| 16 | Lack of management competence | 4.10 | 0.734 | 16th |
| 17 | Cultural differences | 3.95 | 0.712 | 17th |
| 18 | Lack of appropriate legislation | 3.86 | 0.675 | 18th |

Source: Field Survey, 2018

# 4.3.2 The implication of the challenges on project performance in Ghana

The data in Table 4.6 below represent the view of respondents on the implication of the challenges of International joint venture construction on project performance in Ghana. The project performance criteria highlighted here are; cost, time, quality and safety. Respondent were then ask to group the challenges under these four criteria. The response shows that, inheriting a partner’s financial problems, having disagreements about accounting standards and recurrent variations in present economic policies and commercial laws have a major implication on cost. Among these cost implications to project performance, the highest ranked is inheriting a partner’s financial problems with a frequency of 27 of the respondents representing 41.54% and this was supported with literature (Handa and Adas, 1996; Ashley et al., 1987). Expending precious time and energy before consensus could be reached on management preferred way of doing things, unusual fluctuation in economic policies and laws. Changes in policies by mother companies causing a dent on the project, technology-transfer disputes, Differences in national cultures between ICJV partners and differences on sharing of work to be done were classified as challenges of ICJV that have effect on time. The highest ranked under this category is expending hours to establish management way of doing things with a frequency of 19 and a percentage of 29.23%. Lack of management competence, erosion of applicability of certain partner competencies, technology-transfer disputes, misunderstanding of foreign cultures, ethics, and languages and divergent views on work to be done were classified as challenges of ICJV that have effect on quality performance of a project. The highest ranked under this category is Lack of management competence with a frequency of 21 and a percentage of 32.31%. Disagreements about staff allocation and positions in the project team hierarchy, Insecurity related to the possibility of leaving the JV and Lack of trust between partners were classified as challenges of ICJV that have effect on safety performance of a project. These were all supported by literature (Bilas et al., 2007; Fey and Beamish, 2000; Nelson, 2002.

Table 4.6 Implication of ICJV challenges on project performance

| VARIABLES | COST |  | TIME |  | QUALITY |  | SAFETY |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Freq | % | Freq | % | Freq | % | Freq | % |
| Inheriting a partner’s financial problems | 25 | 41 |  |  |  |  |  |  |
| Having disagreements about accounting standards | 21 | 32 |  |  |  |  |  |  |
| Fluctuation in current economic policies and commercial laws | 17 | 26 |  |  |  |  |  |  |
| Expending time and energy to establish mutually agreeable managerial practices | - |  | 19 | 29 |  |  |  |  |
| Frequent changes in current economic policies and commercial laws | - |  | 16 | 24 |  |  |  |  |
| Policy changes in parent companies affecting the project | 1 | 0.5 | 12 | 18 |  |  |  |  |
| Technology-transfer disputes |  |  | 8 | 12 |  |  |  |  |
| Differences in national cultures between ICJV partners |  |  | 6 | 9 |  |  |  |  |
| Disagreement on allocation of work to be done |  |  | 4 | 6 |  |  |  |  |
| Lack of management competence |  |  |  |  | 21 | 32 |  |  |
| Erosion of applicability of certain partner competencies |  |  |  |  | 17 | 26 |  |  |
| Technology-transfer disputes |  |  |  |  | 12 | 18 |  |  |
| Misunderstanding of foreign cultures, ethics, and languages |  |  |  |  | 9 | 13 |  |  |
| Disagreement on allocation of work to be done |  |  |  |  | 6 | 9 |  |  |
| Disagreements about staff allocation and positions in the project team hierarchy |  |  |  |  |  |  | 30 | 47 |
| Insecurity related to the possibility of leaving the JV |  |  |  |  |  |  | 25 | 38 |
| Lack of trust between partners |  |  |  |  |  |  | 10 | 15 |

Source: field data, 2018

# 4.3.3 Strategies for better planning and execution of international joint venture construction projects.

From table 4.7 below, using relative importance index to determine the strategies for better planning and execution of international joint venture construction, dividing projects into subprojects for each partner to undertake their project risk clearly was rated first with a mean and an RII value of 4.54 and 0.811 respectively. The other strategies in order of rank are managers should expand the data movement inside a joint venture, Interpret and respond to strategic and managerial issues, Name external director to encourage the joint venture’s interests as a whole, Name executives or an influential board president, Develop a pioneering and widely accepted classification scheme to breaks national culture into dimensions and also have formal exit mechanisms in order to avoid expensive and long lawsuits. The least ranked factors are Employ an external audit and create a real challenge process. These factors were also support by (Bilas et al., 2007; Bamford et al. 2004; Zhang and Zou, 2007; Hofstede, 1991; Harrigan, 1988; Parkhe, 1991; Mohr and Spekman, 1994) as indicated in literature. This shows that, the identified strategies are very vital and necessary to help mitigate the problems governing international construction joint venture project execution.

Table 4.7: Strategies for better planning and execution of international joint venture construction projects.

| No. | Strategies | Mean | RII | Ranking |
| --- | --- | --- | --- | --- |
| 1 | Divide projects into subprojects for each partner to undertake their project risk clearly | 4.54 | 0.811 | 1st |
| 2 | Manager should improve the information flow inside a joint venture | 4.50 | 0.806 | 2nd |
| 3 | Interpret and respond to strategic and managerial issues | 4.36 | 0.801 | 3rd |
| 4 | Name external director to promote the joint venture’s interests as a whole | 4.31 | 0.754 | 4th |
| 5 | Name executives or an influential board president | 4.30 | 0.726 | 5th |
| 6 | Develop a pioneering and widely accepted classification scheme to breaks national culture into dimensions | 4.24 | 0.705 | 6th |
| 7 | Have formal exit mechanisms, in order to avoid expensive and long lawsuits | 3.63 | 0.694 | 7th |
| 8 | Employ an external audit | 3.59 | 0.681 | 8th |
| 9 | Create a real challenge process | 3.43 | 0.576 | 9th |

Source: Field Survey, 2018

# CHAPTER FIVE

# SUMMARY OF FINDINGS, CONCLUSION AND RECOMMENDATION

# 5.1 INTRODUCTION

This chapter completes the report by summarizing the problems, objectives addressed and lessons uncovered through the research. The discussion is given on how the important study objectives were achieved. This is then followed by the main conclusions of the research findings. The chapter is subsequently brought to a close with recommendations for the adoption of the findings, establishing its usage and preposition for future research.

# 5.2 SUMMARY OF FINDINGS

This research was instigated with the primary aim of the study to identify the challenges facing international joint ventures in the execution of construction project in Ghana. In pursuing this aim, three objectives were set out. The achievement of each of the three research objectives is set out in the following subsections.

# 5.2.1 Problems governing international joint venture construction project execution

The study reveals that, Policy changes in parent companies affecting the project was ranked as a major problem governing international joint venture construction project execution in Ghana.

Other factors in other of ranking were Erosion of applicability of certain partner competencies, Expending time and energy to establish mutually agreeable managerial practices, Inheriting a partner’s financial problems, Disagreements about staff allocation and positions in the project team hierarchy, Misunderstanding of foreign cultures, ethics, and languages, Frequent changes in current economic policies and commercial laws, Changes in host government policies towards foreign investment, Technology-transfer disputes, Differences in national cultures between ICJV partners, Disagreement on allocation of work to be done, Having disagreements about accounting standards, Distrust between partner employees, Insecurity related to the possibility of leaving the Joint venture and Lack of trust between partners. Cultural differences and Lack of appropriate legislation were the least ranked. Conclusion can be drawn from the fact that these problems governing international construction joint venture project execution are critical and strategies to mitigate these problem needs to be employed. Objective one, that is, to identify problems governing international construction joint venture project execution was achieved as respondents responded to the problems identified from literature.

# 5.2.2 The implication of the ICJV challenges on project performance in Ghana

These represent the views of respondents on the implication of the challenges of International joint venture construction on project performance in Ghana. The project performance criteria highlighted here were; cost, time, quality and safety. Respondent were then ask to group the challenges under these four criteria. The study reveal that, inheriting a partner’s financial problems, having disagreements about accounting standards and frequent changes in current economic policies and commercial laws have a major implication on cost. Among these cost implications to project performance, the highest ranked is inheriting a partner’s financial problems. Expending time and energy to establish mutually agreeable managerial practices, frequent changes in current economic policies and commercial laws, Policy changes in parent companies affecting the project, Technology-transfer disputes, Differences in national cultures between ICJV partners and Disagreement on allocation of work to be done were identified as challenges of ICJV that have effect on time. The highest ranked under this category was expending time and energy to establish mutually agreeable managerial practices Lack of management competence, Erosion of applicability of certain partner competencies, Technology-transfer disputes, Misunderstanding of foreign cultures, ethics, and languages and disagreement on allocation of work to be done were classified as challenges of ICJV that have effect on quality performance of a project. The highest ranked under this category is Lack of management competence. Disagreements about staff allocation and positions in the project team hierarchy, Insecurity related to the possibility of leaving the JV and Lack of trust between partners were classified as challenges of ICJV that have effect on safety performance of a project.

# 5.2.3 Strategies for better planning and execution of international joint venture construction projects in Ghana.

The study revealed that determining the strategies for better planning and execution of international joint venture construction, dividing projects into subprojects for each partner to undertake their project risk clearly, managers should expand the data flow inside a joint venture, Interpret and respond to strategic and managerial issues, Name external director to encourage the joint venture’s interests as a whole, Name executives or an influential board president, Develop a pioneering and widely accepted classification scheme to breaks national culture into dimensions and also have formal exit mechanisms in order to avoid expensive and long lawsuits. This shows that, the identified strategies are very vital and necessary to help mitigate the problems governing international construction joint venture project execution.

# 5.3 CONCLUSION

This study explored the challenges facing international joint ventures in the execution of construction project in Ghana. In an attempt to achieve this aim, three objectives were set which includes, identifying the problems governing international joint venture construction project execution in Ghana; ascertain the outcome/implication of the challenges on project performance in Ghana; and to identify strategies for better planning and execution of international joint venture construction projects in Ghana. The study revealed that, Policy changes in parent companies was ranked as a major problem governing international joint venture construction project execution in Ghana. Other factors in other of ranking were erosion of applicability of certain partner competencies, expending time and energy to establish mutually agreeable managerial practices, inheriting a partner’s financial problems, disagreements about staff allocation and positions in the project team hierarchy, misunderstanding of foreign cultures, ethics, and languages, frequent changes in current economic policies and commercial laws, Changes in host government policies towards foreign investment, Technology-transfer disputes, Differences in national cultures between ICJV partners, Disagreement on allocation of work to be done, Having disagreements about accounting standards, Distrust between partner employees, Insecurity related to the possibility of leaving the Joint venture, and Lack of trust between. Considering the implication of the challenges on project performance in order of extremely challenging, respondents indicated that, determining the strategies for better planning and execution of international joint venture construction, dividing projects into subprojects for each partner to undertake their project risk clearly, managers ought to advance the information flow inside a joint venture, Interpret and respond to strategic and managerial issues, Name external director to promote the joint venture’s interests as a whole, Name executives or an influential board president, Develop a ground-breaking and extensively accepted classification scheme to breaks national culture into proportions and also have formal exit mechanisms in order to avoid expensive and long lawsuits are critical to project performance. Further, a number of strategies were proposed by respondents to be important.

# 5.4 RECOMMENDATION

In view of the findings of this research, the following recommendations are therefore prescribed to support Joint Venture projects in Ghana.

- Joint venture managers should improve the information flow inside a joint venture, which partially requires negotiations with a parent company on the matter of proprietary rights.

- When the conflict grows beyond the certain level, and partners find that they cannot cooperate anymore, it is necessary to have formal exit mechanisms, in order to avoid expensive and long lawsuits.

- Joint Venture partners should clearly dividing projects into subprojects for each partner to undertake their project risk clearly

- Name external director to promote the joint venture’s interests as a whole. This will go a long way to help partners to dispatch their responsibilities and obligations efficiently.

# REFERENCES

Afriyie, K. (1988). Factor Choice Characteristics and Industrial-Impact of Joint Ventures-Lessons from A Developing-Economy. Columbia Journal of World Business, Vol. 23, No. (3), pp. 51-62.

Ashley, A. & Sonner, M, (1987). Nature as infrastructure: Making and managing the Panama Canal watershed. Social Studies of Science, 42(4), 539-563.

Arditi, D., and Lee, D. E. (2003). “Assessing the corporate service quality performance of design-build contractors using quality function deployment.” Constr. Manage. Econ., 21(2), 175–185.

Aziz, A. R. (1992). Global strategies: a comparison between Japanese and American construction firms. Construction Management and Economics, 12(6), 473-484.

Bamford, J., Ernst, D., and Gubini, D. G. (2004). Launching a world class joint venture. Harvard Business Review, Vol. 82 No. (2), pp. 91 – 100.

Bamford, J., Ernst, D., and Gubini, D. G. (2004). Launching a world class joint venture. Harvard Business Review, Vol. 82 No. (2), pp. 91 – 100.

Bing, L., and Tiong, L. K. (1999). “Risk management model for international construction joint ventures.” J. Constr. Eng. Manage., 125(5), 377–384.

Bing, L., Tiong, L. K., Fan, W. W., and Chew, D. A. S. (1999). “Risk management in international construction joint ventures.” J. Constr.Eng. Manage., 125(4), 277–284.

Bilas, X., Hwang, B. G., & Yu, G. S. (2007). Identifying the critical risks in underground rail international construction joint ventures: Case study of Singapore. International Journal of Project Management, 31(4), 554-566.

Blumberg, B., Cooper, D. R., & Schindler, P. S. (2005). Business Research Methods, London 2005. Google Scholar.

Brown, L., Rugman, A., & Verbeke, A. (1989). Japanese Joint Ventures with Western Multinationals: Synthesizing the Economic and Cultural Explanations of Failure. Asia Pacific Journal of Management, 6 (2): 225

Boateng, A., and Glaister, K. W. (2000). Foreign direct investment in Ghana: Patterns of activity, distribution and the role of government policy. Journal of Euromarketing, Vol. 8, No. (4), pp. 51-74.

Büchel, B. (2003). "Managing Partner Relations in Joint Ventures “, Mit Sloan Management Review. Str. 91-95.

Burns, J. M. (2003). Transforming leadership: A new pursuit of happiness (Vol. 213). Grove Press.

Chan, E. H. W., and Tse, R. Y. C. (2003). “Cultural considerations in international construction contracts.” J. Constr. Eng. Manage., 10.1061/ (ASCE) 0733-9364(2003)129:4(375), 375–381.

Chan, E. H., and Tse, R. Y. (2003). Cultural considerations in international construction contracts. Journal of construction engineering and management, 129(4), 375-381.

Christensen, L. B., Johnson, B., Turner, L. A., and Christensen, L. B. (2011). Research methods, design, and analysis.

Christou, E., Valachis, I. and Anastasiadou, C. (2008), “Research methodology in hospitality industry: the role of the inquiry paradigms”, available at: www.ul.edu.lb/fthm/papers/ 3rd%20Axis/Methodology%20greece.doc (Accessed July, 2018).

Collis, J., & Hussey, R. (2013). Business research: A practical guide for undergraduate and postgraduate students. Macmillan International Higher Education.

Contractor, F. J., and Lorange, P. (1988). Why should firms cooperate? The strategy and economics basis for cooperative ventures. Cooperative strategies in international business, 3-30.

Creswell, J. W. (2005), Educational research: planning, conducting, and evaluating quantitative and qualitative research, 2nd edition, Upper Saddle River, NJ: Prentice Hall.

Creswell, J. W. (2007), Research design: Qualitative and quantitative approaches, 2nd edn., Thousand Oaks, CA: Sage.

Creswell, J. W. (2009), “Mapping the field of mixed methods research”, Journal of Mixed Methods Research, Vol. 3 No. 2, pp.  95-108.

Creswell, J. W. (2009). Research design: qualitative and quantitative approaches. California: Sage Publications.

Creswell, J. W., and Clark, V. L. P. (2017). Designing and conducting mixed methods research. Sage publications.

Doz Y.L., (1996) Alliance advantage—the art of creating value through partnering. Boston: Harvard Business School Press.

Easterby-Smith, M., Thorpe, R. and Lowe, A. (1991), Management research. An introduction, London, Sage.

El-Sabek, L. M., & McCabe, B. Y. (2018). Coordination challenges of production planning in the construction of international mega-projects in the Middle East. International Journal of Construction Education and Research, 14(2), 118-140.

Fellows, R. and Liu, A. (2008), Research Methods For Construction, 3rd ed, Chichester, Wiley Blackwell.

Fey, C. F. and Beamish, P. W. (2000). Joint Venture Conflict: The Case of Russian International Joint Ventures “, International Business Review, Vol.9, No.1. Str. 139-162.

Fitzgerald, B. and Howcroft, D. (1998), “Towards Dissolution of the IS Research Debate: From Polarisation to Polarity”, Journal of Information Technology, Vol. 13, No. 4, pp. 313-326.

Geringer, J. M. (1988). Joint venture partner selection: Strategies for developed countries. Praeger Pub Text.

Geringer, J. M., and Hebert, L. (1991). Measuring performance of international joint ventures. Journal of international business studies, Vol. 22, No. (2), pp. 249-263.

Geringer, J.M. and Herbert, L. (1991). Measuring Performance of International Joint Ventures. Journal of International Business Studies, Vol.22, No.2. Str. 249-263.

Greener, S. (2008), Business Research Methods. Ventus Publishing ApS, Frederiksberg, Denmark.

Griffith, D. A. (2002). The role of communication competencies in international business relationship development. Journal of World Business, 37(4), 256-265.

Gunhan, S., and Arditi, D. (2005). Factors affecting international construction. Journal of construction engineering and management, 131(3), 273-282.

Gunhan, S., and Arditi, D. (2005a). “Factors affecting international construction.” J. Constr. Eng. Manage., 131(3), 273–282.

Handas, V., & Adas, A. (1996). Predicting the level of organizational effectiveness: a methodology for the construction firm. Construction Management & Economics, 14(4), 341-352.

Han, S. H., Kim, D. Y., Kim, H., & Jang, W. S. (2008). A web-based integrated system for international project risk management. Automation in construction, 17(3), 342-356.

Han, S. H., Park, S. H., Kim, D. Y., Kim, H., and Kang, Y. W. (2007). Causes of bad profit in overseas construction projects. Journal of construction engineering and management, Vol. 133, No. (12), pp. 932-943.

Han, S. H., Diekmann, J. E. & Ock, J. H., (2005). Contractor’s Risk Attitudes in the Selection of International Construction Projects. Journal of Construction Engineering and Management, 131(3), pp. 283-292.

Harriman, D. (1988). Research trend of joint ventures in construction: a two-decade taxonomic review. Journal of facilities management, 12(2), 118-141.

Hofstede, G. (1991). Cultures and Organizations: Software of the Mind. London: McGraw-Hill.

Kauser, S., & Shaw, V. (2004). The influence of behavioural and organisational characteristics on the success of international strategic alliances. International Marketing Review, 21(1), 17-52.

Kumaraswamy, M. and Shrestha, G., (2002). Targeting ‘technology exchange’ for faster organizational and industry development. Building Research and Information, 30(3), pp. 183-195.

Kwok, H., Then, D. and Skitmore, M., (2000). Risk Management in Singapore Construction Joint Ventures. Journal of Construction Research, 1(2), pp. 139-149.

Levy, N. (2000). Performance in international construction joint ventures: Modeling perspective. Journal of Construction Engineering and Management, 129(6), 619-626.

Li, J., Qian, G., Lam, K., and Wang, D. (2000). Breaking into China: Strategic considerations for multinational corporations. Long Range Planning, Vol. 33 No. (5), pp. 673-687.

Madhok, A. (1995). Revisiting Multinational Firms' Tolerance for Joint Ventures: A Trust-Based Approach “, Journal of International Business Studies, Vol.26, No.1. Str. 117-137.

Marsh, D. and Stoker, G. (2002), Theories and Methods in Political Science, 2nd Ed. Houndmills, UK: Palgrave, Macmillan.

Mohamed, S. (2003). “Scorecard approach to benchmarking organizational safety culture in construction.” J. Constr. Eng. Manage., 129(1), 80–88.

Mohr, L., & Spekman, R. L. (1994). Risk management model for international construction joint ventures. Journal of Construction Engineering and Management, 125(5), 377-384.

Nelson, H. C. (2002). Dispute resolution management for international construction projects in China. Management decision.

Lucas, C.L. (1986), International Construction Business Management: A Guide for Architects, Engineers and Contractors, McGraw‐Hill, New York, NY.

Ofori, G. (1991). Programmes for improving the performance of contracting firms in developing countries: A review of approaches and appropriate options. Construction Management and Economics, 9(1), 19-38.

Ostler, B., Arditi, D., Dikmen, I., & Birgonul, M. T. (1988). Performance of international joint ventures in construction. Journal of Management in Engineering, 26(4), 209-222.

Parkhe, A. (1993). “Messy” research, methodological predispositions, and theory development in international joint ventures. Academy of Management review, 18(2), 227-268.

Polit, D. F., Beck, C. T., (2004), Nursing Research. Principles and Methods, 7th edn. J.B. Lippincott Williams and Wilkins Company, Philadelphia, New York, Baltimore.

Pothukuchi, V., Damanpour, F., Choi, J., Chen, C.C. and Park, S.H., (2002). National and organizational culture differences and international joint venture performance. Journal of international business studies, 33(2), pp.243-265.

Reuer, J. J. (2000). Parent firm performance across international joint venture life-cycle stages. Journal of International Business Studies, 31(1), 1-20.

Root, J. I. (1994). Entry mode taxonomy for international construction markets. Journal of Management in Engineering, 25(1), 3-11.

Saunders, M., Lewis, P. and Thronhill, A. (2012), Research Methods for Business Students, 6th ed., Prentice Hall, Cranbury, NJ.

Stebblings, S. B. (1998). “Dispute Resolution in Major Projects,” International Dispute Resolution Conference 1998, Hong Kong, 1-6.

Streubert, H. J. and Carpenter, R. D. (1999), Qualitative Research in Nursing: Advancing the Humanistic Imperative. 2nd Ed. Philadelphia: Lippincott Williams and Williams.

Sridharan, G., (1997). Determinants of Joint Venture Performance in the Construction Industry: Cases from the Mass Rapid Transit Project in Singapore, London: University of London.

Turovski, D. (2005). The Decline and Fall of Joint Ventures: How JVs Became Unpopular and Why That Could Change. Journal of Applied Corporate Finance, Vol 17, No.2. Str. 82-87.

Walker, D. H. T. & Johannes, D. S., (2003). Construction industry joint venture behaviour in Hong Kong—designed for collaborative results?. International Journal of Project Management, Volume 21, pp. 34-39.

Zhang, G., and Zou, P. X. (2007). Fuzzy analytical hierarchy process risk assessment approach for joint venture construction projects in China. Journal of Construction Engineering and Management, Vol. 133 No. (10), pp. 771-779.

Zhang, G., and Zou, P. X. (2007). Fuzzy analytical hierarchy process risk assessment approach for joint venture construction projects in China. Journal of Construction Engineering and Management, Vol. 133 No. (10), pp. 771-779.

APPENDIX

QUESTIONNAIRE SURVEY

KWAME NKRUMAH UNIVERSITY OF SCIENCE AND TECHNOLOGY, KUMASI

COLLEGE OF ART AND BUILT ENVIRONMENT

Department of Building Technology

(MSc. Construction Management)

Topic

Challenges facing international joint ventures in execution of construction projects in Ghana

Dear Sir/Madam

Many thanks for your participation. This questionnaire survey aims to determine the Challenges facing international joint ventures in execution of construction projects in Ghana. Please fill in the questionnaire using the instructions, which will only take you about 10 to 15 minutes. Please be noted that all the information you provide is anonymous and will only be used for academic purpose. Thank you again for your valuable time. If you have any queries, please feel free to contact:

JOSHUA BLERPO

Department of Building Technology

KNUST.

Tel: +233202512745

Email: joshbler@yahoo.com

Section A: Background Information

Q1. Please state your position in your firm

[	] Project Manager

[	] Engineer

[	] Contractor

[	] Architect

[	] Foreman

[	] Quantity Surveyor

[	] Construction manager

Other (please specify) ………………………………………

Q2. Educational Level

[	] Higher National Diploma (HND)

[	] Bachelor Degree

[	] MBA/MSc/MPhil

[	] PhD

Other (please specify) ………………………………………

Q3. Please indicate on average, how many ICJV (International construction Joint Venture) projects you have participated with foreign companies.

[	] less than 5 projects

[	] 5- 10 projects

[	] 11-15 projects

[	] 16 and above projects

Q4. Please indicate how long have you been working in construction industry

[	] Less than 5 years

[	] 6 to 10 years

[	] 11 to 15 years

[	] Above 16 years

Section B: Considering main objectives

PROBLEMS GOVERNING INTERNATIONAL JOINT VENTURE CONSTRUCTION PROJECT EXECUTION IN GHANA.

Q5. Please rank the under listed problems governing international joint venture construction project execution in Ghana using the Likert scale: Please respond by ticking the appropriate boxes

1=Very low;    2= Low;     3= Moderate;      4= High;       5= Very high

| NO. | Problems governing international joint venture construction project execution | levels of influence |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 1 | 2 | 3 | 4 | 5 |
| 1 | Inheriting a partner’s financial problems |  |  |  |  |  |
| 2 | Having disagreements about accounting standards |  |  |  |  |  |
| 3 | Distrust between partner employees |  |  |  |  |  |
| 4 | Policy changes in parent companies affecting the project | 1 |  |  |  |  |
| 5 | Lack of management competence |  |  |  |  |  |
| 6 | Disagreements about staff allocation and positions in the project team hierarchy | 2 |  |  |  |  |
| 9 | Disagreement on allocation of work to be done |  |  |  |  |  |
| 10 | Technology-transfer disputes |  |  |  |  |  |
| 11 | Cultural differences |  |  |  |  |  |
| 12 | Lack of appropriate legislation |  |  |  |  |  |
| 13 | Lack of trust between partners |  |  |  |  |  |
| 14 | Frequent changes in current economic policies and commercial laws |  |  |  |  |  |
| 15 | Misunderstanding of foreign cultures, ethics, and languages |  |  |  |  |  |
| 16 | Changes in host government policies towards foreign investment |  |  |  |  |  |
| 17 | Insecurity related to the possibility of leaving the JV |  |  |  |  |  |
| 18 | Differences in national cultures between ICJV partners |  |  |  |  |  |
| 19 | Expending time and energy to establish mutually agreeable managerial practices | 4 |  |  |  |  |
| 20 | Erosion of applicability of certain partner competencies | 3 |  |  |  |  |
|  | Any other, please state and rank |  |  |  |  |  |
| 21 |  |  |  |  |  |  |

THE OUTCOME/IMPLICATION OF THE CHALLENGES ON PROJECT PERFORMANCE IN GHANA

Q6. Please what is the implication of the challenges on project performance in terms of cost, time, quality and safety? Please respond by ticking the appropriate boxes that are applicable

NB: Please you can tick more than one box in each row where applicable.

| NO. | Problems governing international joint venture construction project execution | levels of influence |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Cost | Time | Quality | safety |
| 1 | Inheriting a partner’s financial problems |  |  |  |  |
| 2 | Having disagreements about accounting standards |  |  |  |  |
| 3 | Distrust between partner employees |  |  |  |  |
| 4 | Policy changes in parent companies affecting the project |  |  |  |  |
| 5 | Lack of management competence |  |  |  |  |
| 6 | Disagreements about staff allocation and positions in the project team hierarchy |  |  |  |  |
| 9 | Disagreement on allocation of work to be done |  |  |  |  |
| 10 | Technology-transfer disputes |  |  |  |  |
| 11 | Cultural differences |  |  |  |  |
| 12 | Lack of appropriate legislation |  |  |  |  |
| 13 | Lack of trust between partners |  |  |  |  |
| 14 | Frequent changes in current economic policies and commercial laws |  |  |  |  |
| 15 | Misunderstanding of foreign cultures, ethics, and languages |  |  |  |  |
| 16 | Changes in host government policies towards foreign investment |  |  |  |  |
| 17 | Insecurity related to the possibility of leaving the JV |  |  |  |  |
| 18 | Differences in national cultures between ICJV partners |  |  |  |  |
| 19 | Expending time and energy to establish mutually agreeable managerial practices |  |  |  |  |
| 20 | Erosion of applicability of certain partner competencies |  |  |  |  |
|  | Any other, please state and rank |  |  |  |  |

STRATEGIES FOR BETTER PLANNING AND EXECUTION OF INTERNATIONAL JOINT VENTURE CONSTRUCTION PROJECTS IN GHANA

Q7. Please rank the under listed strategies for better planning and execution of international joint venture construction projects in Ghana using the Likert scale: Please respond by ticking the appropriate boxes

1= Not important;     2= Less important;     3= moderately important;      4= Important;                              5= Very important

| NO. | Strategies for better planning and execution of international joint venture construction projects | levels of influence |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 1 | 2 | 3 | 4 | 5 |
| 1 | Manager should improve the information flow inside a joint venture |  |  |  |  |  |
| 2 | Have formal exit mechanisms, in order to avoid expensive and long lawsuits |  |  |  |  |  |
| 3 | Name external director to promote the joint venture’s interests as a whole. |  |  |  |  |  |
| 4 | Name executives or an influential board president |  |  |  |  |  |
| 5 | Employ an external audit |  |  |  |  |  |
| 6 | Create a real challenge process |  |  |  |  |  |
| 9 | Divide projects into subprojects for each partner to undertake their project risk clearly |  |  |  |  |  |
| 10 | Develop a pioneering and widely accepted classification scheme to breaks national culture into dimensions |  |  |  |  |  |
| 11 | Interpret and respond to strategic and managerial issues. |  |  |  |  |  |
|  | Any other, please state and rank |  |  |  |  |  |

Thank you for your time